## Build Plan w Hours
Job #: | 055-25
| Description: | SST N20 REACTOR |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean | 10 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 20 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 5 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld | 10 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck N4 & N5 | 4 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam N4 & N5 | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 22 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 11 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles STUB LEGS, LEGS, & SUPPORT LUGS | 16 |  |  |  | 0 | 0
PRE FAB |  | .170 | Roll repads: drill and tap | 4 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .250 | Roll pipe - internal coil 20 PCS 1 1/2" PIPE | 20 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts GUIDE PLATES, COIL BRACES, ETC. | 10 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes BURN HOLES IN HEADERS; DRILL HOLES IN SPARGERS | 24 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 3 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams | 2 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes | 7 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 12 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL N10 - N15 IN GUIDE PLATE | 18 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 8 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners AND WELD | 5 |  |  |  | 0 | 0
PRE FAB |  | .580 | Fabricate internal coil supports | 6 |  |  |  | 0 | 0
PRE FAB |  | .590 | Fabricate internal coil UPPER & LOWER COILS; SPARGER, ETC. | 90 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 20 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE | 2 |  |  |  | 0 | 0
FIT |  | .635 | Install internal coil and supports INSTALL SPARGER; HEADER ASSEMBLY & COOLING FEEDS | 30 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD INSIDE | 12 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 20 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls AND SET UP TRUNION | 5 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack SUPPORT RING & COMPRESSION RINGS; WELD COMPLETE | 35 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD LUGS; FIT LEGS | 20 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 6 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 8 |  |  |  | 0 | 0
FIT |  | .740 | Install dip pipes N16 & N17 | 12 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank COIL & VESSEL | 16 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 2 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 055-25
| Description: | SST N20 REACTOR |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean | 10 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 20 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 5 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld | 10 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck N4 & N5 | 4 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam N4 & N5 | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 22 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 11 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles STUB LEGS, LEGS, & SUPPORT LUGS | 16 |  |  |  | 0 | 0
PRE FAB |  | .170 | Roll repads: drill and tap | 4 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .250 | Roll pipe - internal coil 20 PCS 1 1/2" PIPE | 20 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts GUIDE PLATES, COIL BRACES, ETC. | 10 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes BURN HOLES IN HEADERS; DRILL HOLES IN SPARGERS | 24 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 3 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams | 2 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes | 7 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 12 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL N10 - N15 IN GUIDE PLATE | 18 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 8 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners AND WELD | 5 |  |  |  | 0 | 0
PRE FAB |  | .580 | Fabricate internal coil supports | 6 |  |  |  | 0 | 0
PRE FAB |  | .590 | Fabricate internal coil UPPER & LOWER COILS; SPARGER, ETC. | 90 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 20 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE | 2 |  |  |  | 0 | 0
FIT |  | .635 | Install internal coil and supports INSTALL SPARGER; HEADER ASSEMBLY & COOLING FEEDS | 30 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD INSIDE | 12 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 20 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls AND SET UP TRUNION | 5 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack SUPPORT RING & COMPRESSION RINGS; WELD COMPLETE | 35 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD LUGS; FIT LEGS | 20 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 6 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 8 |  |  |  | 0 | 0
FIT |  | .740 | Install dip pipes N16 & N17 | 12 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank COIL & VESSEL | 16 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 2 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | SST N20 REACTOR | Customer PO: | 3000836264 | Quote: | 8924.3 | SST N20 REACTOR | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-06-12 | Make Qty: | 1 | / | ea | Est Hours: | 540
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 66200 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 66201 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 66202 | 0 | Cut Nozzle Pipe and Clean | 0 | 10 | FixedHrs | 10 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 66203 | 0 | Build Nozzles-Weld | 0 | 20 | FixedHrs | 20 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________
PRE FAB | 66204 | 0 | Build Repads for Nozzles | 0 | 5 | FixedHrs | 5 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________
PRE FAB | 66205 | 0 | Build Dip Tubes-Weld | 0 | 10 | FixedHrs | 10 | .110 | 0 | Build dip tubes and weld | _________________ | _________________ | _________________
PRE FAB | 66206 | 0 | Make Manway Parts | 0 | 1 | FixedHrs | 1 | .115 | 0 | Make manway parts: cut clips, form handles, etc. | _________________ | _________________ | _________________
PRE FAB | 66207 | 0 | Roll Manway Neck | 0 | 4 | FixedHrs | 4 | .125 | 0 | Roll manway neck N4 & N5 | _________________ | _________________ | _________________
PRE FAB | 66208 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 4 | FixedHrs | 4 | .130 | 0 | Set up and weld manway flange and neck seam N4 & N5 | _________________ | _________________ | _________________
PRE FAB | 66209 | 0 | Cut Parts on Burn Table | 0 | 22 | FixedHrs | 22 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 66210 | 0 | Clean & Prep Parts | 0 | 11 | FixedHrs | 11 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 66211 | 0 | Build Supports | 0 | 16 | FixedHrs | 16 | .165 | 0 | Build supports: legs, lugs, saddles STUB LEGS, LEGS, & SUPPORT LUGS | _________________ | _________________ | _________________
PRE FAB | 66212 | 0 | Roll Repads-Drill & Tap | 0 | 4 | FixedHrs | 4 | .170 | 0 | Roll repads: drill and tap | _________________ | _________________ | _________________
PRE FAB | 66213 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 66214 | 0 | Roll Pipe-Internal Coil | 0 | 20 | FixedHrs | 20 | .250 | 0 | Roll pipe - internal coil 20 PCS 1 1/2" PIPE | _________________ | _________________ | _________________
PRE FAB | 66215 | 0 | Fab Miscellaneous Parts | 0 | 10 | FixedHrs | 10 | .252 | 0 | Fabricate miscellaneous parts GUIDE PLATES, COIL BRACES, ETC. | _________________ | _________________ | _________________
PRE FAB | 66216 | 0 | Drill/Punch holes | 0 | 24 | FixedHrs | 24 | .255 | 0 | Drill/punch holes BURN HOLES IN HEADERS; DRILL HOLES IN SPARGERS | _________________ | _________________ | _________________
PRE FAB | 66217 | 0 | Wrap Top & Bottom Heads | 0 | 1 | FixedHrs | 1 | .300 | 0 | Wrap top and bottom heads | _________________ | _________________ | _________________
INSPECTION | 66218 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 66219 | 0 | BI, SQ, T&C Shells | 0 | 3 | FixedHrs | 3 | .305 | 0 | Shells: bring in plate, square, trim and clean | _________________ | _________________ | _________________
PRE FAB | 66220 | 0 | Roll Shell, Tack-Weld I/S | 0 | 2 | FixedHrs | 2 | .315 | 0 | Roll shells, tack and weld inside seams | _________________ | _________________ | _________________
PRE FAB | 66221 | 0 | Build Top Head/Cone | 0 | 10 | FixedHrs | 10 | .350 | 0 | Build top head/cone | _________________ | _________________ | _________________
INSPECTION | 66222 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 66223 | 0 | L/O Top, B&C Holes | 0 | 7 | FixedHrs | 7 | .355 | 0 | Lay out top head, burn and clean holes | _________________ | _________________ | _________________
PRE FAB | 66224 | 0 | Set Nozzles & Lugs - Top | 0 | 12 | FixedHrs | 12 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack | _________________ | _________________ | _________________
PRE FAB | 66225 | 0 | Weld Nozzles - Top Head | 0 | 18 | FixedHrs | 18 | .366 | 0 | Weld out top head nozzles, etc. INCL N10 - N15 IN GUIDE PLATE | _________________ | _________________ | _________________
PRE FAB | 66226 | 0 | I&W Repads -Top | 0 | 8 | FixedHrs | 8 | .370 | 0 | Install and weld out repads - top head | _________________ | _________________ | _________________
PRE FAB | 66227 | 0 | Install Top Stiffeners | 0 | 5 | FixedHrs | 5 | .375 | 0 | Install top stiffeners AND WELD | _________________ | _________________ | _________________
PRE FAB | 66228 | 0 | Fab Internal Coil Support | 0 | 6 | FixedHrs | 6 | .580 | 0 | Fabricate internal coil supports | _________________ | _________________ | _________________
PRE FAB | 66229 | 0 | Fab Internal Coil | 0 | 90 | FixedHrs | 90 | .590 | 0 | Fabricate internal coil UPPER & LOWER COILS; SPARGER, ETC. | _________________ | _________________ | _________________
INSPECTION | 66230 | 0 | ASME Hold Point | 0 | 0 | FixedHrs | 0 | .OI1 | 0 | ASME Hold Point | _________________ | _________________ | _________________
FIT | 66231 | 0 | Fit Bottom Head to Shell | 0 | 20 | FixedHrs | 20 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE | _________________ | _________________ | _________________
FIT | 66232 | 0 | L/O Shell, B&C Holes | 0 | 2 | FixedHrs | 2 | .620 | 0 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE | _________________ | _________________ | _________________
FIT | 66233 | 0 | Install Internal Coil/Spt | 0 | 30 | FixedHrs | 30 | .635 | 0 | Install internal coil and supports INSTALL SPARGER; HEADER ASSEMBLY & COOLING FEEDS | _________________ | _________________ | _________________
INSPECTION | 66234 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 66235 | 0 | Fit Top to Shell | 0 | 12 | FixedHrs | 12 | .640 | 0 | Fit top head to shell - tack AND WELD INSIDE | _________________ | _________________ | _________________
FIT | 66236 | 0 | Weld all Outside Seams | 0 | 20 | FixedHrs | 20 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________
MOVE TANK | 66237 | 0 | Move Tank to Detail Rolls | 0 | 5 | FixedHrs | 5 | .800 | 0 | Move tank to detail rolls AND SET UP TRUNION | _________________ | _________________ | _________________
FIT | 66238 | 0 | Install Insul/Vac Rings | 0 | 35 | FixedHrs | 35 | .715 | 0 | Install insulation/vacuum rings - tack SUPPORT RING & COMPRESSION RINGS; WELD COMPLETE | _________________ | _________________ | _________________
FIT | 66239 | 0 | Install Support Parts | 0 | 20 | FixedHrs | 20 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD LUGS; FIT LEGS | _________________ | _________________ | _________________
FIT | 66240 | 0 | Set Nozzles in Shell | 0 | 6 | FixedHrs | 6 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________
FIT | 66241 | 0 | Weld Shell Nozz & M/Ws | 0 | 8 | FixedHrs | 8 | .726 | 0 | Weld shell nozzles, manways, etc. | _________________ | _________________ | _________________
FIT | 66242 | 0 | Install Dip Pipes | 0 | 12 | FixedHrs | 12 | .740 | 0 | Install dip pipes N16 & N17 | _________________ | _________________ | _________________
FINISHING | 66243 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 66244 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 66245 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
INSPECTION | 66246 | 0 | ASME Inspection Internal | 0 | 0 | FixedHrs | 0 | .OI2 | 0 | ASME Inspection Internal | _________________ | _________________ | _________________
MOVE TANK | 66247 | 0 | Move to Shop Test Area | 0 | 2 | FixedHrs | 2 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 66248 | 0 | Test Tank | 0 | 16 | FixedHrs | 16 | .910 | 0 | Test tank COIL & VESSEL | _________________ | _________________ | _________________
INSPECTION | 66249 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
INSPECTION | 66250 | 0 | ASME Inspection Test | 0 | 0 | FixedHrs | 0 | .OI3 | 0 | ASME Inspection Test | _________________ | _________________ | _________________
FINISHING | 66251 | 0 | Clean Tank Complete | 0 | 20 | FixedHrs | 20 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 66252 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
FINISHING | 66253 | 0 | Prepare Tank for Shipment | 0 | 3 | FixedHrs | 3 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
INSPECTION | 66254 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 66255 | 0 | Load on Truck | 0 | 2 | FixedHrs | 2 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
| Part: | SST N20 REACTOR |  |  |  | Rev:

## Tasks with Hours
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 10
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 20
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 5
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld
Hours | 10
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
Hours | 1
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck N4 & N5
Hours | 4
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam N4 & N5
Hours | 4
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 22
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
Hours | 11
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles STUB LEGS, LEGS, & SUPPORT LUGS
Hours | 16
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .170 | Roll repads: drill and tap
Hours | 4
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .250 | Roll pipe - internal coil 20 PCS 1 1/2" PIPE
Hours | 20
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts GUIDE PLATES, COIL BRACES, ETC.
Hours | 10
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes BURN HOLES IN HEADERS; DRILL HOLES IN SPARGERS
Hours | 24
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
Hours | 1
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
Hours | 3
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams
Hours | 2
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone
Hours | 10
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes
Hours | 7
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
Hours | 12
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL N10 - N15 IN GUIDE PLATE
Hours | 18
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
Hours | 8
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners AND WELD
Hours | 5
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .580 | Fabricate internal coil supports
Hours | 6
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .590 | Fabricate internal coil UPPER & LOWER COILS; SPARGER, ETC.
Hours | 90
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
Hours | 20
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE
Hours | 2
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .635 | Install internal coil and supports INSTALL SPARGER; HEADER ASSEMBLY & COOLING FEEDS
Hours | 30
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD INSIDE
Hours | 12
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 20
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls AND SET UP TRUNION
Hours | 5
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack SUPPORT RING & COMPRESSION RINGS; WELD COMPLETE
Hours | 35
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD LUGS; FIT LEGS
Hours | 20
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 6
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
Hours | 8
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .740 | Install dip pipes N16 & N17
Hours | 12
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 2
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank COIL & VESSEL
Hours | 16
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 20
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 3
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 2
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck N4 & N5
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam N4 & N5
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles STUB LEGS, LEGS, & SUPPORT LUGS
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .170 | Roll repads: drill and tap
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .250 | Roll pipe - internal coil 20 PCS 1 1/2" PIPE
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts GUIDE PLATES, COIL BRACES, ETC.
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes BURN HOLES IN HEADERS; DRILL HOLES IN SPARGERS
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL N10 - N15 IN GUIDE PLATE
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners AND WELD
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .580 | Fabricate internal coil supports
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .590 | Fabricate internal coil UPPER & LOWER COILS; SPARGER, ETC.
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON BURN TABLE
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .635 | Install internal coil and supports INSTALL SPARGER; HEADER ASSEMBLY & COOLING FEEDS
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD INSIDE
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls AND SET UP TRUNION
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack SUPPORT RING & COMPRESSION RINGS; WELD COMPLETE
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD LUGS; FIT LEGS
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .740 | Install dip pipes N16 & N17
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank COIL & VESSEL
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 055-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_