## Build Plan w Hours
Job #: | 061-25
| Description: | BUFFER TANK #6 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean INCL FOR INLET MANIFOLD | 12 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 6 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 3 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld BUILD INLET MANIFOLD | 30 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 40 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 20 |  |  |  | 0 | 0
PRE FAB |  | .175 | Build and weld base ring - skirt | 8 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes BURN HOLES IN MANIFOLD PIPE & REDUCERS | 10 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE INLET MANIFOLD PIPE SUPPORTS | 2 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 9 |  |  |  | 0 | 0
PRE FAB |  | .310 | Bevel shell plates | 12 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM W/COBOT | 18 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .360 | Bevel top head CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD | 1 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS W/REPADS | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .460 | Bevel bottom head CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete | 2 |  |  |  | 0 | 0
PRE FAB |  | .500 | Build skirt - fit and weld shells ROLL (1) SHELL; INCL WELD LONG SEAM W/COBOT | 5 |  |  |  | 0 | 0
PRE FAB |  | .510 | Build skirt; fit base ring to shell and weld FIT & TACK BASE RING TO SHELL | 5 |  |  |  | 0 | 0
FIT |  | .515 | Weld skirt shell seams and base ring WELD BASE RING TO SKIRT SHELL INSIDE & OUTSIDE | 8 |  |  |  | 0 | 0
FIT |  | .530 | Build skirt - fit anchors / gussets FIT (8) GUSSETS; TACK ONLY | 3 |  |  |  | 0 | 0
FIT |  | .545 | Weld skirt anchors, gussets, nozzles, manways, etc. WELD (8) GUSSETS | 6 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell | 4 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 8 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 18 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes PREP NOZZLE HOLES FOR FULL PEN WELDS | 6 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. INSTALL INLET MANIFOLD & SUPPORTS | 36 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 5 |  |  |  | 0 | 0
FIT |  | .641 | Weld top head to shell - inside INCL HOLE WATCH | 12 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 20 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 3 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack INCL WELD COMPLETE | 48 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT TO BOTTOM HEAD AND WELD | 32 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 8 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH & NOZZLE A | 30 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld | 5 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI4 | Customer Inspection | 0 |  |  |  | 1 | 1
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 12 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
MOVE TANK |  | .802 | Move to paint area | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 5 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 061-25
| Description: | BUFFER TANK #6 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean INCL FOR INLET MANIFOLD | 12 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 6 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 3 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld BUILD INLET MANIFOLD | 30 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 40 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 20 |  |  |  | 0 | 0
PRE FAB |  | .175 | Build and weld base ring - skirt | 8 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes BURN HOLES IN MANIFOLD PIPE & REDUCERS | 10 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE INLET MANIFOLD PIPE SUPPORTS | 2 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 9 |  |  |  | 0 | 0
PRE FAB |  | .310 | Bevel shell plates | 12 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM W/COBOT | 18 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .360 | Bevel top head CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD | 1 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS W/REPADS | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .460 | Bevel bottom head CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete | 2 |  |  |  | 0 | 0
PRE FAB |  | .500 | Build skirt - fit and weld shells ROLL (1) SHELL; INCL WELD LONG SEAM W/COBOT | 5 |  |  |  | 0 | 0
PRE FAB |  | .510 | Build skirt; fit base ring to shell and weld FIT & TACK BASE RING TO SHELL | 5 |  |  |  | 0 | 0
FIT |  | .515 | Weld skirt shell seams and base ring WELD BASE RING TO SKIRT SHELL INSIDE & OUTSIDE | 8 |  |  |  | 0 | 0
FIT |  | .530 | Build skirt - fit anchors / gussets FIT (8) GUSSETS; TACK ONLY | 3 |  |  |  | 0 | 0
FIT |  | .545 | Weld skirt anchors, gussets, nozzles, manways, etc. WELD (8) GUSSETS | 6 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell | 4 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together | 8 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 18 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes PREP NOZZLE HOLES FOR FULL PEN WELDS | 6 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. INSTALL INLET MANIFOLD & SUPPORTS | 36 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 5 |  |  |  | 0 | 0
FIT |  | .641 | Weld top head to shell - inside INCL HOLE WATCH | 12 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 20 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 3 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack INCL WELD COMPLETE | 48 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT TO BOTTOM HEAD AND WELD | 32 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 8 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH & NOZZLE A | 30 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld | 5 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI4 | Customer Inspection | 0 |  |  |  | 1 | 1
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 12 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
MOVE TANK |  | .802 | Move to paint area | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 5 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | BUFFER TANK #6 | Customer PO: | PO3662 | Quote: | 9250.1 | BUFFER TANK #6 | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-06-13 | Make Qty: | 1 | / | ea | Est Hours: | 476
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 53085 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 53086 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 53087 | 0 | Cut Nozzle Pipe and Clean | 0 | 12 | FixedHrs | 12 | .100 | 0 | Cut nozzle pipe and clean INCL FOR INLET MANIFOLD | _________________ | _________________ | _________________
PRE FAB | 53088 | 0 | Build Nozzles-Weld | 0 | 6 | FixedHrs | 6 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________
PRE FAB | 53089 | 0 | Build Repads for Nozzles | 0 | 3 | FixedHrs | 3 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________
PRE FAB | 53090 | 0 | Build Dip Tubes-Weld | 0 | 30 | FixedHrs | 30 | .110 | 0 | Build dip tubes and weld BUILD INLET MANIFOLD | _________________ | _________________ | _________________
PRE FAB | 53091 | 0 | Cut Parts on Burn Table | 0 | 40 | FixedHrs | 40 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 53092 | 0 | Clean & Prep Parts | 0 | 20 | FixedHrs | 20 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 53093 | 0 | B&W Base Ring, Skirt | 0 | 8 | FixedHrs | 8 | .175 | 0 | Build and weld base ring - skirt | _________________ | _________________ | _________________
PRE FAB | 53094 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 53095 | 0 | Drill/Punch holes | 0 | 10 | FixedHrs | 10 | .255 | 0 | Drill/punch holes BURN HOLES IN MANIFOLD PIPE & REDUCERS | _________________ | _________________ | _________________
PRE FAB | 53096 | 0 | Misc Fabrication | 0 | 2 | FixedHrs | 2 | .261 | 0 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE INLET MANIFOLD PIPE SUPPORTS | _________________ | _________________ | _________________
PRE FAB | 53097 | 0 | Wrap Top & Bottom Heads | 0 | 2 | FixedHrs | 2 | .300 | 0 | Wrap top and bottom heads | _________________ | _________________ | _________________
INSPECTION | 53098 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 53099 | 0 | BI, SQ, T&C Shells | 0 | 9 | FixedHrs | 9 | .305 | 0 | Shells: bring in plate, square, trim and clean | _________________ | _________________ | _________________
PRE FAB | 53100 | 0 | Bevel Shell Plates | 0 | 12 | FixedHrs | 12 | .310 | 0 | Bevel shell plates | _________________ | _________________ | _________________
PRE FAB | 53101 | 0 | Roll Shell, Tack-Weld I/S | 0 | 18 | FixedHrs | 18 | .315 | 0 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM W/COBOT | _________________ | _________________ | _________________
INSPECTION | 53102 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 53103 | 0 | L/O Top, B&C Holes | 0 | 1 | FixedHrs | 1 | .355 | 0 | Lay out top head, burn and clean holes | _________________ | _________________ | _________________
PRE FAB | 53104 | 0 | Bevel Top Head | 0 | 1 | FixedHrs | 1 | .360 | 0 | Bevel top head CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD | _________________ | _________________ | _________________
PRE FAB | 53105 | 0 | Set Nozzles & Lugs - Top | 0 | 1 | FixedHrs | 1 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack | _________________ | _________________ | _________________
PRE FAB | 53106 | 0 | Weld Nozzles - Top Head | 0 | 6 | FixedHrs | 6 | .366 | 0 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS W/REPADS | _________________ | _________________ | _________________
INSPECTION | 53107 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 53108 | 0 | L/O Bottom, B&C Holes | 0 | 1 | FixedHrs | 1 | .455 | 0 | Lay out bottom head, burn and clean holes | _________________ | _________________ | _________________
PRE FAB | 53109 | 0 | Bevel Bottom Head | 0 | 1 | FixedHrs | 1 | .460 | 0 | Bevel bottom head CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD | _________________ | _________________ | _________________
PRE FAB | 53110 | 0 | Set Nozzles - Bottom Head | 0 | 1 | FixedHrs | 1 | .465 | 0 | Set nozzles in bottom head - tack | _________________ | _________________ | _________________
PRE FAB | 53111 | 0 | Weld Nozzles - Bot. Head | 0 | 2 | FixedHrs | 2 | .466 | 0 | Weld nozzles in bottom head; weld complete | _________________ | _________________ | _________________
PRE FAB | 53112 | 0 | Bld Skirt, Roll & Tack | 0 | 5 | FixedHrs | 5 | .500 | 0 | Build skirt - fit and weld shells ROLL (1) SHELL; INCL WELD LONG SEAM W/COBOT | _________________ | _________________ | _________________
PRE FAB | 53113 | 0 | Bld Skirt, F&T to Base | 0 | 5 | FixedHrs | 5 | .510 | 0 | Build skirt; fit base ring to shell and weld FIT & TACK BASE RING TO SHELL | _________________ | _________________ | _________________
FIT | 53114 | 0 | Weld Skirt | 0 | 8 | FixedHrs | 8 | .515 | 0 | Weld skirt shell seams and base ring WELD BASE RING TO SKIRT SHELL INSIDE & OUTSIDE | _________________ | _________________ | _________________
FIT | 53115 | 0 | Bld Skirt, Fit Anchor/Gst | 0 | 3 | FixedHrs | 3 | .530 | 0 | Build skirt - fit anchors / gussets FIT (8) GUSSETS; TACK ONLY | _________________ | _________________ | _________________
FIT | 53116 | 0 | Weld Skirt Nozzles, Etc. | 0 | 6 | FixedHrs | 6 | .545 | 0 | Weld skirt anchors, gussets, nozzles, manways, etc. WELD (8) GUSSETS | _________________ | _________________ | _________________
INSPECTION | 53117 | 0 | ASME Hold Point | 0 | 0 | FixedHrs | 0 | .OI1 | 0 | ASME Hold Point | _________________ | _________________ | _________________
FIT | 53118 | 0 | Fit Bottom Head to Shell | 0 | 4 | FixedHrs | 4 | .600 | 0 | Fit bottom head to shell | _________________ | _________________ | _________________
FIT | 53119 | 0 | Tack Shell Courses | 0 | 8 | FixedHrs | 8 | .605 | 0 | Tack shell courses together | _________________ | _________________ | _________________
FIT | 53120 | 0 | Weld Inside Round Seams | 0 | 18 | FixedHrs | 18 | .610 | 0 | Weld inside round seams | _________________ | _________________ | _________________
FIT | 53121 | 0 | L/O Shell, B&C Holes | 0 | 6 | FixedHrs | 6 | .620 | 0 | Lay out shell, burn and clean holes PREP NOZZLE HOLES FOR FULL PEN WELDS | _________________ | _________________ | _________________
FIT | 53122 | 0 | Install Internal Parts | 0 | 36 | FixedHrs | 36 | .630 | 0 | Install internals - wear plates, rings, clips, etc. INSTALL INLET MANIFOLD & SUPPORTS | _________________ | _________________ | _________________
INSPECTION | 53123 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 53124 | 0 | Fit Top to Shell | 0 | 5 | FixedHrs | 5 | .640 | 0 | Fit top head to shell - tack | _________________ | _________________ | _________________
FIT | 53125 | 0 | Weld top to shell | 0 | 12 | FixedHrs | 12 | .641 | 0 | Weld top head to shell - inside INCL HOLE WATCH | _________________ | _________________ | _________________
FIT | 53126 | 0 | Weld all Outside Seams | 0 | 20 | FixedHrs | 20 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________
MOVE TANK | 53127 | 0 | Move Tank to Detail Rolls | 0 | 3 | FixedHrs | 3 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 53128 | 0 | Install Insul/Vac Rings | 0 | 48 | FixedHrs | 48 | .715 | 0 | Install insulation/vacuum rings - tack INCL WELD COMPLETE | _________________ | _________________ | _________________
FIT | 53129 | 0 | Install Support Parts | 0 | 32 | FixedHrs | 32 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT TO BOTTOM HEAD AND WELD | _________________ | _________________ | _________________
FIT | 53130 | 0 | Set Nozzles in Shell | 0 | 8 | FixedHrs | 8 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________
FIT | 53131 | 0 | Weld Shell Nozz & M/Ws | 0 | 30 | FixedHrs | 30 | .726 | 0 | Weld shell nozzles, manways, etc. INCL HOLE WATCH & NOZZLE A | _________________ | _________________ | _________________
FIT | 53132 | 0 | Add Repads-Weld | 0 | 5 | FixedHrs | 5 | .730 | 0 | Add repads and weld | _________________ | _________________ | _________________
FINISHING | 53133 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 53134 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 53135 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
INSPECTION | 53136 | 0 | Customer Inspection | 0 | 0 | FixedHrs | 0 | .OI4 | 0 | Customer Inspection | _________________ | _________________ | _________________
INSPECTION | 53137 | 0 | ASME Inspection Internal | 0 | 0 | FixedHrs | 0 | .OI2 | 0 | ASME Inspection Internal | _________________ | _________________ | _________________
MOVE TANK | 53138 | 0 | Move to Shop Test Area | 0 | 2 | FixedHrs | 2 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 53139 | 0 | Test Tank | 0 | 12 | FixedHrs | 12 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 53140 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
INSPECTION | 53141 | 0 | ASME Inspection Test | 0 | 0 | FixedHrs | 0 | .OI3 | 0 | ASME Inspection Test | _________________ | _________________ | _________________
MOVE TANK | 53142 | 0 | Move to Paint Area | 0 | 2 | FixedHrs | 2 | .802 | 0 | Move to paint area | _________________ | _________________ | _________________
INSPECTION | 53143 | 0 | QC Inspection - Sandblast | 0 | 0 | FixedHrs | 0 | .QC9 | 0 | QC Inspection - Sandblast | _________________ | _________________ | _________________
INSPECTION | 53144 | 0 | QC Inspection - Paint | 0 | 0 | FixedHrs | 0 | .QC90 | 0 | QC Inspection - Paint | _________________ | _________________ | _________________
FINISHING | 53145 | 0 | Prepare Tank for Shipment | 0 | 3 | FixedHrs | 3 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
INSPECTION | 53146 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 53147 | 0 | Load on Truck | 0 | 5 | FixedHrs | 5 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
| Part: | BUFFER TANK #6 |  |  |  | Rev:

## Tasks with Hours
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean INCL FOR INLET MANIFOLD
Hours | 12
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 6
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 3
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld BUILD INLET MANIFOLD
Hours | 30
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 40
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
Hours | 20
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .175 | Build and weld base ring - skirt
Hours | 8
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes BURN HOLES IN MANIFOLD PIPE & REDUCERS
Hours | 10
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE INLET MANIFOLD PIPE SUPPORTS
Hours | 2
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
Hours | 2
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
Hours | 9
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .310 | Bevel shell plates
Hours | 12
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM W/COBOT
Hours | 18
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes
Hours | 1
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .360 | Bevel top head CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD
Hours | 1
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
Hours | 1
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS W/REPADS
Hours | 6
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes
Hours | 1
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .460 | Bevel bottom head CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD
Hours | 1
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
Hours | 1
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete
Hours | 2
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .500 | Build skirt - fit and weld shells ROLL (1) SHELL; INCL WELD LONG SEAM W/COBOT
Hours | 5
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .510 | Build skirt; fit base ring to shell and weld FIT & TACK BASE RING TO SHELL
Hours | 5
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .515 | Weld skirt shell seams and base ring WELD BASE RING TO SKIRT SHELL INSIDE & OUTSIDE
Hours | 8
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .530 | Build skirt - fit anchors / gussets FIT (8) GUSSETS; TACK ONLY
Hours | 3
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .545 | Weld skirt anchors, gussets, nozzles, manways, etc. WELD (8) GUSSETS
Hours | 6
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell
Hours | 4
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
Hours | 8
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
Hours | 18
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes PREP NOZZLE HOLES FOR FULL PEN WELDS
Hours | 6
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. INSTALL INLET MANIFOLD & SUPPORTS
Hours | 36
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
Hours | 5
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .641 | Weld top head to shell - inside INCL HOLE WATCH
Hours | 12
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 20
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 3
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack INCL WELD COMPLETE
Hours | 48
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT TO BOTTOM HEAD AND WELD
Hours | 32
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 8
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH & NOZZLE A
Hours | 30
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld
Hours | 5
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI4 | Customer Inspection
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 2
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 12
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
Hours | 2
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 3
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 5
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean INCL FOR INLET MANIFOLD
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld BUILD INLET MANIFOLD
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .175 | Build and weld base ring - skirt
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes BURN HOLES IN MANIFOLD PIPE & REDUCERS
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE INLET MANIFOLD PIPE SUPPORTS
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .310 | Bevel shell plates
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM W/COBOT
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .360 | Bevel top head CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS W/REPADS
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .460 | Bevel bottom head CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .500 | Build skirt - fit and weld shells ROLL (1) SHELL; INCL WELD LONG SEAM W/COBOT
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .510 | Build skirt; fit base ring to shell and weld FIT & TACK BASE RING TO SHELL
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .515 | Weld skirt shell seams and base ring WELD BASE RING TO SKIRT SHELL INSIDE & OUTSIDE
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .530 | Build skirt - fit anchors / gussets FIT (8) GUSSETS; TACK ONLY
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .545 | Weld skirt anchors, gussets, nozzles, manways, etc. WELD (8) GUSSETS
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes PREP NOZZLE HOLES FOR FULL PEN WELDS
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. INSTALL INLET MANIFOLD & SUPPORTS
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .641 | Weld top head to shell - inside INCL HOLE WATCH
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack INCL WELD COMPLETE
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT TO BOTTOM HEAD AND WELD
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH & NOZZLE A
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI4 | Customer Inspection
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 061-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_