## Build Plan w Hours
Job #: | 078-25
| Description: | R-310 PACKED BED REACTOR |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean INCL CUT 10" SHELL | 7 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld WELD WITH COBOT | 10 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 2 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 1 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles BUILD (4) LEGS | 6 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL INSTALL (2) LIFT LUGS | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete AND INSTAL MESH | 2 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD | 4 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD | 4 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD | 5 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack AND PREP FOR FULL PEN WELDS | 8 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 15 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 078-25
| Description: | R-310 PACKED BED REACTOR |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean INCL CUT 10" SHELL | 7 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld WELD WITH COBOT | 10 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 2 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 1 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles BUILD (4) LEGS | 6 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL INSTALL (2) LIFT LUGS | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete AND INSTAL MESH | 2 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD | 4 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD | 4 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD | 5 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack AND PREP FOR FULL PEN WELDS | 8 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 15 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | R-310 PACKED BED REACTOR | Customer PO: | 63958 | Quote: | 9202.4 | R-310 PACKED BED REACTOR | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-06-25 | Make Qty: | 1 | / | ea | Est Hours: | 95
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 54751 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 54752 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 54753 | 0 | Cut Nozzle Pipe and Clean | 0 | 7 | FixedHrs | 7 | .100 | 0 | Cut nozzle pipe and clean INCL CUT 10" SHELL | _________________ | _________________ | _________________
PRE FAB | 54754 | 0 | Build Nozzles-Weld | 0 | 10 | FixedHrs | 10 | .105 | 0 | Build nozzles and weld WELD WITH COBOT | _________________ | _________________ | _________________
PRE FAB | 54755 | 0 | Cut Parts on Burn Table | 0 | 2 | FixedHrs | 2 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 54756 | 0 | Clean & Prep Parts | 0 | 1 | FixedHrs | 1 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 54757 | 0 | Build Supports | 0 | 6 | FixedHrs | 6 | .165 | 0 | Build supports: legs, lugs, saddles BUILD (4) LEGS | _________________ | _________________ | _________________
PRE FAB | 54758 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
INSPECTION | 54759 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 54760 | 0 | L/O Top, B&C Holes | 0 | 1 | FixedHrs | 1 | .355 | 0 | Lay out top head, burn and clean holes | _________________ | _________________ | _________________
PRE FAB | 54761 | 0 | Set Nozzles & Lugs - Top | 0 | 1 | FixedHrs | 1 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack | _________________ | _________________ | _________________
PRE FAB | 54762 | 0 | Weld Nozzles - Top Head | 0 | 2 | FixedHrs | 2 | .366 | 0 | Weld out top head nozzles, etc. INCL INSTALL (2) LIFT LUGS | _________________ | _________________ | _________________
INSPECTION | 54763 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 54764 | 0 | L/O Bottom, B&C Holes | 0 | 1 | FixedHrs | 1 | .455 | 0 | Lay out bottom head, burn and clean holes | _________________ | _________________ | _________________
PRE FAB | 54765 | 0 | Set Nozzles - Bottom Head | 0 | 1 | FixedHrs | 1 | .465 | 0 | Set nozzles in bottom head - tack | _________________ | _________________ | _________________
PRE FAB | 54766 | 0 | Weld Nozzles - Bot. Head | 0 | 2 | FixedHrs | 2 | .466 | 0 | Weld nozzles in bottom head; weld complete AND INSTAL MESH | _________________ | _________________ | _________________
INSPECTION | 54767 | 0 | ASME Hold Point | 0 | 0 | FixedHrs | 0 | .OI1 | 0 | ASME Hold Point | _________________ | _________________ | _________________
FIT | 54768 | 0 | Fit Bottom Head to Shell | 0 | 4 | FixedHrs | 4 | .600 | 0 | Fit bottom head to shell AND WELD | _________________ | _________________ | _________________
FIT | 54769 | 0 | L/O Shell, B&C Holes | 0 | 8 | FixedHrs | 8 | .620 | 0 | Lay out shell, burn and clean holes | _________________ | _________________ | _________________
INSPECTION | 54770 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 54771 | 0 | Fit Top to Shell | 0 | 4 | FixedHrs | 4 | .640 | 0 | Fit top head to shell - tack AND WELD | _________________ | _________________ | _________________
MOVE TANK | 54772 | 0 | Move Tank to Detail Rolls | 0 | 1 | FixedHrs | 1 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 54773 | 0 | Install Support Parts | 0 | 5 | FixedHrs | 5 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD | _________________ | _________________ | _________________
FIT | 54774 | 0 | Set Nozzles in Shell | 0 | 8 | FixedHrs | 8 | .725 | 0 | Set nozzles in shell - tack AND PREP FOR FULL PEN WELDS | _________________ | _________________ | _________________
FIT | 54775 | 0 | Weld Shell Nozz & M/Ws | 0 | 15 | FixedHrs | 15 | .726 | 0 | Weld shell nozzles, manways, etc. | _________________ | _________________ | _________________
FINISHING | 54776 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 54777 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 54778 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
INSPECTION | 54779 | 0 | ASME Inspection Internal | 0 | 0 | FixedHrs | 0 | .OI2 | 0 | ASME Inspection Internal | _________________ | _________________ | _________________
MOVE TANK | 54780 | 0 | Move to Shop Test Area | 0 | 1 | FixedHrs | 1 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 54781 | 0 | Test Tank | 0 | 6 | FixedHrs | 6 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 54782 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
INSPECTION | 54783 | 0 | ASME Inspection Test | 0 | 0 | FixedHrs | 0 | .OI3 | 0 | ASME Inspection Test | _________________ | _________________ | _________________
FINISHING | 54784 | 0 | Clean Tank Complete | 0 | 5 | FixedHrs | 5 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 54785 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
INSPECTION | 54786 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
| Part: | R-310 PACKED BED REACTOR |  |  |  | Rev:

## Tasks with Hours
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean INCL CUT 10" SHELL
Hours | 7
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld WELD WITH COBOT
Hours | 10
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 2
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
Hours | 1
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles BUILD (4) LEGS
Hours | 6
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes
Hours | 1
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
Hours | 1
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL INSTALL (2) LIFT LUGS
Hours | 2
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes
Hours | 1
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
Hours | 1
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete AND INSTAL MESH
Hours | 2
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD
Hours | 4
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes
Hours | 8
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD
Hours | 4
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 1
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD
Hours | 5
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack AND PREP FOR FULL PEN WELDS
Hours | 8
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
Hours | 15
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 1
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 6
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 5
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean INCL CUT 10" SHELL
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld WELD WITH COBOT
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles BUILD (4) LEGS
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL INSTALL (2) LIFT LUGS
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete AND INSTAL MESH
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack AND PREP FOR FULL PEN WELDS
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 078-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_