## Build Plan w Hours
Job #: | 083-25
| Description: | REACTOR 12 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean | 12 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld USE COBOT TO WELD RFSO NOZZLES | 18 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 4 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld | 4 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel NECK FOR BETTS MANWAY | 1 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 1 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 3 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 20 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 12 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles INCL STUB LEGS | 20 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts (3) DIP TUBE SUPPORTS | 3 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean PREP (1) DOUBLE SHELL | 6 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL (1) DOUBLE SHELL; WELD L/S WITH COBOT | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes CUT HOLES AT CNC TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 8 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 24 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head AND LIFT LUGS | 12 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners GUSSETS ON NOZZLE (G) | 5 |  |  |  | 0 | 0
PRE FAB |  | .390 | Grind inside welds smooth - top head GRIND WELDS SMOOTH (NOT FLUSH) | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes CUT HOLES AT CNC TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete | 2 |  |  |  | 0 | 0
FIT |  | .477 | Cut and fit jacket to bottom head | 20 |  |  |  | 0 | 0
FIT |  | .478 | Weld jacket to bottom head | 24 |  |  |  | 0 | 0
FIT |  | .479 | Install jacket nozzles - bottom head | 8 |  |  |  | 0 | 0
PRE FAB |  | .490 | Grind inside welds smooth - bottom head GRIND WELDS SMOOTH (NOT FLUSH) | 1 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 7 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON CNC TABLE | 1 |  |  |  | 0 | 0
FIT |  | .637 | Grind inside welds smooth - shell GRIND WELDS SMOOTH (NOT FLUSH) | 15 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 4 |  |  |  | 0 | 0
FIT |  | .641 | Weld top head to shell - inside INCL HOLE WATCH | 8 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams USE COLUMN & BOOM | 6 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .700 | Fit jacket to shell | 60 |  |  |  | 0 | 0
FIT |  | .705 | Weld jacket to shell | 30 |  |  |  | 0 | 0
FIT |  | .710 | Install jacket nozzles | 8 |  |  |  | 0 | 0
FIT |  | .711 | Weld jacket nozzles | 8 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack | 12 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD | 20 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 2 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH | 6 |  |  |  | 0 | 0
FIT |  | .735 | Install dip pipe supports | 4 |  |  |  | 0 | 0
FIT |  | .740 | Install dip pipes | 3 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank TANK & (3) COILS | 30 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 36 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 6 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 083-25
| Description: | REACTOR 12 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean | 12 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld USE COBOT TO WELD RFSO NOZZLES | 18 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 4 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld | 4 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel NECK FOR BETTS MANWAY | 1 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 1 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 3 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 20 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 12 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles INCL STUB LEGS | 20 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts (3) DIP TUBE SUPPORTS | 3 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean PREP (1) DOUBLE SHELL | 6 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL (1) DOUBLE SHELL; WELD L/S WITH COBOT | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes CUT HOLES AT CNC TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 8 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 24 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head AND LIFT LUGS | 12 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners GUSSETS ON NOZZLE (G) | 5 |  |  |  | 0 | 0
PRE FAB |  | .390 | Grind inside welds smooth - top head GRIND WELDS SMOOTH (NOT FLUSH) | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes CUT HOLES AT CNC TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete | 2 |  |  |  | 0 | 0
FIT |  | .477 | Cut and fit jacket to bottom head | 20 |  |  |  | 0 | 0
FIT |  | .478 | Weld jacket to bottom head | 24 |  |  |  | 0 | 0
FIT |  | .479 | Install jacket nozzles - bottom head | 8 |  |  |  | 0 | 0
PRE FAB |  | .490 | Grind inside welds smooth - bottom head GRIND WELDS SMOOTH (NOT FLUSH) | 1 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 7 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON CNC TABLE | 1 |  |  |  | 0 | 0
FIT |  | .637 | Grind inside welds smooth - shell GRIND WELDS SMOOTH (NOT FLUSH) | 15 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 4 |  |  |  | 0 | 0
FIT |  | .641 | Weld top head to shell - inside INCL HOLE WATCH | 8 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams USE COLUMN & BOOM | 6 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 2 |  |  |  | 0 | 0
FIT |  | .700 | Fit jacket to shell | 60 |  |  |  | 0 | 0
FIT |  | .705 | Weld jacket to shell | 30 |  |  |  | 0 | 0
FIT |  | .710 | Install jacket nozzles | 8 |  |  |  | 0 | 0
FIT |  | .711 | Weld jacket nozzles | 8 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack | 12 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD | 20 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 2 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH | 6 |  |  |  | 0 | 0
FIT |  | .735 | Install dip pipe supports | 4 |  |  |  | 0 | 0
FIT |  | .740 | Install dip pipes | 3 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank TANK & (3) COILS | 30 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 36 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 6 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | REACTOR 12 | Customer PO: | 4500357344 | Quote: | 9077.2 | REACTOR 12 | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-07-14 | Make Qty: | 1 | / | ea | Est Hours: | 505
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 55023 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 55024 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 55025 | 0 | Cut Nozzle Pipe and Clean | 0 | 12 | FixedHrs | 12 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 55026 | 0 | Build Nozzles-Weld | 0 | 18 | FixedHrs | 18 | .105 | 0 | Build nozzles and weld USE COBOT TO WELD RFSO NOZZLES | _________________ | _________________ | _________________
PRE FAB | 55027 | 0 | Build Repads for Nozzles | 0 | 4 | FixedHrs | 4 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________
PRE FAB | 55028 | 0 | Build Dip Tubes-Weld | 0 | 4 | FixedHrs | 4 | .110 | 0 | Build dip tubes and weld | _________________ | _________________ | _________________
PRE FAB | 55029 | 0 | Brn MW Neck, Clean, Bevel | 0 | 1 | FixedHrs | 1 | .120 | 0 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel NECK FOR BETTS MANWAY | _________________ | _________________ | _________________
PRE FAB | 55030 | 0 | Roll Manway Neck | 0 | 1 | FixedHrs | 1 | .125 | 0 | Roll manway neck | _________________ | _________________ | _________________
PRE FAB | 55031 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 3 | FixedHrs | 3 | .130 | 0 | Set up and weld manway flange and neck seam | _________________ | _________________ | _________________
PRE FAB | 55032 | 0 | Cut Parts on Burn Table | 0 | 20 | FixedHrs | 20 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 55033 | 0 | Clean & Prep Parts | 0 | 12 | FixedHrs | 12 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 55034 | 0 | Build Supports | 0 | 20 | FixedHrs | 20 | .165 | 0 | Build supports: legs, lugs, saddles INCL STUB LEGS | _________________ | _________________ | _________________
PRE FAB | 55035 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 55036 | 0 | Fab Miscellaneous Parts | 0 | 3 | FixedHrs | 3 | .252 | 0 | Fabricate miscellaneous parts (3) DIP TUBE SUPPORTS | _________________ | _________________ | _________________
PRE FAB | 55037 | 0 | Wrap Top & Bottom Heads | 0 | 2 | FixedHrs | 2 | .300 | 0 | Wrap top and bottom heads | _________________ | _________________ | _________________
INSPECTION | 55038 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 55039 | 0 | BI, SQ, T&C Shells | 0 | 6 | FixedHrs | 6 | .305 | 0 | Shells: bring in plate, square, trim and clean PREP (1) DOUBLE SHELL | _________________ | _________________ | _________________
PRE FAB | 55040 | 0 | Roll Shell, Tack-Weld I/S | 0 | 5 | FixedHrs | 5 | .315 | 0 | Roll shells, tack and weld inside seams ROLL (1) DOUBLE SHELL; WELD L/S WITH COBOT | _________________ | _________________ | _________________
INSPECTION | 55041 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 55042 | 0 | L/O Top, B&C Holes | 0 | 2 | FixedHrs | 2 | .355 | 0 | Lay out top head, burn and clean holes CUT HOLES AT CNC TABLE | _________________ | _________________ | _________________
PRE FAB | 55043 | 0 | Set Nozzles & Lugs - Top | 0 | 8 | FixedHrs | 8 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack | _________________ | _________________ | _________________
PRE FAB | 55044 | 0 | Weld Nozzles - Top Head | 0 | 24 | FixedHrs | 24 | .366 | 0 | Weld out top head nozzles, etc. | _________________ | _________________ | _________________
PRE FAB | 55045 | 0 | I&W Repads -Top | 0 | 12 | FixedHrs | 12 | .370 | 0 | Install and weld out repads - top head AND LIFT LUGS | _________________ | _________________ | _________________
PRE FAB | 55046 | 0 | Install Top Stiffeners | 0 | 5 | FixedHrs | 5 | .375 | 0 | Install top stiffeners GUSSETS ON NOZZLE (G) | _________________ | _________________ | _________________
PRE FAB | 55047 | 0 | Grind I/S Weld Smooth-Top | 0 | 8 | FixedHrs | 8 | .390 | 0 | Grind inside welds smooth - top head GRIND WELDS SMOOTH (NOT FLUSH) | _________________ | _________________ | _________________
INSPECTION | 55048 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 55049 | 0 | L/O Bottom, B&C Holes | 0 | 2 | FixedHrs | 2 | .455 | 0 | Lay out bottom head, burn and clean holes CUT HOLES AT CNC TABLE | _________________ | _________________ | _________________
PRE FAB | 55050 | 0 | Set Nozzles - Bottom Head | 0 | 1 | FixedHrs | 1 | .465 | 0 | Set nozzles in bottom head - tack | _________________ | _________________ | _________________
PRE FAB | 55051 | 0 | Weld Nozzles - Bot. Head | 0 | 2 | FixedHrs | 2 | .466 | 0 | Weld nozzles in bottom head; weld complete | _________________ | _________________ | _________________
FIT | 55052 | 0 | Cut & Fit Btm Jacket | 0 | 20 | FixedHrs | 20 | .477 | 0 | Cut and fit jacket to bottom head | _________________ | _________________ | _________________
FIT | 55053 | 0 | Weld Jacket to Bottom | 0 | 24 | FixedHrs | 24 | .478 | 0 | Weld jacket to bottom head | _________________ | _________________ | _________________
FIT | 55054 | 0 | Install Jacket Nozzle-Btm | 0 | 8 | FixedHrs | 8 | .479 | 0 | Install jacket nozzles - bottom head | _________________ | _________________ | _________________
PRE FAB | 55055 | 0 | Grind I/S Weld Smooth-Btm | 0 | 1 | FixedHrs | 1 | .490 | 0 | Grind inside welds smooth - bottom head GRIND WELDS SMOOTH (NOT FLUSH) | _________________ | _________________ | _________________
INSPECTION | 55056 | 0 | ASME Hold Point | 0 | 0 | FixedHrs | 0 | .OI1 | 0 | ASME Hold Point | _________________ | _________________ | _________________
FIT | 55057 | 0 | Fit Bottom Head to Shell | 0 | 7 | FixedHrs | 7 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE | _________________ | _________________ | _________________
FIT | 55058 | 0 | L/O Shell, B&C Holes | 0 | 1 | FixedHrs | 1 | .620 | 0 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON CNC TABLE | _________________ | _________________ | _________________
FIT | 55059 | 0 | Grind I/S Weld Smooth-Shl | 0 | 15 | FixedHrs | 15 | .637 | 0 | Grind inside welds smooth - shell GRIND WELDS SMOOTH (NOT FLUSH) | _________________ | _________________ | _________________
INSPECTION | 55060 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 55061 | 0 | Fit Top to Shell | 0 | 4 | FixedHrs | 4 | .640 | 0 | Fit top head to shell - tack | _________________ | _________________ | _________________
FIT | 55062 | 0 | Weld top to shell | 0 | 8 | FixedHrs | 8 | .641 | 0 | Weld top head to shell - inside INCL HOLE WATCH | _________________ | _________________ | _________________
FIT | 55063 | 0 | Weld all Outside Seams | 0 | 6 | FixedHrs | 6 | .645 | 0 | Weld all outside seams USE COLUMN & BOOM | _________________ | _________________ | _________________
MOVE TANK | 55064 | 0 | Move Tank to Detail Rolls | 0 | 2 | FixedHrs | 2 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 55065 | 0 | Fit Jacket to Shell | 0 | 60 | FixedHrs | 60 | .700 | 0 | Fit jacket to shell | _________________ | _________________ | _________________
FIT | 55066 | 0 | Weld Jacket to Shell | 0 | 30 | FixedHrs | 30 | .705 | 0 | Weld jacket to shell | _________________ | _________________ | _________________
FIT | 55067 | 0 | Install Jacket Nozzles | 0 | 8 | FixedHrs | 8 | .710 | 0 | Install jacket nozzles | _________________ | _________________ | _________________
FIT | 55068 | 0 | Weld Jacket Nozzles | 0 | 8 | FixedHrs | 8 | .711 | 0 | Weld jacket nozzles | _________________ | _________________ | _________________
FIT | 55069 | 0 | Install Insul/Vac Rings | 0 | 12 | FixedHrs | 12 | .715 | 0 | Install insulation/vacuum rings - tack | _________________ | _________________ | _________________
FIT | 55070 | 0 | Install Support Parts | 0 | 20 | FixedHrs | 20 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD | _________________ | _________________ | _________________
FIT | 55071 | 0 | Set Nozzles in Shell | 0 | 2 | FixedHrs | 2 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________
FIT | 55072 | 0 | Weld Shell Nozz & M/Ws | 0 | 6 | FixedHrs | 6 | .726 | 0 | Weld shell nozzles, manways, etc. INCL HOLE WATCH | _________________ | _________________ | _________________
FIT | 55073 | 0 | Install Dip Pipe Supports | 0 | 4 | FixedHrs | 4 | .735 | 0 | Install dip pipe supports | _________________ | _________________ | _________________
FIT | 55074 | 0 | Install Dip Pipes | 0 | 3 | FixedHrs | 3 | .740 | 0 | Install dip pipes | _________________ | _________________ | _________________
FINISHING | 55075 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 55076 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 55077 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
INSPECTION | 55078 | 0 | ASME Inspection Internal | 0 | 0 | FixedHrs | 0 | .OI2 | 0 | ASME Inspection Internal | _________________ | _________________ | _________________
MOVE TANK | 55079 | 0 | Move to Shop Test Area | 0 | 2 | FixedHrs | 2 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 55080 | 0 | Test Tank | 0 | 30 | FixedHrs | 30 | .910 | 0 | Test tank TANK & (3) COILS | _________________ | _________________ | _________________
INSPECTION | 55081 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
INSPECTION | 55082 | 0 | ASME Inspection Test | 0 | 0 | FixedHrs | 0 | .OI3 | 0 | ASME Inspection Test | _________________ | _________________ | _________________
FINISHING | 55083 | 0 | Clean Tank Complete | 0 | 36 | FixedHrs | 36 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 55084 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
FINISHING | 55085 | 0 | Prepare Tank for Shipment | 0 | 3 | FixedHrs | 3 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
INSPECTION | 55086 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 55087 | 0 | Load on Truck | 0 | 6 | FixedHrs | 6 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
| Part: | REACTOR 12 |  |  |  | Rev:

## Tasks with Hours
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 12
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld USE COBOT TO WELD RFSO NOZZLES
Hours | 18
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 4
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld
Hours | 4
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel NECK FOR BETTS MANWAY
Hours | 1
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
Hours | 1
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
Hours | 3
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 20
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
Hours | 12
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles INCL STUB LEGS
Hours | 20
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts (3) DIP TUBE SUPPORTS
Hours | 3
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
Hours | 2
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean PREP (1) DOUBLE SHELL
Hours | 6
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL (1) DOUBLE SHELL; WELD L/S WITH COBOT
Hours | 5
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes CUT HOLES AT CNC TABLE
Hours | 2
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
Hours | 8
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
Hours | 24
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head AND LIFT LUGS
Hours | 12
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners GUSSETS ON NOZZLE (G)
Hours | 5
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .390 | Grind inside welds smooth - top head GRIND WELDS SMOOTH (NOT FLUSH)
Hours | 8
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes CUT HOLES AT CNC TABLE
Hours | 2
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
Hours | 1
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete
Hours | 2
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .477 | Cut and fit jacket to bottom head
Hours | 20
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .478 | Weld jacket to bottom head
Hours | 24
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .479 | Install jacket nozzles - bottom head
Hours | 8
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .490 | Grind inside welds smooth - bottom head GRIND WELDS SMOOTH (NOT FLUSH)
Hours | 1
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
Hours | 7
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON CNC TABLE
Hours | 1
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .637 | Grind inside welds smooth - shell GRIND WELDS SMOOTH (NOT FLUSH)
Hours | 15
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
Hours | 4
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .641 | Weld top head to shell - inside INCL HOLE WATCH
Hours | 8
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams USE COLUMN & BOOM
Hours | 6
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 2
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .700 | Fit jacket to shell
Hours | 60
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .705 | Weld jacket to shell
Hours | 30
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .710 | Install jacket nozzles
Hours | 8
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .711 | Weld jacket nozzles
Hours | 8
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack
Hours | 12
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD
Hours | 20
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 2
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH
Hours | 6
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .735 | Install dip pipe supports
Hours | 4
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .740 | Install dip pipes
Hours | 3
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 2
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank TANK & (3) COILS
Hours | 30
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 36
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 3
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 6
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld USE COBOT TO WELD RFSO NOZZLES
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel NECK FOR BETTS MANWAY
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles INCL STUB LEGS
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts (3) DIP TUBE SUPPORTS
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean PREP (1) DOUBLE SHELL
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL (1) DOUBLE SHELL; WELD L/S WITH COBOT
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes CUT HOLES AT CNC TABLE
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head AND LIFT LUGS
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners GUSSETS ON NOZZLE (G)
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .390 | Grind inside welds smooth - top head GRIND WELDS SMOOTH (NOT FLUSH)
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes CUT HOLES AT CNC TABLE
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .477 | Cut and fit jacket to bottom head
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .478 | Weld jacket to bottom head
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .479 | Install jacket nozzles - bottom head
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .490 | Grind inside welds smooth - bottom head GRIND WELDS SMOOTH (NOT FLUSH)
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CLEAN UP HOLES CUT ON CNC TABLE
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .637 | Grind inside welds smooth - shell GRIND WELDS SMOOTH (NOT FLUSH)
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .641 | Weld top head to shell - inside INCL HOLE WATCH
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams USE COLUMN & BOOM
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .700 | Fit jacket to shell
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .705 | Weld jacket to shell
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .710 | Install jacket nozzles
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .711 | Weld jacket nozzles
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. INCL HOLE WATCH
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .735 | Install dip pipe supports
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .740 | Install dip pipes
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank TANK & (3) COILS
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 083-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_