## Build Plan w Hours
Job #: | 109-25
| Description: | ¦25-109y~ |  |  | Delivery Date:
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Description | Run Rate | Oper/Serv |  |  |  | 0 | 0
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 2 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) CUT PARTS ON TABLE & CUT SHELL PIPE TO LENGTH AT SAW | 4 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 2 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles FORM SADDLES & WELD ON GROUND LUG | 2 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell FIT BOTH LEFT AND RIGHT HEADS | 3 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CUT NOZZLE HOLES IN SHELL | 4 |  |  |  | 0 | 0
FIT |  | .637 | Grind inside welds smooth - shell | 2 |  |  |  | 0 | 0
FIT |  | .638 | Polish inside weld seams - shell | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .645 | Weld all outside seams FULL PEN BOTH LEFT AND RIGHT HEADS | 6 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | 2 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 4 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. FULL PEN FROM OUTSIDE | 6 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 1 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Location |  | Due Date |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Quantity | Name | Vendor |  |  |  | 0 | 0
35627 |  | ______________ | 0 | Build Head to Specifications |  |  |  | 0 | 0
40231 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35632 |  | ______________ | 0 | SA312-316/316L WLD #4POLISH INSIDE |  |  |  | 0 | 0
40232 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39133 |  | ______________ | 0 | Pipe 316L 2" Sch40 Welded |  |  |  | 0 | 0
SA312-316/316L |  | 0 | 0 | 0 |  |  |  | 0 | 0
40406 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39134 |  | ______________ | 0 | Flange 316L 2" 150# RFSO |  |  |  | 0 | 0
SA182F-316/316L B16.5 |  | 0 | 0 | 0 |  |  |  | 0 | 0
40406 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39135 |  | ______________ | 0 | Studpad 316L 2" 150# Std |  |  |  | 0 | 0
SA182F-316/316L B16.5 |  | 0 | 0 | 0 |  |  |  | 0 | 0
40406 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Sch End | 0 | Rev |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Description | 0 | Due Date |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 109-25
| Description: | ¦25-109y~ |  |  | Delivery Date:
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Description | Run Rate | Oper/Serv |  |  |  | 0 | 0
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 2 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) CUT PARTS ON TABLE & CUT SHELL PIPE TO LENGTH AT SAW | 4 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 2 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles FORM SADDLES & WELD ON GROUND LUG | 2 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell FIT BOTH LEFT AND RIGHT HEADS | 3 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes CUT NOZZLE HOLES IN SHELL | 4 |  |  |  | 0 | 0
FIT |  | .637 | Grind inside welds smooth - shell | 2 |  |  |  | 0 | 0
FIT |  | .638 | Polish inside weld seams - shell | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .645 | Weld all outside seams FULL PEN BOTH LEFT AND RIGHT HEADS | 6 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | 2 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 4 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. FULL PEN FROM OUTSIDE | 6 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 1 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Location |  | Due Date |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Quantity | Name | Vendor |  |  |  | 0 | 0
35627 |  | ______________ | 0 | Build Head to Specifications |  |  |  | 0 | 0
40231 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35632 |  | ______________ | 0 | SA312-316/316L WLD #4POLISH INSIDE |  |  |  | 0 | 0
40232 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39133 |  | ______________ | 0 | Pipe 316L 2" Sch40 Welded |  |  |  | 0 | 0
SA312-316/316L |  | 0 | 0 | 0 |  |  |  | 0 | 0
40406 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39134 |  | ______________ | 0 | Flange 316L 2" 150# RFSO |  |  |  | 0 | 0
SA182F-316/316L B16.5 |  | 0 | 0 | 0 |  |  |  | 0 | 0
40406 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39135 |  | ______________ | 0 | Studpad 316L 2" 150# Std |  |  |  | 0 | 0
SA182F-316/316L B16.5 |  | 0 | 0 | 0 |  |  |  | 0 | 0
40406 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Sch End | 0 | Rev |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Description | 0 | Due Date |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
¦25-109y~
Part: | V-117 | Customer PO: | 967245923 | Quote: |  | V-117 | Line: |  |  |  | Rev: |  | Drawing: |  |  | Order Qty: | 1 | / | ea | Order Date: | 2025-10-31 | Make Qty: | 1 | / | ea | Est Hours: | 56
Customer | Ship To | EPIC SYSTEMS GROUP. LLC - P&M 4142 MERAMEC BOTTOM ROAD ST. LOUIS, MO 63129 US | EPIC SYSTEMS GROUP, LLC - P&M 4142 MERAMEC BOTTOM ROAD ST. LOUIS,MO 63129 United States
Contact | Ship Via |  | Best Way | Phone | Fax | 314-845-0077 |  | 314-845-6166
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 66256 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________ | ¦66256&~ | PRE FAB
INSPECTION | 66257 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________ | ¦66257+~ | INSPECTION
PRE FAB | 66258 | 0 | Cut Nozzle Pipe and Clean | 0 | 2 | FixedHrs | 2 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________ | ¦662580~ | PRE FAB
PRE FAB | 66259 | 0 | Build Nozzles-Weld | 0 | 4 | FixedHrs | 4 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________ | ¦662595~ | PRE FAB
PRE FAB | 66260 | 0 | Cut Parts on Burn Table | 0 | 4 | FixedHrs | 4 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) CUT PARTS ON TABLE & CUT SHELL PIPE TO LENGTH AT SAW | _________________ | _________________ | _________________ | ¦66260s~ | PRE FAB
PRE FAB | 66261 | 0 | Clean & Prep Parts | 0 | 2 | FixedHrs | 2 | .156 | 0 |  | _________________ | _________________ | _________________ | ¦66261x~ | PRE FAB
PRE FAB | 66262 | 0 | Build Supports | 0 | 2 | FixedHrs | 2 | .165 | 0 | Build supports: legs, lugs, saddles FORM SADDLES & WELD ON GROUND LUG | _________________ | _________________ | _________________ | ¦66262£~ | PRE FAB
INSPECTION | 66263 | 0 | ASME Hold Point | 0 | 0 | FixedHrs | 0 | .OI1 | 0 | ASME Hold Point | _________________ | _________________ | _________________ | ¦66263¨~ | INSPECTION
FIT | 66264 | 0 | Fit Bottom Head to Shell | 0 | 3 | FixedHrs | 3 | .600 | 0 | Fit bottom head to shell FIT BOTH LEFT AND RIGHT HEADS | _________________ | _________________ | _________________ | ¦66264®~ | FIT
FIT | 66265 | 0 | L/O Shell, B&C Holes | 0 | 4 | FixedHrs | 4 | .620 | 0 | Lay out shell, burn and clean holes CUT NOZZLE HOLES IN SHELL | _________________ | _________________ | _________________ | ¦66265%~ | FIT
FIT | 66266 | 0 | Grind I/S Weld Smooth-Shl | 0 | 2 | FixedHrs | 2 | .637 | 0 | Grind inside welds smooth - shell | _________________ | _________________ | _________________ | ¦66266*~ | FIT
FIT | 66267 | 0 | Polish I/S Weld Seam-Shl | 0 | 2 | FixedHrs | 2 | .638 | 0 | Polish inside weld seams - shell | _________________ | _________________ | _________________ | ¦66267/~ | FIT
INSPECTION | 66268 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________ | ¦662684~ | INSPECTION
FIT | 66269 | 0 | Weld all Outside Seams | 0 | 6 | FixedHrs | 6 | .645 | 0 | Weld all outside seams FULL PEN BOTH LEFT AND RIGHT HEADS | _________________ | _________________ | _________________ | ¦662699~ | FIT
FIT | 66270 | 0 | Install Support Parts | 0 | 2 | FixedHrs | 2 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | _________________ | _________________ | _________________ | ¦66270w~ | FIT
FIT | 66271 | 0 | Set Nozzles in Shell | 0 | 4 | FixedHrs | 4 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________ | ¦66271¢~ | FIT
FIT | 66272 | 0 | Weld Shell Nozz & M/Ws | 0 | 6 | FixedHrs | 6 | .726 | 0 | Weld shell nozzles, manways, etc. FULL PEN FROM OUTSIDE | _________________ | _________________ | _________________ | ¦66272§~ | FIT
FINISHING | 66273 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________ | ¦66273¬~ | FINISHING
INSPECTION | 66274 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________ | ¦66274$~ | INSPECTION
INSPECTION | 66275 | 0 | ASME Inspection Internal | 0 | 0 | FixedHrs | 0 | .OI2 | 0 | ASME Inspection Internal | _________________ | _________________ | _________________ | ¦66275)~ | INSPECTION
MOVE TANK | 66276 | 0 | Move to Shop Test Area | 0 | 1 | FixedHrs | 1 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________ | ¦66276.~ | MOVE TANK
FINISHING | 66277 | 0 | Test Tank | 0 | 3 | FixedHrs | 3 | .910 | 0 | Test tank | _________________ | _________________ | _________________ | ¦662773~ | FINISHING
INSPECTION | 66278 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________ | ¦662788~ | INSPECTION
INSPECTION | 66279 | 0 | ASME Inspection Test | 0 | 0 | FixedHrs | 0 | .OI3 | 0 | ASME Inspection Test | _________________ | _________________ | _________________ | ¦66279=~ | INSPECTION
FINISHING | 66280 | 0 | Clean Tank Complete | 0 | 6 | FixedHrs | 6 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________ | ¦66280¡~ | FINISHING
INSPECTION | 66281 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________ | ¦66281¦~ | INSPECTION
FINISHING | 66282 | 0 | Prepare Tank for Shipment | 0 | 1 | FixedHrs | 1 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________ | ¦66282«~ | FINISHING
INSPECTION | 66283 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________ | ¦66283#~ | INSPECTION
SHIPPING | 66284 | 0 | Load on Truck | 0 | 1 | FixedHrs | 1 | .960 | 0 | Load on truck | _________________ | _________________ | _________________ | ¦66284(~ | SHIPPING
Materials
| Picks | Comments | Material | Primary | Due Date | Requirement Key | Description | Location | Quantity
Detail Number:
| Buys | Comments | Material Description | Requirement Key | Vendor | PO | Due Date | Quantity | Qty | Name | Date
35627 |  | HEAD | 2 | ¦35627&~ | Build Head to Specifications | ea | ______________ | ______________ | ______________
40231 | 2025-12-16 | 8
35632 |  | PIPE, 18" SCH10 (0.25" WALL) X 4' | 1 | ¦35632x~ | SA312-316/316L WLD #4POLISH INSIDE | ea | ______________ | ______________ | ______________
40232 | 2025-12-16 | 4
39133 |  | PIPE 316L 2 SC40 WLD X | 0.5 | ¦39133v~ | Pipe 316L 2" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40406 | 2026-02-16 | 1
39134 |  | FLANGE 316L 2"150 RFSO | 4 | ¦39134¡~ | Flange 316L 2" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40406 | 2026-02-16 | 10
39135 |  | STUDPAD 316L 2"150 STD | 1 | ¦39135¦~ | Studpad 316L 2" 150# Std | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40406 | 2026-02-16 | 1
| Components | Job | Sch Start | Part | Rev | Total Est Hrs | Make Qty | Sch End
/
| Services | Vendor | Service | PO | Due Date |  | Operation Key | Description | Quantity
| Part: | V-117 |  |  |  | Rev:

## Tasks with Hours
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Description | Run Rate
Hours | Oper/Serv
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 2
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 4
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) CUT PARTS ON TABLE & CUT SHELL PIPE TO LENGTH AT SAW
Hours | 4
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 2
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles FORM SADDLES & WELD ON GROUND LUG
Hours | 2
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell FIT BOTH LEFT AND RIGHT HEADS
Hours | 3
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CUT NOZZLE HOLES IN SHELL
Hours | 4
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .637 | Grind inside welds smooth - shell
Hours | 2
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .638 | Polish inside weld seams - shell
Hours | 2
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams FULL PEN BOTH LEFT AND RIGHT HEADS
Hours | 6
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE
Hours | 2
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 4
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. FULL PEN FROM OUTSIDE
Hours | 6
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 1
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 3
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 6
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 1
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 1
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Location
Hours | Due Date
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Quantity | Name
Hours | Vendor
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | Build Head to Specifications
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | SA312-316/316L WLD #4POLISH INSIDE
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | Pipe 316L 2" Sch40 Welded
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | Flange 316L 2" 150# RFSO
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | Studpad 316L 2" 150# Std
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Sch End | 0
Hours | Rev
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Description | 0
Hours | Due Date
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Description | Run Rate
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) CUT PARTS ON TABLE & CUT SHELL PIPE TO LENGTH AT SAW
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles FORM SADDLES & WELD ON GROUND LUG
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell FIT BOTH LEFT AND RIGHT HEADS
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes CUT NOZZLE HOLES IN SHELL
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .637 | Grind inside welds smooth - shell
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .638 | Polish inside weld seams - shell
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams FULL PEN BOTH LEFT AND RIGHT HEADS
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. FULL PEN FROM OUTSIDE
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Location
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Quantity | Name
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Sch End | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Description | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 109-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_