## Build Plan w Hours
Job #: | 110-25
| Description: | ¦25-110H~ |  |  | Delivery Date:
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Description | Run Rate | Oper/Serv |  |  |  | 0 | 0
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 5 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 8 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld | 2 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 10 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 5 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles TACK ONLY | 6 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts VORTEX BREAKER & (2) WEAR PADS | 2 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 2 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAM W/COBOT | 2 |  |  |  | 0 | 0
FIT |  | .325 | Install body flange on shell - tack | 1 |  |  |  | 0 | 0
FIT |  | .326 | Weld Body Flange on Shell | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL (1) LIFT LUG | 6 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL (1) LIFT LUG | 8 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 1 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners INSTALL (4) GUSSETS FOR N7 | 2 |  |  |  | 0 | 0
FIT |  | .382 | Install body flange on top head; tack | 1 |  |  |  | 0 | 0
FIT |  | .383 | Weld body flange - top head | 4 |  |  |  | 0 | 0
PRE FAB |  | .395 | Polish inside weld seams - top head | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack INCL VORTEX BREAKER | 2 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete INCL VORTEX BREAKER | 3 |  |  |  | 0 | 0
PRE FAB |  | .495 | Polish inside weld seams - bottom head INCL WEAR PADS | 3 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 5 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
FIT |  | .638 | Polish inside weld seams - shell | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 1 |  |  |  | 0 | 0
FIT |  | .641 | Weld top head to shell - inside MAKE FULL PEN WELD FROM OUTSIDE | 5 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 3 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack (2) INSULATION RINGS | 6 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | 8 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack AND WELD | 2 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
MOVE TANK |  | .801 | Move to shop test area | 0 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 2 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Location |  | Due Date |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Quantity | Name | Vendor |  |  |  | 0 | 0
35618 |  | ______________ | 0 | SA182F-316/316L |  |  |  | 0 | 0
40223 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35619 |  | ______________ | 0 | Build Head to Specifications |  |  |  | 0 | 0
40225 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35620 |  | ______________ | 0 | Plate 316L 3/16"x 60"x |  |  |  | 0 | 0
SA240-316/316L |  | 0 | 0 | 0 |  |  |  | 0 | 0
40226 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35621 |  | ______________ | 0 |  |  |  |  | 0 | 0
40226 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39122 |  | ______________ | 0 | SA193-B7 (ZINC PLATED) |  |  |  | 0 | 0
40402 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39123 |  | ______________ | 0 | SA194-2H (ZINC PLATED) |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39124 |  | ______________ | 0 | SA193-B7 (ZINC PLATED) |  |  |  | 0 | 0
40402 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39125 |  | ______________ | 0 | SA194-2H (ZINC PLATED) |  |  |  | 0 | 0
40402 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 110-25
| Description: | ¦25-110H~ |  |  | Delivery Date:
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Description | Run Rate | Oper/Serv |  |  |  | 0 | 0
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 5 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 8 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld | 2 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 10 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 5 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles TACK ONLY | 6 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts VORTEX BREAKER & (2) WEAR PADS | 2 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 2 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAM W/COBOT | 2 |  |  |  | 0 | 0
FIT |  | .325 | Install body flange on shell - tack | 1 |  |  |  | 0 | 0
FIT |  | .326 | Weld Body Flange on Shell | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL (1) LIFT LUG | 6 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL (1) LIFT LUG | 8 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 1 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners INSTALL (4) GUSSETS FOR N7 | 2 |  |  |  | 0 | 0
FIT |  | .382 | Install body flange on top head; tack | 1 |  |  |  | 0 | 0
FIT |  | .383 | Weld body flange - top head | 4 |  |  |  | 0 | 0
PRE FAB |  | .395 | Polish inside weld seams - top head | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack INCL VORTEX BREAKER | 2 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete INCL VORTEX BREAKER | 3 |  |  |  | 0 | 0
PRE FAB |  | .495 | Polish inside weld seams - bottom head INCL WEAR PADS | 3 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 5 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
FIT |  | .638 | Polish inside weld seams - shell | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 1 |  |  |  | 0 | 0
FIT |  | .641 | Weld top head to shell - inside MAKE FULL PEN WELD FROM OUTSIDE | 5 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 3 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack (2) INSULATION RINGS | 6 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | 8 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack AND WELD | 2 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
MOVE TANK |  | .801 | Move to shop test area | 0 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 2 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Location |  | Due Date |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Quantity | Name | Vendor |  |  |  | 0 | 0
35618 |  | ______________ | 0 | SA182F-316/316L |  |  |  | 0 | 0
40223 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35619 |  | ______________ | 0 | Build Head to Specifications |  |  |  | 0 | 0
40225 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35620 |  | ______________ | 0 | Plate 316L 3/16"x 60"x |  |  |  | 0 | 0
SA240-316/316L |  | 0 | 0 | 0 |  |  |  | 0 | 0
40226 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35621 |  | ______________ | 0 |  |  |  |  | 0 | 0
40226 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39122 |  | ______________ | 0 | SA193-B7 (ZINC PLATED) |  |  |  | 0 | 0
40402 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39123 |  | ______________ | 0 | SA194-2H (ZINC PLATED) |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39124 |  | ______________ | 0 | SA193-B7 (ZINC PLATED) |  |  |  | 0 | 0
40402 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39125 |  | ______________ | 0 | SA194-2H (ZINC PLATED) |  |  |  | 0 | 0
40402 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
¦25-110H~
Part: | T-117 | Customer PO: | 967245922 | Quote: | 9315.4 | T-117 | Line: |  |  |  | Rev: |  | Drawing: |  |  | Order Qty: | 1 | / | ea | Order Date: | 2025-10-31 | Make Qty: | 1 | / | ea | Est Hours: | 146
Customer | Ship To | EPIC SYSTEMS GROUP. LLC - P&M 4142 MERAMEC BOTTOM ROAD ST. LOUIS, MO 63129 US | EPIC SYSTEMS GROUP, LLC - P&M 4142 MERAMEC BOTTOM ROAD ST. LOUIS,MO 63129 United States
Contact | Ship Via |  | Best Way | Phone | Fax | 314-845-0077 |  | 314-845-6166
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 66285 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________ | ¦66285-~ | PRE FAB
INSPECTION | 66286 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________ | ¦662862~ | INSPECTION
PRE FAB | 66287 | 0 | Cut Nozzle Pipe and Clean | 0 | 5 | FixedHrs | 5 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________ | ¦662877~ | PRE FAB
PRE FAB | 66288 | 0 | Build Nozzles-Weld | 0 | 8 | FixedHrs | 8 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________ | ¦66288<~ | PRE FAB
PRE FAB | 66289 | 0 | Build Repads for Nozzles | 0 | 1 | FixedHrs | 1 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________ | ¦66289A~ | PRE FAB
PRE FAB | 66290 | 0 | Build Dip Tubes-Weld | 0 | 2 | FixedHrs | 2 | .110 | 0 | Build dip tubes and weld | _________________ | _________________ | _________________ | ¦66290¥~ | PRE FAB
PRE FAB | 66291 | 0 | Cut Parts on Burn Table | 0 | 10 | FixedHrs | 10 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________ | ¦66291ª~ | PRE FAB
PRE FAB | 66292 | 0 | Clean & Prep Parts | 0 | 5 | FixedHrs | 5 | .156 | 0 |  | _________________ | _________________ | _________________ | ¦66292"~ | PRE FAB
PRE FAB | 66293 | 0 | Build Supports | 0 | 6 | FixedHrs | 6 | .165 | 0 | Build supports: legs, lugs, saddles TACK ONLY | _________________ | _________________ | _________________ | ¦66293'~ | PRE FAB
PRE FAB | 66294 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________ | ¦66294,~ | PRE FAB
PRE FAB | 66295 | 0 | Fab Miscellaneous Parts | 0 | 2 | FixedHrs | 2 | .252 | 0 | Fabricate miscellaneous parts VORTEX BREAKER & (2) WEAR PADS | _________________ | _________________ | _________________ | ¦662951~ | PRE FAB
PRE FAB | 66296 | 0 | Wrap Top & Bottom Heads | 0 | 1 | FixedHrs | 1 | .300 | 0 | Wrap top and bottom heads | _________________ | _________________ | _________________ | ¦662966~ | PRE FAB
INSPECTION | 66297 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________ | ¦66297;~ | INSPECTION
PRE FAB | 66298 | 0 | BI, SQ, T&C Shells | 0 | 2 | FixedHrs | 2 | .305 | 0 | Shells: bring in plate, square, trim and clean | _________________ | _________________ | _________________ | ¦66298@~ | PRE FAB
PRE FAB | 66299 | 0 | Roll Shell, Tack-Weld I/S | 0 | 2 | FixedHrs | 2 | .315 | 0 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAM W/COBOT | _________________ | _________________ | _________________ | ¦66299E~ | PRE FAB
FIT | 66300 | 0 | Install Body Flg-Shell | 0 | 1 | FixedHrs | 1 | .325 | 0 | Install body flange on shell - tack | _________________ | _________________ | _________________ | ¦66300^~ | FIT
FIT | 66301 | 0 | Weld Body Flg Shell | 0 | 4 | FixedHrs | 4 | .326 | 0 | Weld Body Flange on Shell | _________________ | _________________ | _________________ | ¦66301c~ | FIT
INSPECTION | 66302 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________ | ¦66302h~ | INSPECTION
PRE FAB | 66303 | 0 | L/O Top, B&C Holes | 0 | 2 | FixedHrs | 2 | .355 | 0 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE | _________________ | _________________ | _________________ | ¦66303m~ | PRE FAB
PRE FAB | 66304 | 0 | Set Nozzles & Lugs - Top | 0 | 6 | FixedHrs | 6 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack INCL (1) LIFT LUG | _________________ | _________________ | _________________ | ¦66304r~ | PRE FAB
PRE FAB | 66305 | 0 | Weld Nozzles - Top Head | 0 | 8 | FixedHrs | 8 | .366 | 0 | Weld out top head nozzles, etc. INCL (1) LIFT LUG | _________________ | _________________ | _________________ | ¦66305w~ | PRE FAB
PRE FAB | 66306 | 0 | I&W Repads -Top | 0 | 1 | FixedHrs | 1 | .370 | 0 | Install and weld out repads - top head | _________________ | _________________ | _________________ | ¦66306¢~ | PRE FAB
PRE FAB | 66307 | 0 | Install Top Stiffeners | 0 | 2 | FixedHrs | 2 | .375 | 0 | Install top stiffeners INSTALL (4) GUSSETS FOR N7 | _________________ | _________________ | _________________ | ¦66307§~ | PRE FAB
FIT | 66308 | 0 | Install Body Flange - Top | 0 | 1 | FixedHrs | 1 | .382 | 0 | Install body flange on top head; tack | _________________ | _________________ | _________________ | ¦66308¬~ | FIT
FIT | 66309 | 0 | Weld Body Flg-Top W/C | 0 | 4 | FixedHrs | 4 | .383 | 0 | Weld body flange - top head | _________________ | _________________ | _________________ | ¦66309$~ | FIT
PRE FAB | 66310 | 0 | Polish I/S Weld Seam-Top | 0 | 4 | FixedHrs | 4 | .395 | 0 | Polish inside weld seams - top head | _________________ | _________________ | _________________ | ¦66310b~ | PRE FAB
INSPECTION | 66311 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________ | ¦66311g~ | INSPECTION
PRE FAB | 66312 | 0 | L/O Bottom, B&C Holes | 0 | 1 | FixedHrs | 1 | .455 | 0 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE | _________________ | _________________ | _________________ | ¦66312l~ | PRE FAB
PRE FAB | 66313 | 0 | Set Nozzles - Bottom Head | 0 | 2 | FixedHrs | 2 | .465 | 0 | Set nozzles in bottom head - tack INCL VORTEX BREAKER | _________________ | _________________ | _________________ | ¦66313q~ | PRE FAB
PRE FAB | 66314 | 0 | Weld Nozzles - Bot. Head | 0 | 3 | FixedHrs | 3 | .466 | 0 | Weld nozzles in bottom head; weld complete INCL VORTEX BREAKER | _________________ | _________________ | _________________ | ¦66314v~ | PRE FAB
PRE FAB | 66315 | 0 | Polish I/S Weld Seam-Btm | 0 | 3 | FixedHrs | 3 | .495 | 0 | Polish inside weld seams - bottom head INCL WEAR PADS | _________________ | _________________ | _________________ | ¦66315¡~ | PRE FAB
INSPECTION | 66316 | 0 | ASME Hold Point | 0 | 0 | FixedHrs | 0 | .OI1 | 0 | ASME Hold Point | _________________ | _________________ | _________________ | ¦66316¦~ | INSPECTION
FIT | 66317 | 0 | Fit Bottom Head to Shell | 0 | 5 | FixedHrs | 5 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE | _________________ | _________________ | _________________ | ¦66317«~ | FIT
FIT | 66318 | 0 | L/O Shell, B&C Holes | 0 | 1 | FixedHrs | 1 | .620 | 0 | Lay out shell, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________ | ¦66318#~ | FIT
FIT | 66319 | 0 | Polish I/S Weld Seam-Shl | 0 | 3 | FixedHrs | 3 | .638 | 0 | Polish inside weld seams - shell | _________________ | _________________ | _________________ | ¦66319(~ | FIT
INSPECTION | 66320 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________ | ¦66320f~ | INSPECTION
FIT | 66321 | 0 | Fit Top to Shell | 0 | 1 | FixedHrs | 1 | .640 | 0 | Fit top head to shell - tack | _________________ | _________________ | _________________ | ¦66321k~ | FIT
FIT | 66322 | 0 | Weld top to shell | 0 | 5 | FixedHrs | 5 | .641 | 0 | Weld top head to shell - inside MAKE FULL PEN WELD FROM OUTSIDE | _________________ | _________________ | _________________ | ¦66322p~ | FIT
FIT | 66323 | 0 | Weld all Outside Seams | 0 | 3 | FixedHrs | 3 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________ | ¦66323u~ | FIT
MOVE TANK | 66324 | 0 | Move Tank to Detail Rolls | 0 | 1 | FixedHrs | 1 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________ | ¦66324z~ | MOVE TANK
FIT | 66325 | 0 | Install Insul/Vac Rings | 0 | 6 | FixedHrs | 6 | .715 | 0 | Install insulation/vacuum rings - tack (2) INSULATION RINGS | _________________ | _________________ | _________________ | ¦66325¥~ | FIT
FIT | 66326 | 0 | Install Support Parts | 0 | 8 | FixedHrs | 8 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | _________________ | _________________ | _________________ | ¦66326ª~ | FIT
FIT | 66327 | 0 | Set Nozzles in Shell | 0 | 2 | FixedHrs | 2 | .725 | 0 | Set nozzles in shell - tack AND WELD | _________________ | _________________ | _________________ | ¦66327"~ | FIT
FINISHING | 66328 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________ | ¦66328'~ | FINISHING
FIT | 66329 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________ | ¦66329,~ | FIT
MOVE TANK | 66330 | 0 | Move to Shop Test Area | 0 | 0 | FixedHrs | 0 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________ | ¦66330j~ | MOVE TANK
FINISHING | 66331 | 0 | Test Tank | 0 | 10 | FixedHrs | 10 | .910 | 0 | Test tank | _________________ | _________________ | _________________ | ¦66331o~ | FINISHING
INSPECTION | 66332 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________ | ¦66332t~ | INSPECTION
INSPECTION | 66333 | 0 | ASME Inspection Test | 0 | 0 | FixedHrs | 0 | .OI3 | 0 | ASME Inspection Test | _________________ | _________________ | _________________ | ¦66333y~ | INSPECTION
FINISHING | 66334 | 0 | Clean Tank Complete | 0 | 8 | FixedHrs | 8 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________ | ¦66334¤~ | FINISHING
INSPECTION | 66335 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________ | ¦66335©~ | INSPECTION
FINISHING | 66336 | 0 | Prepare Tank for Shipment | 0 | 1 | FixedHrs | 1 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________ | ¦66336!~ | FINISHING
INSPECTION | 66337 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________ | ¦66337&~ | INSPECTION
SHIPPING | 66338 | 0 | Load on Truck | 0 | 2 | FixedHrs | 2 | .960 | 0 | Load on truck | _________________ | _________________ | _________________ | ¦66338+~ | SHIPPING
Materials
| Picks | Comments | Material | Primary | Due Date | Requirement Key | Description | Location | Quantity
Detail Number:
| Buys | Comments | Material Description | Requirement Key | Vendor | PO | Due Date | Quantity | Qty | Name | Date
35618 |  | FLANGE 36"150#RFWN SERIES-B B16.47 WITH35-5/8"BORE | 2 | ¦35618'~ | SA182F-316/316L | ea | ______________ | ______________ | ______________
40223 | 2025-12-15 | 2
35619 |  | HEAD | 2 | ¦35619,~ | Build Head to Specifications | ea | ______________ | ______________ | ______________
40225 | 2025-12-12 | 2
35620 |  | PLT 316L 3/16 X 60 X | 1 | ¦35620j~ | Plate 316L 3/16"x 60"x | ea | ______________ | ______________ | ______________
SA240-316/316L
40226 | 2025-11-20 | 1
35621 |  | EST. FUEL SURCHARGE | 1 | ¦35621o~ |  | ea | ______________ | ______________ | ______________
40226 | 2025-11-20 | 1
39122 |  | BOLT 5/8" - 11NC X 3" HH | 4 | ¦39122m~ | SA193-B7 (ZINC PLATED) | ea | ______________ | ______________ | ______________
40402 | 2026-02-02 | 4
39123 |  | STUD 7/8" - 9NC HH | 100 | ¦39123r~ | SA194-2H (ZINC PLATED) | ea | ______________ | ______________ | ______________
2026-02-02
39124 |  | STUD 7/8" - 9NC X 7" FULL THREADED | 50 | ¦39124w~ | SA193-B7 (ZINC PLATED) | ea | ______________ | ______________ | ______________
40402 | 2026-02-02 | 50
39125 |  | NUT, 5/8" - 11NC HH | 4 | ¦39125¢~ | SA194-2H (ZINC PLATED) | ea | ______________ | ______________ | ______________
40402 | 2026-02-02 | 4
39126 |  | NUT 7/8" - 9NC HH | 100 | ¦39126§~ | SA194-2H (ZINC PLATED) | ea | ______________ | ______________ | ______________
40402 | 2026-02-02 | 100
39127 |  | GASKET RING 1/8X3 150# | 1 | ¦39127¬~ | Gasket Ring 1/8"x3" 150# | ea | ______________ | ______________ | ______________
40403 | 2026-02-02 | 1
39128 |  | GASKET | 1 | ¦39128$~ | As Specified | ea | ______________ | ______________ | ______________
40403 | 2026-02-02 | 1
39129 |  | 'FREIGHT | 1 | ¦39129)~ |  | ea | ______________ | ______________ | ______________
40443 | 2026-02-12 | 1
39130 |  | PLT 316L 1/4 X 48 X | 1 | ¦39130g~ | Plate 316L 1/4"x 48"x | ea | ______________ | ______________ | ______________
SA240-316/316L 208"
40404 | 2026-01-27 | 1
39131 |  | EST FUEL SURCHARGE | 1 | ¦39131l~ |  | ea | ______________ | ______________ | ______________
40404 | 2026-01-27 | 1
39136 |  | PIPE 316L 2 SC40 WLD X | 2.5 | ¦39136«~ | Pipe 316L 2" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40406 | 2026-02-16 | 1
40406 | 2026-02-16 | 2
39137 |  | FLANGE 316L 2"150 RFSO | 6 | ¦39137#~ | Flange 316L 2" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40406 | 2026-02-16 | 10
39138 |  | CPLG 316L 1/2 3000 FULL THRD | 1 | ¦39138(~ | Coupling 316L 1/2"3000 Full Th | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.11
40406 | 2026-02-16 | 1
39139 |  | STUDPAD 316L 3"150 STD | 1 | ¦39139-~ | Studpad 316L 3" 150# Std | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40406 | 2026-02-16 | 1
39140 |  | FLANGE 316L 3/4"150 RFSO | 1 | ¦39140k~ | Flange 316L 3/4" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40406 | 2026-02-16 | 1
39141 |  | FLANGE 316L 1.5"150 RFSO | 1 | ¦39141p~ | Flange 316L 1.5" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40406 | 2026-02-16 | 1
39142 |  | FLANGE 316L 3"150 BLIND | 1 | ¦39142u~ | Flange 316L 3" 150# BLIND | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40406 | 2026-02-16 | 1
39143 |  | FLANGE 316L 3"150 RFSO | 1 | ¦39143z~ | Flange 316L 3" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40406 | 2026-02-16 | 1
39144 |  | FLANGE 316L 4"150 RFSO | 1 | ¦39144¥~ | Flange 316L 4" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40406 | 2026-02-16 | 1
39145 |  | TOE PIPE 316L 1/2 SC40 WLD X | 1 | ¦39145ª~ | TOE Pipe 316L 1/2" Sch40 Welded | ea | ______________ | ______________ | ______________
40406 | 2026-02-16 | 1
39146 |  | PIPE 316L 1 SC40 WLD X | 1 | ¦39146"~ | Pipe 316L 1" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40406 | 2026-02-16 | 1
39147 |  | PIPE 316L 3/4 SC40 WLD X | 1 | ¦39147'~ | Pipe 316L 3/4" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40406 | 2026-02-16 | 1
39148 |  | PIPE 316L 1.5 SC40 WLD X | 1 | ¦39148,~ | Pipe 316L 1.5" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40406 | 2026-02-16 | 1
39149 |  | PIPE 316L 3 SC40 WLD X | 1 | ¦391491~ | Pipe 316L 3" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40406 | 2026-02-16 | 1
39150 |  | PIPE 316L 4 SC40 WLD X | 1 | ¦39150o~ | Pipe 316L 4" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40406 | 2026-02-16 | 1
39151 |  | FLANGE 316L 1"150 RFSO | 2 | ¦39151t~ | Flange 316L 1" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40406 | 2026-02-16 | 2
39350 |  | WELD-IN THERMOWELL | 1 | ¦39350u~ | WIL12316P1T | ea | ______________ | ______________ | ______________
40443 | 2026-02-12 | 3
39355 |  | CC FEES | 1 | ¦39355'~ |  | ea | ______________ | ______________ | ______________
40443 | 2026-02-12 | 1
| Components | Job | Sch Start | Part | Rev | Total Est Hrs | Make Qty | Sch End
/
| Services | Vendor | Service | PO | Due Date |  | Operation Key | Description | Quantity
| Part: | T-117 |  |  |  | Rev:

## Tasks with Hours
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Description | Run Rate
Hours | Oper/Serv
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 5
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 8
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 1
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld
Hours | 2
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 10
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 5
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles TACK ONLY
Hours | 6
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts VORTEX BREAKER & (2) WEAR PADS
Hours | 2
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
Hours | 1
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
Hours | 2
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAM W/COBOT
Hours | 2
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .325 | Install body flange on shell - tack
Hours | 1
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .326 | Weld Body Flange on Shell
Hours | 4
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE
Hours | 2
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL (1) LIFT LUG
Hours | 6
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL (1) LIFT LUG
Hours | 8
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
Hours | 1
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners INSTALL (4) GUSSETS FOR N7
Hours | 2
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .382 | Install body flange on top head; tack
Hours | 1
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .383 | Weld body flange - top head
Hours | 4
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .395 | Polish inside weld seams - top head
Hours | 4
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE
Hours | 1
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack INCL VORTEX BREAKER
Hours | 2
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete INCL VORTEX BREAKER
Hours | 3
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .495 | Polish inside weld seams - bottom head INCL WEAR PADS
Hours | 3
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
Hours | 5
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes ON BURN TABLE
Hours | 1
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .638 | Polish inside weld seams - shell
Hours | 3
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
Hours | 1
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .641 | Weld top head to shell - inside MAKE FULL PEN WELD FROM OUTSIDE
Hours | 5
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 3
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 1
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack (2) INSULATION RINGS
Hours | 6
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE
Hours | 8
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack AND WELD
Hours | 2
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 10
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 8
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 1
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 2
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Location
Hours | Due Date
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Quantity | Name
Hours | Vendor
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | SA182F-316/316L
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | Build Head to Specifications
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | Plate 316L 3/16"x 60"x
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours
_

## Tasks - No Hours
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Description | Run Rate
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles TACK ONLY
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts VORTEX BREAKER & (2) WEAR PADS
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAM W/COBOT
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .325 | Install body flange on shell - tack
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .326 | Weld Body Flange on Shell
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL (1) LIFT LUG
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL (1) LIFT LUG
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners INSTALL (4) GUSSETS FOR N7
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .382 | Install body flange on top head; tack
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .383 | Weld body flange - top head
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .395 | Polish inside weld seams - top head
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack INCL VORTEX BREAKER
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete INCL VORTEX BREAKER
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .495 | Polish inside weld seams - bottom head INCL WEAR PADS
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes ON BURN TABLE
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .638 | Polish inside weld seams - shell
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .641 | Weld top head to shell - inside MAKE FULL PEN WELD FROM OUTSIDE
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack (2) INSULATION RINGS
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack AND WELD
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Location
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Quantity | Name
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 110-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_