## Build Plan w Hours
Job #: | 111-25
| Description: | ¦25-111N~ |  |  | Delivery Date:
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Description | Run Rate | Oper/Serv |  |  |  | 0 | 0
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 4 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 6 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 2 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld | 1 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 1 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 2 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 2 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 10 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 5 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles TACK ONLY | 6 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. INCL MAKE & POLISH VORTEX BREAKER | 4 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 2 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAM W/ COBOT | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL (2) LIFT LUGS | 7 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | 10 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 3 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners GUSSETS FOR N3 | 2 |  |  |  | 0 | 0
PRE FAB |  | .395 | Polish inside weld seams - top head | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack INCL VORTEX BREAKER | 3 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete INCL VORTEX BREAKER | 3 |  |  |  | 0 | 0
PRE FAB |  | .495 | Polish inside weld seams - bottom head | 2 |  |  |  | 0 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 5 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
FIT |  | .638 | Polish inside weld seams - shell INCL HOLE WATCH | 14 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD INSIDE (INCL HOLE WATCH) | 8 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .700 | Fit jacket to shell | 8 |  |  |  | 0 | 0
FIT |  | .705 | Weld jacket to shell | 16 |  |  |  | 0 | 0
FIT |  | .710 | Install jacket nozzles | 3 |  |  |  | 0 | 0
FIT |  | .711 | Weld jacket nozzles | 3 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack | 12 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | 8 |  |  |  | 0 | 0
FIT |  | .735 | Install dip pipe supports | 3 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank FOR TANK AND JACKET | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 2 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Location |  | Due Date |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Quantity | Name | Vendor |  |  |  | 0 | 0
35635 |  | ______________ | 0 | Build Head to Specifications |  |  |  | 0 | 0
40233 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35679 |  | ______________ | 0 | Plate 316L 3/16"x 72"x |  |  |  | 0 | 0
SA240-316/316L |  | 0 | 0 | 0 |  |  |  | 0 | 0
40244 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35789 |  | ______________ | 0 | Build Dipple Jacket to Specs |  |  |  | 0 | 0
40283 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35791 |  | ______________ | 0 |  |  |  |  | 0 | 0
40283 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39351 |  | ______________ | 0 | WIL12316P1T |  |  |  | 0 | 0
40443 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39642 |  | ______________ | 0 | Plate 316L 1/4"x 48"x |  |  |  | 0 | 0
SA240-316/316L 208" |  | 0 | 0 | 0 |  |  |  | 0 | 0
40557 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39643 |  | ______________ | 0 | Plate 304L 1/4"x 48"x |  |  |  | 0 | 0
SA240-304/304L |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 111-25
| Description: | ¦25-111N~ |  |  | Delivery Date:
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Description | Run Rate | Oper/Serv |  |  |  | 0 | 0
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 4 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 6 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 2 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld | 1 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 1 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 2 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 2 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 10 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 5 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles TACK ONLY | 6 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. INCL MAKE & POLISH VORTEX BREAKER | 4 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 2 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAM W/ COBOT | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL (2) LIFT LUGS | 7 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | 10 |  |  |  | 0 | 0
PRE FAB |  | .370 | Install and weld out repads - top head | 3 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners GUSSETS FOR N3 | 2 |  |  |  | 0 | 0
PRE FAB |  | .395 | Polish inside weld seams - top head | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack INCL VORTEX BREAKER | 3 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete INCL VORTEX BREAKER | 3 |  |  |  | 0 | 0
PRE FAB |  | .495 | Polish inside weld seams - bottom head | 2 |  |  |  | 0 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 5 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
FIT |  | .638 | Polish inside weld seams - shell INCL HOLE WATCH | 14 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD INSIDE (INCL HOLE WATCH) | 8 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .700 | Fit jacket to shell | 8 |  |  |  | 0 | 0
FIT |  | .705 | Weld jacket to shell | 16 |  |  |  | 0 | 0
FIT |  | .710 | Install jacket nozzles | 3 |  |  |  | 0 | 0
FIT |  | .711 | Weld jacket nozzles | 3 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack | 12 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | 8 |  |  |  | 0 | 0
FIT |  | .735 | Install dip pipe supports | 3 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank FOR TANK AND JACKET | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 2 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Location |  | Due Date |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Quantity | Name | Vendor |  |  |  | 0 | 0
35635 |  | ______________ | 0 | Build Head to Specifications |  |  |  | 0 | 0
40233 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35679 |  | ______________ | 0 | Plate 316L 3/16"x 72"x |  |  |  | 0 | 0
SA240-316/316L |  | 0 | 0 | 0 |  |  |  | 0 | 0
40244 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35789 |  | ______________ | 0 | Build Dipple Jacket to Specs |  |  |  | 0 | 0
40283 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35791 |  | ______________ | 0 |  |  |  |  | 0 | 0
40283 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39351 |  | ______________ | 0 | WIL12316P1T |  |  |  | 0 | 0
40443 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39642 |  | ______________ | 0 | Plate 316L 1/4"x 48"x |  |  |  | 0 | 0
SA240-316/316L 208" |  | 0 | 0 | 0 |  |  |  | 0 | 0
40557 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39643 |  | ______________ | 0 | Plate 304L 1/4"x 48"x |  |  |  | 0 | 0
SA240-304/304L |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
¦25-111N~
Part: | T-118A | Customer PO: | 967245922 | Quote: | 9315.4 | T-118A | Line: |  |  |  | Rev: |  | Drawing: |  |  | Order Qty: | 1 | / | ea | Order Date: | 2025-10-31 | Make Qty: | 1 | / | ea | Est Hours: | 205
Customer | Ship To | EPIC SYSTEMS GROUP. LLC - P&M 4142 MERAMEC BOTTOM ROAD ST. LOUIS, MO 63129 US | EPIC SYSTEMS GROUP, LLC - P&M 4142 MERAMEC BOTTOM ROAD ST. LOUIS,MO 63129 United States
Contact | Ship Via |  | Best Way | Phone | Fax | 314-845-0077 |  | 314-845-6166
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 66339 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________ | ¦663390~ | PRE FAB
INSPECTION | 66340 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________ | ¦66340n~ | INSPECTION
PRE FAB | 66341 | 0 | Cut Nozzle Pipe and Clean | 0 | 4 | FixedHrs | 4 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________ | ¦66341s~ | PRE FAB
PRE FAB | 66342 | 0 | Build Nozzles-Weld | 0 | 6 | FixedHrs | 6 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________ | ¦66342x~ | PRE FAB
PRE FAB | 66343 | 0 | Build Repads for Nozzles | 0 | 2 | FixedHrs | 2 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________ | ¦66343£~ | PRE FAB
PRE FAB | 66344 | 0 | Build Dip Tubes-Weld | 0 | 1 | FixedHrs | 1 | .110 | 0 | Build dip tubes and weld | _________________ | _________________ | _________________ | ¦66344¨~ | PRE FAB
PRE FAB | 66345 | 0 | Make Manway Parts | 0 | 2 | FixedHrs | 2 | .115 | 0 | Make manway parts: cut clips, form handles, etc. | _________________ | _________________ | _________________ | ¦66345®~ | PRE FAB
PRE FAB | 66346 | 0 | Roll Manway Neck | 0 | 1 | FixedHrs | 1 | .125 | 0 | Roll manway neck | _________________ | _________________ | _________________ | ¦66346%~ | PRE FAB
PRE FAB | 66347 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 2 | FixedHrs | 2 | .130 | 0 | Set up and weld manway flange and neck seam | _________________ | _________________ | _________________ | ¦66347*~ | PRE FAB
PRE FAB | 66348 | 0 | Bld Davit Arm Aby Cover | 0 | 2 | FixedHrs | 2 | .135 | 0 | Build davit arm assembly and cover | _________________ | _________________ | _________________ | ¦66348/~ | PRE FAB
PRE FAB | 66349 | 0 | Cut Parts on Burn Table | 0 | 10 | FixedHrs | 10 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________ | ¦663494~ | PRE FAB
PRE FAB | 66350 | 0 | Clean & Prep Parts | 0 | 5 | FixedHrs | 5 | .156 | 0 |  | _________________ | _________________ | _________________ | ¦66350r~ | PRE FAB
PRE FAB | 66351 | 0 | Build Supports | 0 | 6 | FixedHrs | 6 | .165 | 0 | Build supports: legs, lugs, saddles TACK ONLY | _________________ | _________________ | _________________ | ¦66351w~ | PRE FAB
PRE FAB | 66352 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 4 | FixedHrs | 4 | .200 | 0 | Make lift lugs, ground lugs, etc. INCL MAKE & POLISH VORTEX BREAKER | _________________ | _________________ | _________________ | ¦66352¢~ | PRE FAB
PRE FAB | 66353 | 0 | Wrap Top & Bottom Heads | 0 | 1 | FixedHrs | 1 | .300 | 0 | Wrap top and bottom heads | _________________ | _________________ | _________________ | ¦66353§~ | PRE FAB
INSPECTION | 66354 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________ | ¦66354¬~ | INSPECTION
PRE FAB | 66355 | 0 | BI, SQ, T&C Shells | 0 | 2 | FixedHrs | 2 | .305 | 0 | Shells: bring in plate, square, trim and clean | _________________ | _________________ | _________________ | ¦66355$~ | PRE FAB
PRE FAB | 66356 | 0 | Roll Shell, Tack-Weld I/S | 0 | 2 | FixedHrs | 2 | .315 | 0 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAM W/ COBOT | _________________ | _________________ | _________________ | ¦66356)~ | PRE FAB
INSPECTION | 66357 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________ | ¦66357.~ | INSPECTION
PRE FAB | 66358 | 0 | L/O Top, B&C Holes | 0 | 2 | FixedHrs | 2 | .355 | 0 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE | _________________ | _________________ | _________________ | ¦663583~ | PRE FAB
PRE FAB | 66359 | 0 | Set Nozzles & Lugs - Top | 0 | 7 | FixedHrs | 7 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack INCL (2) LIFT LUGS | _________________ | _________________ | _________________ | ¦663598~ | PRE FAB
PRE FAB | 66360 | 0 | Weld Nozzles - Top Head | 0 | 10 | FixedHrs | 10 | .366 | 0 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | _________________ | _________________ | _________________ | ¦66360v~ | PRE FAB
PRE FAB | 66361 | 0 | I&W Repads -Top | 0 | 3 | FixedHrs | 3 | .370 | 0 | Install and weld out repads - top head | _________________ | _________________ | _________________ | ¦66361¡~ | PRE FAB
PRE FAB | 66362 | 0 | Install Top Stiffeners | 0 | 2 | FixedHrs | 2 | .375 | 0 | Install top stiffeners GUSSETS FOR N3 | _________________ | _________________ | _________________ | ¦66362¦~ | PRE FAB
PRE FAB | 66363 | 0 | Polish I/S Weld Seam-Top | 0 | 6 | FixedHrs | 6 | .395 | 0 | Polish inside weld seams - top head | _________________ | _________________ | _________________ | ¦66363«~ | PRE FAB
INSPECTION | 66364 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________ | ¦66364#~ | INSPECTION
PRE FAB | 66365 | 0 | L/O Bottom, B&C Holes | 0 | 1 | FixedHrs | 1 | .455 | 0 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE | _________________ | _________________ | _________________ | ¦66365(~ | PRE FAB
PRE FAB | 66366 | 0 | Set Nozzles - Bottom Head | 0 | 3 | FixedHrs | 3 | .465 | 0 | Set nozzles in bottom head - tack INCL VORTEX BREAKER | _________________ | _________________ | _________________ | ¦66366-~ | PRE FAB
PRE FAB | 66367 | 0 | Weld Nozzles - Bot. Head | 0 | 3 | FixedHrs | 3 | .466 | 0 | Weld nozzles in bottom head; weld complete INCL VORTEX BREAKER | _________________ | _________________ | _________________ | ¦663672~ | PRE FAB
PRE FAB | 66395 | 0 | Polish I/S Weld Seam-Btm | 0 | 2 | FixedHrs | 2 | .495 | 0 | Polish inside weld seams - bottom head | _________________ | _________________ | _________________ | ¦663954~ | PRE FAB
INSPECTION | 66368 | 0 | ASME Inspection Internal | 0 | 0 | FixedHrs | 0 | .OI2 | 0 | ASME Inspection Internal | _________________ | _________________ | _________________ | ¦663687~ | INSPECTION
FIT | 66369 | 0 | Fit Bottom Head to Shell | 0 | 5 | FixedHrs | 5 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE | _________________ | _________________ | _________________ | ¦66369<~ | FIT
FIT | 66370 | 0 | L/O Shell, B&C Holes | 0 | 1 | FixedHrs | 1 | .620 | 0 | Lay out shell, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________ | ¦66370z~ | FIT
FIT | 66371 | 0 | Polish I/S Weld Seam-Shl | 0 | 14 | FixedHrs | 14 | .638 | 0 | Polish inside weld seams - shell INCL HOLE WATCH | _________________ | _________________ | _________________ | ¦66371¥~ | FIT
INSPECTION | 66372 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________ | ¦66372ª~ | INSPECTION
FIT | 66373 | 0 | Fit Top to Shell | 0 | 8 | FixedHrs | 8 | .640 | 0 | Fit top head to shell - tack AND WELD INSIDE (INCL HOLE WATCH) | _________________ | _________________ | _________________ | ¦66373"~ | FIT
MOVE TANK | 66374 | 0 | Move Tank to Detail Rolls | 0 | 1 | FixedHrs | 1 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________ | ¦66374'~ | MOVE TANK
FIT | 66375 | 0 | Fit Jacket to Shell | 0 | 8 | FixedHrs | 8 | .700 | 0 | Fit jacket to shell | _________________ | _________________ | _________________ | ¦66375,~ | FIT
FIT | 66376 | 0 | Weld Jacket to Shell | 0 | 16 | FixedHrs | 16 | .705 | 0 | Weld jacket to shell | _________________ | _________________ | _________________ | ¦663761~ | FIT
FIT | 66377 | 0 | Install Jacket Nozzles | 0 | 3 | FixedHrs | 3 | .710 | 0 | Install jacket nozzles | _________________ | _________________ | _________________ | ¦663776~ | FIT
FIT | 66378 | 0 | Weld Jacket Nozzles | 0 | 3 | FixedHrs | 3 | .711 | 0 | Weld jacket nozzles | _________________ | _________________ | _________________ | ¦66378;~ | FIT
FIT | 66379 | 0 | Install Insul/Vac Rings | 0 | 12 | FixedHrs | 12 | .715 | 0 | Install insulation/vacuum rings - tack | _________________ | _________________ | _________________ | ¦66379@~ | FIT
FIT | 66380 | 0 | Install Support Parts | 0 | 8 | FixedHrs | 8 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | _________________ | _________________ | _________________ | ¦66380¤~ | FIT
FIT | 66381 | 0 | Install Dip Pipe Supports | 0 | 3 | FixedHrs | 3 | .735 | 0 | Install dip pipe supports | _________________ | _________________ | _________________ | ¦66381©~ | FIT
FINISHING | 66382 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________ | ¦66382!~ | FINISHING
FIT | 66383 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________ | ¦66383&~ | FIT
INSPECTION | 66384 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________ | ¦66384+~ | INSPECTION
INSPECTION | 66385 | 0 | ASME Inspection Internal | 0 | 0 | FixedHrs | 0 | .OI2 | 0 | ASME Inspection Internal | _________________ | _________________ | _________________ | ¦663850~ | INSPECTION
MOVE TANK | 66386 | 0 | Move to Shop Test Area | 0 | 1 | FixedHrs | 1 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________ | ¦663865~ | MOVE TANK
FINISHING | 66387 | 0 | Test Tank | 0 | 20 | FixedHrs | 20 | .910 | 0 | Test tank FOR TANK AND JACKET | _________________ | _________________ | _________________ | ¦66387:~ | FINISHING
INSPECTION | 66388 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________ | ¦66388?~ | INSPECTION
INSPECTION | 66389 | 0 | ASME Inspection Test | 0 | 0 | FixedHrs | 0 | .OI3 | 0 | ASME Inspection Test | _________________ | _________________ | _________________ | ¦66389D~ | INSPECTION
FINISHING | 66390 | 0 | Clean Tank Complete | 0 | 8 | FixedHrs | 8 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________ | ¦66390¨~ | FINISHING
INSPECTION | 66391 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________ | ¦66391®~ | INSPECTION
FINISHING | 66392 | 0 | Prepare Tank for Shipment | 0 | 1 | FixedHrs | 1 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________ | ¦66392%~ | FINISHING
INSPECTION | 66393 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________ | ¦66393*~ | INSPECTION
SHIPPING | 66394 | 0 | Load on Truck | 0 | 2 | FixedHrs | 2 | .960 | 0 | Load on truck | _________________ | _________________ | _________________ | ¦66394/~ | SHIPPING
Materials
| Picks | Comments | Material | Primary | Due Date | Requirement Key | Description | Location | Quantity
Detail Number:
| Buys | Comments | Material Description | Requirement Key | Vendor | PO | Due Date | Quantity | Qty | Name | Date
35635 |  | HEAD | 2 | ¦35635®~ | Build Head to Specifications | ea | ______________ | ______________ | ______________
40233 | 2026-01-23 | 4
35679 |  | PLT 316L 3/16 X 72 X | 1 | ¦35679D~ | Plate 316L 3/16"x 72"x | ea | ______________ | ______________ | ______________
SA240-316/316L
40244 | 2025-12-17 | 2
35789 |  | DIPPLE JACKET | 1 | ¦35789K~ | Build Dipple Jacket to Specs | ea | ______________ | ______________ | ______________
40283 | 2025-12-29 | 2
35791 |  | 'FREIGHT | 0.5 | ¦35791'~ |  | ea | ______________ | ______________ | ______________
40283 | 2025-12-29 | 1
39351 |  | WELD-IN THERMOWELL | 1 | ¦39351z~ | WIL12316P1T | ea | ______________ | ______________ | ______________
40443 | 2026-02-12 | 3
39642 |  | PLT 316L 1/4 X 48 X | 0.5 | ¦39642ª~ | Plate 316L 1/4"x 48"x | ea | ______________ | ______________ | ______________
SA240-316/316L 208"
40557 | 2026-04-02 | 1
39643 |  | PLT 304L 1/4 X 48 X | 0.5 | ¦39643"~ | Plate 304L 1/4"x 48"x | ea | ______________ | ______________ | ______________
SA240-304/304L
40557 | 2026-04-02 | 1
39646 |  | EST. FUEL SURCHARGE | 1 | ¦396461~ |  | ea | ______________ | ______________ | ______________
40557 | 2026-04-02 | 1
39647 |  | GASKET RING 1/8X16 150# | 1 | ¦396476~ | Gasket Ring 1/8"x16" 150# | ea | ______________ | ______________ | ______________
40561 | 2026-03-12 | 2
39662 |  | STUD, 1" - 8NC X 6 1/2" FULL THREADED | 16 | ¦39662%~ | SA193-B7 (ZINC COATED) | ea | ______________ | ______________ | ______________
40571 | 2026-03-16 | 32
39663 |  | NUT, 1" - 8NC HH | 32 | ¦39663*~ | SA194-2H (ZINC COATED) | ea | ______________ | ______________ | ______________
40571 | 2026-03-16 | 64
39685 |  | PIPE 316L 3 SC40 WLD X | 1 | ¦39685<~ | Pipe 316L 3" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40578 | 2026-04-02 | 1
39686 |  | FLANGE 304L 2"150 RFSO | 2 | ¦39686A~ | Flange 304L 2" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-304/304L B16.5
40578 | 2026-04-02 | 4
39687 |  | PIPE 304L 2 SC40 WLD X | 0.5 | ¦39687F~ | Pipe 304L 2" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-304/304L
40578 | 2026-04-02 | 1
39688 |  | FLANGE 316L 16"150 BLIND | 1 | ¦39688K~ | Flange 316L 16" 150 BLIND | ea | ______________ | ______________ | ______________
40578 | 2026-04-02 | 2
39689 |  | FLANGE 316L 1"150 RFSO | 1 | ¦39689P~ | Flange 316L 1" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40578 | 2026-04-02 | 2
39690 |  | FLANGE 316L 2"150 RFSO | 3 | ¦39690'~ | Flange 316L 2" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40578 | 2026-04-02 | 6
39691 |  | FLANGE 316L 3"150 RFSO | 3 | ¦39691,~ | Flange 316L 3" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40578 | 2026-04-02 | 6
39692 |  | FLANGE 316L 16"150 RFSO | 1 | ¦396921~ | Flange 316L 16" 150 RFSO | ea | ______________ | ______________ | ______________
40578 | 2026-04-02 | 2
39693 |  | PIPE 316L 1 SC40 WLD X | 0.5 | ¦396936~ | Pipe 316L 1" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40578 | 2026-04-02 | 1
39694 |  | PIPE 316L 2 SC40 WLD X | 0.5 | ¦39694;~ | Pipe 316L 2" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40578 | 2026-04-02 | 1
| Components | Job | Sch Start | Part | Rev | Total Est Hrs | Make Qty | Sch End
/
| Services | Vendor | Service | PO | Due Date |  | Operation Key | Description | Quantity
| Part: | T-118A |  |  |  | Rev:

## Tasks with Hours
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Description | Run Rate
Hours | Oper/Serv
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 4
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 6
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 2
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld
Hours | 1
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
Hours | 2
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
Hours | 1
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
Hours | 2
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
Hours | 2
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 10
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 5
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles TACK ONLY
Hours | 6
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc. INCL MAKE & POLISH VORTEX BREAKER
Hours | 4
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
Hours | 1
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
Hours | 2
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAM W/ COBOT
Hours | 2
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE
Hours | 2
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL (2) LIFT LUGS
Hours | 7
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS
Hours | 10
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
Hours | 3
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners GUSSETS FOR N3
Hours | 2
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .395 | Polish inside weld seams - top head
Hours | 6
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE
Hours | 1
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack INCL VORTEX BREAKER
Hours | 3
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete INCL VORTEX BREAKER
Hours | 3
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .495 | Polish inside weld seams - bottom head
Hours | 2
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
Hours | 5
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes ON BURN TABLE
Hours | 1
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .638 | Polish inside weld seams - shell INCL HOLE WATCH
Hours | 14
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD INSIDE (INCL HOLE WATCH)
Hours | 8
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 1
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .700 | Fit jacket to shell
Hours | 8
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .705 | Weld jacket to shell
Hours | 16
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .710 | Install jacket nozzles
Hours | 3
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .711 | Weld jacket nozzles
Hours | 3
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack
Hours | 12
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE
Hours | 8
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .735 | Install dip pipe supports
Hours | 3
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 1
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank FOR TANK AND JACKET
Hours | 20
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 8
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 1
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 2
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Location
Hours | Due Date
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Quantity | Name
Hours | Vendor
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | Build Head to Specifications
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | Plate 316L 3/16"x 72"x
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | Build Dipple Jacket to Specs
_

## Tasks - No Hours
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Description | Run Rate
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles TACK ONLY
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc. INCL MAKE & POLISH VORTEX BREAKER
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAM W/ COBOT
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL (2) LIFT LUGS
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .370 | Install and weld out repads - top head
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners GUSSETS FOR N3
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .395 | Polish inside weld seams - top head
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack INCL VORTEX BREAKER
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete INCL VORTEX BREAKER
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .495 | Polish inside weld seams - bottom head
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes ON BURN TABLE
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .638 | Polish inside weld seams - shell INCL HOLE WATCH
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD INSIDE (INCL HOLE WATCH)
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .700 | Fit jacket to shell
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .705 | Weld jacket to shell
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .710 | Install jacket nozzles
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .711 | Weld jacket nozzles
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .735 | Install dip pipe supports
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank FOR TANK AND JACKET
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Location
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Quantity | Name
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 111-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_