## Build Plan w Hours
Job #: | 023-26
| Description: | DEMO TANK |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean CUT PIPE FOR SHELL & N1; PREP FOR FULL PEN WELD | 3 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld N1 & N3 | 2 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 1 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .460 | Bevel bottom head PREP PIPE CAP FOR FULL PEN WELD | 1 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell | 1 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .645 | Weld all outside seams MAKE FULL PEN WELD TO JOIN PIPE CAP TO SHELL | 1 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt | 1 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack INCL PREP FOR FULL PEN WELD | 1 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC51 | UT Components | 0 |  |  |  | 1 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 1 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 023-26
| Description: | DEMO TANK |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean CUT PIPE FOR SHELL & N1; PREP FOR FULL PEN WELD | 3 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld N1 & N3 | 2 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 1 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .460 | Bevel bottom head PREP PIPE CAP FOR FULL PEN WELD | 1 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell | 1 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .645 | Weld all outside seams MAKE FULL PEN WELD TO JOIN PIPE CAP TO SHELL | 1 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt | 1 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack INCL PREP FOR FULL PEN WELD | 1 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC51 | UT Components | 0 |  |  |  | 1 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 1 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | DEMO TANK | Customer PO: | 8675309 | Quote: |  | DEMO TANK | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2026-03-05 | Make Qty: | 1 | / | ea | Est Hours: | 17
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 66180 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 66181 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 66182 | 0 | Cut Nozzle Pipe and Clean | 0 | 3 | FixedHrs | 3 | .100 | 0 | Cut nozzle pipe and clean CUT PIPE FOR SHELL & N1; PREP FOR FULL PEN WELD | _________________ | _________________ | _________________
PRE FAB | 66183 | 0 | Build Nozzles-Weld | 0 | 2 | FixedHrs | 2 | .105 | 0 | Build nozzles and weld N1 & N3 | _________________ | _________________ | _________________
PRE FAB | 66184 | 0 | Cut Parts on Burn Table | 0 | 1 | FixedHrs | 1 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 66185 | 0 | Build Supports | 0 | 1 | FixedHrs | 1 | .165 | 0 | Build supports: legs, lugs, saddles | _________________ | _________________ | _________________
INSPECTION | 66186 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 66187 | 0 | Bevel Bottom Head | 0 | 1 | FixedHrs | 1 | .460 | 0 | Bevel bottom head PREP PIPE CAP FOR FULL PEN WELD | _________________ | _________________ | _________________
INSPECTION | 66188 | 0 | ASME Hold Point | 0 | 0 | FixedHrs | 0 | .OI1 | 0 | ASME Hold Point | _________________ | _________________ | _________________
FIT | 66189 | 0 | Fit Bottom Head to Shell | 0 | 1 | FixedHrs | 1 | .600 | 0 | Fit bottom head to shell | _________________ | _________________ | _________________
FIT | 66190 | 0 | L/O Shell, B&C Holes | 0 | 1 | FixedHrs | 1 | .620 | 0 | Lay out shell, burn and clean holes | _________________ | _________________ | _________________
INSPECTION | 66191 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 66192 | 0 | Weld all Outside Seams | 0 | 1 | FixedHrs | 1 | .645 | 0 | Weld all outside seams MAKE FULL PEN WELD TO JOIN PIPE CAP TO SHELL | _________________ | _________________ | _________________
FIT | 66193 | 0 | Install Support Parts | 0 | 1 | FixedHrs | 1 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt | _________________ | _________________ | _________________
FIT | 66194 | 0 | Set Nozzles in Shell | 0 | 1 | FixedHrs | 1 | .725 | 0 | Set nozzles in shell - tack INCL PREP FOR FULL PEN WELD | _________________ | _________________ | _________________
FIT | 66195 | 0 | Weld Shell Nozz & M/Ws | 0 | 1 | FixedHrs | 1 | .726 | 0 | Weld shell nozzles, manways, etc. | _________________ | _________________ | _________________
INSPECTION | 66196 | 0 | UT Components | 0 | 0 | FixedHrs | 0 | .QC51 | 0 | UT Components | _________________ | _________________ | _________________
FINISHING | 66197 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 66198 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
FINISHING | 66199 | 0 | Test Tank | 0 | 1 | FixedHrs | 1 | .910 | 0 | Test tank | _________________ | _________________ | _________________
| Part: | DEMO TANK |  |  |  | Rev:

## Tasks with Hours
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean CUT PIPE FOR SHELL & N1; PREP FOR FULL PEN WELD
Hours | 3
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld N1 & N3
Hours | 2
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 1
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles
Hours | 1
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .460 | Bevel bottom head PREP PIPE CAP FOR FULL PEN WELD
Hours | 1
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell
Hours | 1
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes
Hours | 1
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams MAKE FULL PEN WELD TO JOIN PIPE CAP TO SHELL
Hours | 1
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt
Hours | 1
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack INCL PREP FOR FULL PEN WELD
Hours | 1
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
Hours | 1
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC51 | UT Components
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 1
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean CUT PIPE FOR SHELL & N1; PREP FOR FULL PEN WELD
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld N1 & N3
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .460 | Bevel bottom head PREP PIPE CAP FOR FULL PEN WELD
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams MAKE FULL PEN WELD TO JOIN PIPE CAP TO SHELL
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack INCL PREP FOR FULL PEN WELD
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC51 | UT Components
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 023-26 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_