## Build Plan w Hours
Job #: | 25-057 | Description: | BUFFER TANK #2 |  | Total Est Hours: | 476
Similar jobs used: | 25-059, 25-066, 25-067, 25-060, 25-064
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  |  | none | nan
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | none | nan
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 12 | 8.6 | high | group_total:34h
PRE FAB |  | .105 | Build Nozzles-Weld | 6 | 18 | high | group_total:34h
PRE FAB |  | .107 | Build Repads for Nozzles | 3 | 2.8 | high | group_total:34h
PRE FAB |  | .110 | Build Dip Tubes-Weld | 30 | 4.2 | high | group_total:34h
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 40 | 26.6 | high | group_total:33h
PRE FAB |  | .156 | Clean & Prep Parts | 20 | 6.2 | high | group_total:33h
Supports
PRE FAB |  | .175 | B&W Base Ring, Skirt | 8 | 9.2 | high | group_total:9h
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2 | 3 | high | group_total:10h
PRE FAB |  | .255 | Drill/Punch holes | 10 | 1.8 | high | group_total:10h
PRE FAB |  | .261 | Misc Fabrication | 2 | 5.5 | high | group_total:10h
Shells
PRE FAB |  | .300 | Wrap Top & Bottom Heads | 2 | 0.4 | high | group_total:22h
INSPECTION |  | .QC3 | UT Shells |  |  | none | nan
PRE FAB |  | .305 | BI, SQ, T&C Shells | 9 | 10.3 | high | group_total:22h
PRE FAB |  | .310 | Bevel Shell Plates | 12 | 2.3 | high | group_total:22h
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 18 | 9.5 | high | group_total:22h
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  |  | none | nan
PRE FAB |  | .355 | L/O Top, B&C Holes | 1 | 2.3 | high | group_total:9h
PRE FAB |  | .360 | Bevel Top Head | 1 | 0.2 | high | group_total:9h
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 1 | 2.3 | high | group_total:9h
PRE FAB |  | .366 | Weld Nozzles - Top Head | 6 | 4.4 | high | group_total:9h
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 1 | 2.4 | high | group_total:6h
PRE FAB |  | .460 | Bevel Bottom Head | 1 | 0.3 | high | group_total:6h
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1 | 1.3 | high | group_total:6h
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 2 | 2.5 | high | group_total:6h
Skirt
PRE FAB |  | .500 | Bld Skirt, Roll & Tack | 5 | 5.1 | high | group_total:22h
PRE FAB |  | .510 | Bld Skirt, F&T to Base | 5 | 4.8 | high | group_total:22h
FIT |  | .515 | Weld Skirt | 8 | 4.2 | high | group_total:22h
FIT |  | .530 | Bld Skirt, Fit Anchor/Gst | 3 | 4.1 | high | group_total:22h
FIT |  | .545 | Weld Skirt Nozzles, Etc. | 6 | 4 | high | group_total:22h
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point |  |  | none | nan
FIT |  | .600 | Fit Bottom Head to Shell | 4 | 23.7 | high | group_total:123h
FIT |  | .605 | Tack Shell Courses | 8 | 13.8 | high | group_total:123h
FIT |  | .610 | Weld Inside Round Seams | 18 | 16.3 | high | group_total:123h
FIT |  | .620 | L/O Shell, B&C Holes | 6 | 5.3 | high | group_total:123h
FIT |  | .630 | Install Internal Parts | 36 | 9.6 | high | group_total:123h
INSPECTION |  | .QC5 | QC Inspection - Internal |  |  | none | nan
FIT |  | .640 | Fit Top to Shell | 5 | 14.2 | high | group_total:123h
FIT |  | .641 | Weld top to shell | 12 | 7.2 | high | group_total:123h
FIT |  | .645 | Weld all Outside Seams | 20 | 33 | high | group_total:123h
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 3 | 3 | none | nan
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 48 | 24.5 | high | group_total:115h
FIT |  | .720 | Install Support Parts | 32 | 30.5 | high | group_total:115h
FIT |  | .725 | Set Nozzles in Shell | 8 | 15.2 | high | group_total:115h
FIT |  | .726 | Weld Shell Nozz & M/Ws | 30 | 30.3 | high | group_total:115h
FIT |  | .730 | Add Repads-Weld | 5 | 9.2 | high | group_total:115h
FINISHING |  | .765 | Install Name Tag | 1 | 1.9 | high | group_total:115h
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 3.3 | high | group_total:115h
INSPECTION |  | .QC6 | QC Inspection - Fab |  |  | none | nan
INSPECTION |  | .OI4 | Customer Inspection |  |  | none | nan
INSPECTION |  | .OI2 | ASME Inspection Internal |  |  | none | nan
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 2 | 3 | high | group_total:29h
FINISHING |  | .910 | Test Tank | 12 | 14.4 | high | group_total:29h
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | none | nan
INSPECTION |  | .OI3 | ASME Inspection Test |  |  | none | nan
MOVE TANK |  | .802 | Move to Paint Area | 2 | 0.8 | high | group_total:29h
INSPECTION |  | .QC9 | QC Inspection - Sandblast |  |  | none | nan
INSPECTION |  | .QC90 | QC Inspection - Paint |  |  | none | nan
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 3 | 4.8 | high | group_total:29h
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | none | nan
SHIPPING |  | .960 | Load on Truck | 5 | 6 | high | group_total:29h
|  |  | Total Predicted Hours |  | 416.3

## Build Plan - No Hours
Job #: | 25-057 | Description: | BUFFER TANK #2 |  | Total Est Hours: | 476
Similar jobs used: | 25-059, 25-066, 25-067, 25-060, 25-064
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 12
PRE FAB |  | .105 | Build Nozzles-Weld | 6
PRE FAB |  | .107 | Build Repads for Nozzles | 3
PRE FAB |  | .110 | Build Dip Tubes-Weld | 30
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 40
PRE FAB |  | .156 | Clean & Prep Parts | 20
Supports
PRE FAB |  | .175 | B&W Base Ring, Skirt | 8
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 2
PRE FAB |  | .255 | Drill/Punch holes | 10
PRE FAB |  | .261 | Misc Fabrication | 2
Shells
PRE FAB |  | .300 | Wrap Top & Bottom Heads | 2
INSPECTION |  | .QC3 | UT Shells
PRE FAB |  | .305 | BI, SQ, T&C Shells | 9
PRE FAB |  | .310 | Bevel Shell Plates | 12
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 18
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 1
PRE FAB |  | .360 | Bevel Top Head | 1
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 1
PRE FAB |  | .366 | Weld Nozzles - Top Head | 6
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 1
PRE FAB |  | .460 | Bevel Bottom Head | 1
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 2
Skirt
PRE FAB |  | .500 | Bld Skirt, Roll & Tack | 5
PRE FAB |  | .510 | Bld Skirt, F&T to Base | 5
FIT |  | .515 | Weld Skirt | 8
FIT |  | .530 | Bld Skirt, Fit Anchor/Gst | 3
FIT |  | .545 | Weld Skirt Nozzles, Etc. | 6
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point
FIT |  | .600 | Fit Bottom Head to Shell | 4
FIT |  | .605 | Tack Shell Courses | 8
FIT |  | .610 | Weld Inside Round Seams | 18
FIT |  | .620 | L/O Shell, B&C Holes | 6
FIT |  | .630 | Install Internal Parts | 36
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 5
FIT |  | .641 | Weld top to shell | 12
FIT |  | .645 | Weld all Outside Seams | 20
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 3
Install Nozzles and Externals
FIT |  | .715 | Install Insul/Vac Rings | 48
FIT |  | .720 | Install Support Parts | 32
FIT |  | .725 | Set Nozzles in Shell | 8
FIT |  | .726 | Weld Shell Nozz & M/Ws | 30
FIT |  | .730 | Add Repads-Weld | 5
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
INSPECTION |  | .OI4 | Customer Inspection
INSPECTION |  | .OI2 | ASME Inspection Internal
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 2
FINISHING |  | .910 | Test Tank | 12
INSPECTION |  | .QC7 | QC Inspection - Test
INSPECTION |  | .OI3 | ASME Inspection Test
MOVE TANK |  | .802 | Move to Paint Area | 2
INSPECTION |  | .QC9 | QC Inspection - Sandblast
INSPECTION |  | .QC90 | QC Inspection - Paint
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 3
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 5
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
25-059
25-066
25-067
25-060
25-064
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 0 | none | nan | nan
.QC1 | UT Top & Bottom Heads | 0 | none | nan | nan
.100 | Cut Nozzle Pipe and Clean | 8.6 | high | group_total:34h | model(NOZZLES)
.105 | Build Nozzles-Weld | 18 | high | group_total:34h | model(NOZZLES)
.107 | Build Repads for Nozzles | 2.8 | high | group_total:34h | model(NOZZLES)
.110 | Build Dip Tubes-Weld | 4.2 | high | group_total:34h | model(NOZZLES)
.155 | Cut Parts on Burn Table | 26.6 | high | group_total:33h | model(CUT_PREP)
.156 | Clean & Prep Parts | 6.2 | high | group_total:33h | model(CUT_PREP)
.175 | B&W Base Ring, Skirt | 9.2 | high | group_total:9h | model(SUPPORTS)
.200 | Bld Lift Lugs, Grd Lugs | 3 | high | group_total:10h | model(MISC_PARTS)
.255 | Drill/Punch holes | 1.8 | high | group_total:10h | model(MISC_PARTS)
.261 | Misc Fabrication | 5.5 | high | group_total:10h | model(MISC_PARTS)
.300 | Wrap Top & Bottom Heads | 0.4 | high | group_total:22h | model(SHELLS)
.QC3 | UT Shells | 0 | none | nan | nan
.305 | BI, SQ, T&C Shells | 10.3 | high | group_total:22h | model(SHELLS)
.310 | Bevel Shell Plates | 2.3 | high | group_total:22h | model(SHELLS)
.315 | Roll Shell, Tack-Weld I/S | 9.5 | high | group_total:22h | model(SHELLS)
.QC4 | QC Inspection -Top/Bot/Co | 0 | none | nan | nan
.355 | L/O Top, B&C Holes | 2.3 | high | group_total:9h | model(TOP_HEAD)
.360 | Bevel Top Head | 0.2 | high | group_total:9h | model(TOP_HEAD)
.365 | Set Nozzles & Lugs - Top | 2.3 | high | group_total:9h | model(TOP_HEAD)
.366 | Weld Nozzles - Top Head | 4.4 | high | group_total:9h | model(TOP_HEAD)
.QC4 | QC Inspection -Top/Bot/Co | 0 | none | nan | nan
.455 | L/O Bottom, B&C Holes | 2.4 | high | group_total:6h | model(BTM_HEAD)
.460 | Bevel Bottom Head | 0.3 | high | group_total:6h | model(BTM_HEAD)
.465 | Set Nozzles - Bottom Head | 1.3 | high | group_total:6h | model(BTM_HEAD)
.466 | Weld Nozzles - Bot. Head | 2.5 | high | group_total:6h | model(BTM_HEAD)
.500 | Bld Skirt, Roll & Tack | 5.1 | high | group_total:22h | model(SKIRT)
.510 | Bld Skirt, F&T to Base | 4.8 | high | group_total:22h | model(SKIRT)
.515 | Weld Skirt | 4.2 | high | group_total:22h | model(SKIRT)
.530 | Bld Skirt, Fit Anchor/Gst | 4.1 | high | group_total:22h | model(SKIRT)
.545 | Weld Skirt Nozzles, Etc. | 4 | high | group_total:22h | model(SKIRT)
.OI1 | ASME Hold Point | 0 | none | nan | nan
.600 | Fit Bottom Head to Shell | 23.7 | high | group_total:123h | model(FIT_ASSEMBLY)
.605 | Tack Shell Courses | 13.8 | high | group_total:123h | model(FIT_ASSEMBLY)
.610 | Weld Inside Round Seams | 16.3 | high | group_total:123h | model(FIT_ASSEMBLY)
.620 | L/O Shell, B&C Holes | 5.3 | high | group_total:123h | model(FIT_ASSEMBLY)
.630 | Install Internal Parts | 9.6 | high | group_total:123h | model(FIT_ASSEMBLY)
.QC5 | QC Inspection - Internal | 0 | none | nan | nan
.640 | Fit Top to Shell | 14.2 | high | group_total:123h | model(FIT_ASSEMBLY)
.641 | Weld top to shell | 7.2 | high | group_total:123h | model(FIT_ASSEMBLY)
.645 | Weld all Outside Seams | 33 | high | group_total:123h | model(FIT_ASSEMBLY)
.800 | Move Tank to Detail Rolls | 3 | none | nan | nan
.715 | Install Insul/Vac Rings | 24.5 | high | group_total:115h | model(DETAIL_EXT)
.720 | Install Support Parts | 30.5 | high | group_total:115h | model(DETAIL_EXT)
.725 | Set Nozzles in Shell | 15.2 | high | group_total:115h | model(DETAIL_EXT)
.726 | Weld Shell Nozz & M/Ws | 30.3 | high | group_total:115h | model(DETAIL_EXT)
.730 | Add Repads-Weld | 9.2 | high | group_total:115h | model(DETAIL_EXT)
.765 | Install Name Tag | 1.9 | high | group_total:115h | model(DETAIL_EXT)
.770 | Inspect Tank, Make Repair | 3.3 | high | group_total:115h | model(DETAIL_EXT)
.QC6 | QC Inspection - Fab | 0 | none | nan | nan
.OI4 | Customer Inspection | 0 | none | nan | nan
.OI2 | ASME Inspection Internal | 0 | none | nan | nan
.801 | Move to Shop Test Area | 3 | high | group_total:29h | model(TEST_CLEAN)
.910 | Test Tank | 14.4 | high | group_total:29h | model(TEST_CLEAN)
.QC7 | QC Inspection - Test | 0 | none | nan | nan
.OI3 | ASME Inspection Test | 0 | none | nan | nan
.802 | Move to Paint Area | 0.8 | high | group_total:29h | model(TEST_CLEAN)
.QC9 | QC Inspection - Sandblast | 0 | none | nan | nan
.QC90 | QC Inspection - Paint | 0 | none | nan | nan
.940 | Prepare Tank for Shipment | 4.8 | high | group_total:29h | model(TEST_CLEAN)
.QC95 | QC Inspection - Final & L | 0 | none | nan | nan
.960 | Load on Truck | 6 | high | group_total:29h | model(TEST_CLEAN)