## Build Plan w Hours
Job #: | 25-096 | Description: | T-3405 |  | Total Est Hours: | 97
Similar jobs used: | 25-097, 25-111, 23-060, 25-109, 25-113
Work Center |  | Op # | Task | Est Hours | Predicted Hours | Confidence | Range | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material |  |  | none | nan
INSPECTION |  | .QC1 | UT Top & Bottom Heads |  |  | none | nan
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 4 | 3.8 | high | group_total:12h
PRE FAB |  | .105 | Build Nozzles-Weld | 8 | 7.9 | high | group_total:12h
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 8 | 6.8 | high | group_total:8h
PRE FAB |  | .156 | Clean & Prep Parts | 4 | 1.6 | high | group_total:8h
Supports
PRE FAB |  | .165 | Build Supports | 10 | 3.5 | high | group_total:4h
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 1 | 4.1 | high | group_total:4h
Shells
PRE FAB |  | .300 | Wrap Top & Bottom Heads | 1 | 0.1 | high | group_total:7h
INSPECTION |  | .QC3 | UT Shells |  |  | none | nan
PRE FAB |  | .305 | BI, SQ, T&C Shells | 4 | 3.4 | high | group_total:7h
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 4 | 3.2 | high | group_total:7h
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co |  |  | none | nan
PRE FAB |  | .355 | L/O Top, B&C Holes | 3 | 1.5 | high | group_total:6h
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 3 | 1.5 | high | group_total:6h
PRE FAB |  | .366 | Weld Nozzles - Top Head | 6 | 3 | high | group_total:6h
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 1 | 0.7 | high | group_total:2h
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1 | 0.4 | high | group_total:2h
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 1 | 0.8 | high | group_total:2h
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point |  |  | none | nan
FIT |  | .600 | Fit Bottom Head to Shell | 4 | 6.8 | high | group_total:11h
INSPECTION |  | .QC5 | QC Inspection - Internal |  |  | none | nan
FIT |  | .640 | Fit Top to Shell | 4 | 4.1 | high | group_total:11h
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 1 | 1 | none | nan
Install Nozzles and Externals
FIT |  | .720 | Install Support Parts | 14 | 14.5 | high | group_total:17h
FINISHING |  | .765 | Install Name Tag | 1 | 0.9 | high | group_total:17h
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1 | 1.6 | high | group_total:17h
INSPECTION |  | .QC6 | QC Inspection - Fab |  |  | none | nan
INSPECTION |  | .OI2 | ASME Inspection Internal |  |  | none | nan
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 1 | 1.5 | high | group_total:27h
FINISHING |  | .910 | Test Tank | 5 | 7.2 | high | group_total:27h
INSPECTION |  | .QC7 | QC Inspection - Test |  |  | none | nan
INSPECTION |  | .OI3 | ASME Inspection Test |  |  | none | nan
FINISHING |  | .920 | Clean Tank Complete | 5 | 12.5 | high | group_total:27h
INSPECTION |  | .QC8 | QC Inspection - Clean |  |  | none | nan
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1 | 2.4 | high | group_total:27h
INSPECTION |  | .QC95 | QC Inspection - Final & L |  |  | none | nan
SHIPPING |  | .960 | Load on Truck | 1 | 3 | high | group_total:27h
|  |  | Total Predicted Hours |  | 97.8

## Build Plan - No Hours
Job #: | 25-096 | Description: | T-3405 |  | Total Est Hours: | 97
Similar jobs used: | 25-097, 25-111, 23-060, 25-109, 25-113
Work Center |  | Op # | Task | Est Hours | Notes | Completed By | Date
Receive & Inspect
PRE FAB |  | .010 | Receive Material
INSPECTION |  | .QC1 | UT Top & Bottom Heads
Nozzles and Manways
PRE FAB |  | .100 | Cut Nozzle Pipe and Clean | 4
PRE FAB |  | .105 | Build Nozzles-Weld | 8
Cut & Prep Parts
PRE FAB |  | .155 | Cut Parts on Burn Table | 8
PRE FAB |  | .156 | Clean & Prep Parts | 4
Supports
PRE FAB |  | .165 | Build Supports | 10
Misc. Parts
PRE FAB |  | .200 | Bld Lift Lugs, Grd Lugs | 1
Shells
PRE FAB |  | .300 | Wrap Top & Bottom Heads | 1
INSPECTION |  | .QC3 | UT Shells
PRE FAB |  | .305 | BI, SQ, T&C Shells | 4
PRE FAB |  | .315 | Roll Shell, Tack-Weld I/S | 4
Top Head
INSPECTION |  | .QC4 | QC Inspection -Top/Bot/Co
PRE FAB |  | .355 | L/O Top, B&C Holes | 3
PRE FAB |  | .365 | Set Nozzles & Lugs - Top | 3
PRE FAB |  | .366 | Weld Nozzles - Top Head | 6
Bottom Head
PRE FAB |  | .455 | L/O Bottom, B&C Holes | 1
PRE FAB |  | .465 | Set Nozzles - Bottom Head | 1
PRE FAB |  | .466 | Weld Nozzles - Bot. Head | 1
Build Main Tank and Install Internals
INSPECTION |  | .OI1 | ASME Hold Point
FIT |  | .600 | Fit Bottom Head to Shell | 4
INSPECTION |  | .QC5 | QC Inspection - Internal
FIT |  | .640 | Fit Top to Shell | 4
MOVE TANK |  | .800 | Move Tank to Detail Rolls | 1
Install Nozzles and Externals
FIT |  | .720 | Install Support Parts | 14
FINISHING |  | .765 | Install Name Tag | 1
Inspect and Repair
FIT |  | .770 | Inspect Tank, Make Repair | 1
INSPECTION |  | .QC6 | QC Inspection - Fab
INSPECTION |  | .OI2 | ASME Inspection Internal
Test and Clean
MOVE TANK |  | .801 | Move to Shop Test Area | 1
FINISHING |  | .910 | Test Tank | 5
INSPECTION |  | .QC7 | QC Inspection - Test
INSPECTION |  | .OI3 | ASME Inspection Test
FINISHING |  | .920 | Clean Tank Complete | 5
INSPECTION |  | .QC8 | QC Inspection - Clean
Ship
FINISHING |  | .940 | Prepare Tank for Shipment | 1
INSPECTION |  | .QC95 | QC Inspection - Final & L
SHIPPING |  | .960 | Load on Truck | 1
Total Predicted Hours

## Sibling Analysis
Sibling Job Analysis
Jobs used for predictions:
25-097
25-111
23-060
25-109
25-113
Per-Operation Source Detail
Op Code | Description | Predicted Hrs | Confidence | Range | Source Jobs
.010 | Receive Material | 0 | none | nan | nan
.QC1 | UT Top & Bottom Heads | 0 | none | nan | nan
.100 | Cut Nozzle Pipe and Clean | 3.8 | high | group_total:12h | model(NOZZLES)
.105 | Build Nozzles-Weld | 7.9 | high | group_total:12h | model(NOZZLES)
.155 | Cut Parts on Burn Table | 6.8 | high | group_total:8h | model(CUT_PREP)
.156 | Clean & Prep Parts | 1.6 | high | group_total:8h | model(CUT_PREP)
.165 | Build Supports | 3.5 | high | group_total:4h | model(SUPPORTS)
.200 | Bld Lift Lugs, Grd Lugs | 4.1 | high | group_total:4h | model(MISC_PARTS)
.300 | Wrap Top & Bottom Heads | 0.1 | high | group_total:7h | model(SHELLS)
.QC3 | UT Shells | 0 | none | nan | nan
.305 | BI, SQ, T&C Shells | 3.4 | high | group_total:7h | model(SHELLS)
.315 | Roll Shell, Tack-Weld I/S | 3.2 | high | group_total:7h | model(SHELLS)
.QC4 | QC Inspection -Top/Bot/Co | 0 | none | nan | nan
.355 | L/O Top, B&C Holes | 1.5 | high | group_total:6h | model(TOP_HEAD)
.365 | Set Nozzles & Lugs - Top | 1.5 | high | group_total:6h | model(TOP_HEAD)
.366 | Weld Nozzles - Top Head | 3 | high | group_total:6h | model(TOP_HEAD)
.QC4 | QC Inspection -Top/Bot/Co | 0 | none | nan | nan
.455 | L/O Bottom, B&C Holes | 0.7 | high | group_total:2h | model(BTM_HEAD)
.465 | Set Nozzles - Bottom Head | 0.4 | high | group_total:2h | model(BTM_HEAD)
.466 | Weld Nozzles - Bot. Head | 0.8 | high | group_total:2h | model(BTM_HEAD)
.OI1 | ASME Hold Point | 0 | none | nan | nan
.600 | Fit Bottom Head to Shell | 6.8 | high | group_total:11h | model(FIT_ASSEMBLY)
.QC5 | QC Inspection - Internal | 0 | none | nan | nan
.640 | Fit Top to Shell | 4.1 | high | group_total:11h | model(FIT_ASSEMBLY)
.800 | Move Tank to Detail Rolls | 1 | none | nan | nan
.720 | Install Support Parts | 14.5 | high | group_total:17h | model(DETAIL_EXT)
.765 | Install Name Tag | 0.9 | high | group_total:17h | model(DETAIL_EXT)
.770 | Inspect Tank, Make Repair | 1.6 | high | group_total:17h | model(DETAIL_EXT)
.QC6 | QC Inspection - Fab | 0 | none | nan | nan
.OI2 | ASME Inspection Internal | 0 | none | nan | nan
.801 | Move to Shop Test Area | 1.5 | high | group_total:27h | model(TEST_CLEAN)
.910 | Test Tank | 7.2 | high | group_total:27h | model(TEST_CLEAN)
.QC7 | QC Inspection - Test | 0 | none | nan | nan
.OI3 | ASME Inspection Test | 0 | none | nan | nan
.920 | Clean Tank Complete | 12.5 | high | group_total:27h | model(TEST_CLEAN)
.QC8 | QC Inspection - Clean | 0 | none | nan | nan
.940 | Prepare Tank for Shipment | 2.4 | high | group_total:27h | model(TEST_CLEAN)
.QC95 | QC Inspection - Final & L | 0 | none | nan | nan
.960 | Load on Truck | 3 | high | group_total:27h | model(TEST_CLEAN)