## Sheet1
Assembly # | Process | Hours Left | % Complete | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13
MF01000510-1 | Shell: Complete (X-ray complete) | 0 | 100 | bar: 2026-02-12
| Bottom: Complete (awaiting X-ray reshoot) (Vacuum Box Complete) | 0.5 | 95 | bar: 2026-02-12
| Shell to Bottom: In Staging (awaiting bottom X-ray 12th) | 0.5 | 95 | bar: 2026-02-12 to 2026-02-13
| Shell to Top: In Staging (awaiting Shell to Bottom) | 100 | 0 | bar: 2026-02-13 to 2026-02-14; 2026-02-16
| Top: Long seams still need to be welded (Vacuum Box not complete) | 60 | 0 | bar: 2026-02-16 to 2026-02-18
| Nozzles: Fabricated; in staging (awaiting shell to top) | 33 | 60 | bar: 2026-02-18 to 2026-02-19
| Wall Rings: In staging (awaiting shell to top) | 36 | 60 | bar: 2026-02-19 to 2026-02-20
| Shell Stiffeners: Fabricated; in staging (awaiting shell to top) | 33 | 60 | bar: 2026-02-20 to 2026-02-21
MF01000510-2 | Bottom: Complete (X-Ray Complete) (Vacuum Box Complete) | 0.5 | 95 | bar: 2026-02-12
| Shell to Bottom: in staging (awaiting x-ray of shel 12th) | 0.5 | 95 | bar: 2026-02-12
| Shell: weld complete (X-ray to be conducted on the 12th) | 0.5 | 95 | bar: 2026-02-12
| Top: Long seams still need to be welded (Vacuum Box not complete) | 60 | 0 | bar: 2026-02-21; 2026-02-23
| Shell to Top: In Staging (awaiting Shell to Bottom) | 130 | 0 | bar: 2026-02-23 to 2026-02-27
| Nozzles: Fabricated; in staging (awaiting shell to top) | 40 | 60 | bar: 2026-02-27 to 2026-02-28
| Shell Stiffeners: Fabricated; in staging (awaiting shell to top) | 40 | 60 | bar: 2026-03-02 to 2026-03-04
MF01000510-3 | Pieces cut need to be constructed (in progress) | 34 | 60 | bar: 2026-03-04 to 2026-03-06
MF01000510-4 | Pieces cut need to be constructed (in progress) | 30 | 60 | bar: 2026-03-06 to 2026-03-07
| Weld outside Seams | 90 | 0 | bar: 2026-03-06 to 2026-03-07; 2026-03-09
| Fit handrail and install clips | 60 | 0 | bar: 2026-03-09 to 2026-03-10
| Final QC checks and testing | 40 | 0 | bar: 2026-03-10
| Disassemble, prep and ship | 51.5 | 0 | bar: 2026-03-10 to 2026-03-12
840