## Schedule
Nudyne | time axis 2026-02-09 to 2026-12-28
PLANNED SHIPMENT WEEK OF
DESCRIPTION | JOB #
BUFFER TANK #9 | 064-25 | 2026-02-16 |  | 2026-05-18: Minor Detailing
Drawings Notes
Procurement Notes
Fabrication Notes
Cut nozzle pipe and clean INCL FOR INLET MANIFOLD | .100 | PRE FAB | 12
Build nozzles and weld | .105 | PRE FAB | 6
Build Repads for Nozzles, drill and tap holes | .107 | PRE FAB | 3
Build dip tubes and weld BUILD INLET MANIFOLD | .110 | PRE FAB | 30
Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | .155 | PRE FAB | 40
Build and weld base ring - skirt | .175 | PRE FAB | 8
Make lift lugs, ground lugs, etc. | .200 | PRE FAB | 2
Drill/punch holes BURN HOLES IN MANIFOLD PIPE & REDUCERS | .255 | PRE FAB | 10
Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE INLET MANIFOLD PIPE SUPPORTS | .261 | PRE FAB | 2
Wrap top and bottom heads | .300 | PRE FAB | 2
Shells: bring in plate, square, trim and clean | .305 | PRE FAB | 9
Bevel shell plates | .310 | PRE FAB | 12
Roll shells, tack and weld inside seams INCL WELD LONG SEAM W/COBOT | .315 | PRE FAB | 18
QC Inspection - Top/Bottom/Cones | .QC4 | INSPECTION | 0
Lay out top head, burn and clean holes | .355 | PRE FAB | 1
Bevel top head CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD | .360 | PRE FAB | 1
Set nozzles, lift lugs, etc. in top head - tack | .365 | PRE FAB | 1
Weld out top head nozzles, etc. INCL (2) LIFT LUGS W/REPADS | .366 | PRE FAB | 6
QC Inspection - Top/Bottom/Cones | .QC4 | INSPECTION | 0
Lay out bottom head, burn and clean holes | .455 | PRE FAB | 1
Bevel bottom head CLEAN UP NOZZLE HOLE & PREP FOR FULL PEN WELD | .460 | PRE FAB | 1
Set nozzles in bottom head - tack | .465 | PRE FAB | 1
Weld nozzles in bottom head; weld complete | .466 | PRE FAB | 2
Build skirt - fit and weld shells ROLL (1) SHELL; INCL WELD LONG SEAM W/COBOT | .500 | PRE FAB | 5
Build skirt; fit base ring to shell and weld FIT & TACK BASE RING TO SHELL | .510 | PRE FAB | 5
Weld skirt shell seams and base ring WELD BASE RING TO SKIRT SHELL INSIDE & OUTSIDE | .515 | FIT | 8
Build skirt - fit anchors / gussets FIT (8) GUSSETS; TACK ONLY | .530 | FIT | 3
Weld skirt anchors, gussets, nozzles, manways, etc. WELD (8) GUSSETS | .545 | FIT | 6
ASME Hold Point | .OI1 | INSPECTION | 0
Fit bottom head to shell | .600 | FIT | 4
Tack shell courses together | .605 | FIT | 8
Weld inside round seams | .610 | FIT | 18
Lay out shell, burn and clean holes PREP NOZZLE HOLES FOR FULL PEN WELDS | .620 | FIT | 6
Install internals - wear plates, rings, clips, etc. INSTALL INLET MANIFOLD & SUPPORTS | .630 | FIT | 36
QC Inspection - Internal | .QC5 | INSPECTION | 0
Fit top head to shell - tack | .640 | FIT | 5
Weld top head to shell - inside INCL HOLE WATCH | .641 | FIT | 12
Weld all outside seams | .645 | FIT | 20
Move tank to detail rolls | .800 | MOVE TANK | 3
Install insulation/vacuum rings - tack INCL WELD COMPLETE | .715 | FIT | 48
Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT TO BOTTOM HEAD AND WELD | .720 | FIT | 32
Set nozzles in shell - tack | .725 | FIT | 8
Weld shell nozzles, manways, etc. INCL HOLE WATCH & NOZZLE A | .726 | FIT | 30
Add repads and weld | .730 | FIT | 5
Install name tag | .765 | FINISHING | 1
Inspect tank, make repairs, get QC inspector | .770 | FIT | 1
QC Inspection - Fabrication | .QC6 | INSPECTION | 0
Customer Inspection | .OI4 | INSPECTION | 0
ASME Inspection Internal | .OI2 | INSPECTION | 0
Move to shop test area | .801 | MOVE TANK | 2
Test tank | .910 | FINISHING | 12
QC Inspection - Test | .QC7 | INSPECTION | 0
ASME Inspection Test | .OI3 | INSPECTION | 0
Move to paint area | .802 | MOVE TANK | 2
QC Inspection - Sandblast | .QC9 | INSPECTION | 0
QC Inspection - Paint | .QC90 | INSPECTION | 0
Prepare tank for shipment | .940 | FINISHING | 3
QC Inspection - Final & Loose Items | .QC95 | INSPECTION | 0
Load on truck | .960 | SHIPPING | 5
Yellow Areas = Drawing Process
Gray areas = Fabrication
Blue Areas = Inspection/Dissassembly
Orange areas = Shipping
2026-02-11