## Build Plan w Hours
Job #: | 089-25
| Description: | DISSOLVING TANK |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean | 10 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 14 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 12 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 6 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 4 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 6 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 5 |  |  |  | 0 | 0
PRE FAB |  | .145 | Install cladding on flange FOR MANWAY | 10 |  |  |  | 0 | 0
PRE FAB |  | .147 | Install cladding on blind/cover FOR MANWAY | 20 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 70 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 35 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 4 |  |  |  | 0 | 0
PRE FAB |  | .235 | Build top and bottom stiffeners INCL CUT NOTCHES IN BEAMS | 65 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts MAKE (2) STACK CONNECTIONS (N14 A & B) | 48 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE OVERFLOW ASSEMBLY | 48 |  |  |  | 0 | 0
INSPECTION |  | .QC2 | QC Inspection - Components prior to shipping to Subcontractor | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean PREP *8) SHELL SECTIONS FOR ROLLING | 24 |  |  |  | 0 | 0
PRE FAB |  | .310 | Bevel shell plates | 48 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL (8) SHELL SECTIONS | 40 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone BUILD TOP IN (2) SECTIONS | 40 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes ***DO NOT CUT COLLAR CONNECTIONS*** | 1 |  |  |  | 0 | 0
PRE FAB |  | .360 | Bevel top head | 30 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners INSTALL (4) STIFFENERS ON LOWER ROOF SECTION | 20 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone BUILD BOTTOM IN (2) SECTIONS | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .460 | Bevel bottom head | 30 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell FIT LOWER SHELL COURSE & WELD TO BOTTOM | 100 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together FIT UPPER SHELL COURSE TO LOWER SHELL COURSE | 80 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 50 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes BEVEL HOLES CUT ON BURN TABLE | 40 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. (3) WEAR PADS & (8) SHIPPING SUPPORTS | 60 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 80 |  |  |  | 0 | 0
FIT |  | .641 | Weld top head to shell - inside | 50 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 120 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack INSTALL (12) VERTICAL SHELL STIFFENERS | 60 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (14) GUSSETS | 28 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack FIT NOZZLES, MANWAY, AND MIXER MOUNTS | 56 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 120 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld | 40 |  |  |  | 0 | 0
FIT |  | .750 | Fit handrail - install and weld clips SEPARATE TANK IN (2) SECTIONS | 60 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI4 | Customer Inspection | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 20 |  |  |  | 0 | 0
FINISHING |  | .900 | Dye pen test | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 50 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 10 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 25 |  |  |  | 0 | 0
SHIPPING |  | .971 | Take parts to machine shop | 4 |  |  |  | 0 | 0
SHIPPING |  | .973 | Pick up parts from machine shop | 4 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 089-25
| Description: | DISSOLVING TANK |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean | 10 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 14 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 12 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 6 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 4 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 6 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 5 |  |  |  | 0 | 0
PRE FAB |  | .145 | Install cladding on flange FOR MANWAY | 10 |  |  |  | 0 | 0
PRE FAB |  | .147 | Install cladding on blind/cover FOR MANWAY | 20 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 70 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 35 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 4 |  |  |  | 0 | 0
PRE FAB |  | .235 | Build top and bottom stiffeners INCL CUT NOTCHES IN BEAMS | 65 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts MAKE (2) STACK CONNECTIONS (N14 A & B) | 48 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE OVERFLOW ASSEMBLY | 48 |  |  |  | 0 | 0
INSPECTION |  | .QC2 | QC Inspection - Components prior to shipping to Subcontractor | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean PREP *8) SHELL SECTIONS FOR ROLLING | 24 |  |  |  | 0 | 0
PRE FAB |  | .310 | Bevel shell plates | 48 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams ROLL (8) SHELL SECTIONS | 40 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone BUILD TOP IN (2) SECTIONS | 40 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes ***DO NOT CUT COLLAR CONNECTIONS*** | 1 |  |  |  | 0 | 0
PRE FAB |  | .360 | Bevel top head | 30 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners INSTALL (4) STIFFENERS ON LOWER ROOF SECTION | 20 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone BUILD BOTTOM IN (2) SECTIONS | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .460 | Bevel bottom head | 30 |  |  |  | 0 | 0
FIT |  | .600 | Fit bottom head to shell FIT LOWER SHELL COURSE & WELD TO BOTTOM | 100 |  |  |  | 0 | 0
FIT |  | .605 | Tack shell courses together FIT UPPER SHELL COURSE TO LOWER SHELL COURSE | 80 |  |  |  | 0 | 0
FIT |  | .610 | Weld inside round seams | 50 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes BEVEL HOLES CUT ON BURN TABLE | 40 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. (3) WEAR PADS & (8) SHIPPING SUPPORTS | 60 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 80 |  |  |  | 0 | 0
FIT |  | .641 | Weld top head to shell - inside | 50 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 120 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack INSTALL (12) VERTICAL SHELL STIFFENERS | 60 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (14) GUSSETS | 28 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack FIT NOZZLES, MANWAY, AND MIXER MOUNTS | 56 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. | 120 |  |  |  | 0 | 0
FIT |  | .730 | Add repads and weld | 40 |  |  |  | 0 | 0
FIT |  | .750 | Fit handrail - install and weld clips SEPARATE TANK IN (2) SECTIONS | 60 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI4 | Customer Inspection | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 20 |  |  |  | 0 | 0
FINISHING |  | .900 | Dye pen test | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 50 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 10 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 25 |  |  |  | 0 | 0
SHIPPING |  | .971 | Take parts to machine shop | 4 |  |  |  | 0 | 0
SHIPPING |  | .973 | Pick up parts from machine shop | 4 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | DISSOLVING TANK | Customer PO: | S30019941 | Quote: | DISSOLVING TANK | DISSOLVING TANK | Line: | 10 |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-08-25 | Make Qty: | 1 | / | ea | Est Hours: | 1700
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 55385 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 55386 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 55387 | 0 | Cut Nozzle Pipe and Clean | 0 | 10 | FixedHrs | 10 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 55388 | 0 | Build Nozzles-Weld | 0 | 14 | FixedHrs | 14 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________
PRE FAB | 55389 | 0 | Build Repads for Nozzles | 0 | 12 | FixedHrs | 12 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________
PRE FAB | 55390 | 0 | Make Manway Parts | 0 | 6 | FixedHrs | 6 | .115 | 0 | Make manway parts: cut clips, form handles, etc. | _________________ | _________________ | _________________
PRE FAB | 55391 | 0 | Brn MW Neck, Clean, Bevel | 0 | 2 | FixedHrs | 2 | .120 | 0 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | _________________ | _________________ | _________________
PRE FAB | 55392 | 0 | Roll Manway Neck | 0 | 4 | FixedHrs | 4 | .125 | 0 | Roll manway neck | _________________ | _________________ | _________________
PRE FAB | 55393 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 6 | FixedHrs | 6 | .130 | 0 | Set up and weld manway flange and neck seam | _________________ | _________________ | _________________
PRE FAB | 55394 | 0 | Bld Davit Arm Aby Cover | 0 | 5 | FixedHrs | 5 | .135 | 0 | Build davit arm assembly and cover | _________________ | _________________ | _________________
PRE FAB | 55395 | 0 | Install Cladding on Flng | 0 | 10 | FixedHrs | 10 | .145 | 0 | Install cladding on flange FOR MANWAY | _________________ | _________________ | _________________
PRE FAB | 55396 | 0 | Install Clad on Blind/Cov | 0 | 20 | FixedHrs | 20 | .147 | 0 | Install cladding on blind/cover FOR MANWAY | _________________ | _________________ | _________________
PRE FAB | 55397 | 0 | Cut Parts on Burn Table | 0 | 70 | FixedHrs | 70 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 55398 | 0 | Clean & Prep Parts | 0 | 35 | FixedHrs | 35 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 55399 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 4 | FixedHrs | 4 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 55400 | 0 | Bld T-B Stiffeners | 0 | 65 | FixedHrs | 65 | .235 | 0 | Build top and bottom stiffeners INCL CUT NOTCHES IN BEAMS | _________________ | _________________ | _________________
PRE FAB | 55401 | 0 | Fab Miscellaneous Parts | 0 | 48 | FixedHrs | 48 | .252 | 0 | Fabricate miscellaneous parts MAKE (2) STACK CONNECTIONS (N14 A & B) | _________________ | _________________ | _________________
PRE FAB | 55402 | 0 | Misc Fabrication | 0 | 48 | FixedHrs | 48 | .261 | 0 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE OVERFLOW ASSEMBLY | _________________ | _________________ | _________________
INSPECTION | 55403 | 0 | QC Inspection - Pre Sub C | 0 | 0 | FixedHrs | 0 | .QC2 | 0 | QC Inspection - Components prior to shipping to Subcontractor | _________________ | _________________ | _________________
INSPECTION | 55404 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 55405 | 0 | BI, SQ, T&C Shells | 0 | 24 | FixedHrs | 24 | .305 | 0 | Shells: bring in plate, square, trim and clean PREP *8) SHELL SECTIONS FOR ROLLING | _________________ | _________________ | _________________
PRE FAB | 55406 | 0 | Bevel Shell Plates | 0 | 48 | FixedHrs | 48 | .310 | 0 | Bevel shell plates | _________________ | _________________ | _________________
PRE FAB | 55407 | 0 | Roll Shell, Tack-Weld I/S | 0 | 40 | FixedHrs | 40 | .315 | 0 | Roll shells, tack and weld inside seams ROLL (8) SHELL SECTIONS | _________________ | _________________ | _________________
PRE FAB | 55408 | 0 | Build Top Head/Cone | 0 | 40 | FixedHrs | 40 | .350 | 0 | Build top head/cone BUILD TOP IN (2) SECTIONS | _________________ | _________________ | _________________
INSPECTION | 55409 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 55410 | 0 | L/O Top, B&C Holes | 0 | 1 | FixedHrs | 1 | .355 | 0 | Lay out top head, burn and clean holes ***DO NOT CUT COLLAR CONNECTIONS*** | _________________ | _________________ | _________________
PRE FAB | 55411 | 0 | Bevel Top Head | 0 | 30 | FixedHrs | 30 | .360 | 0 | Bevel top head | _________________ | _________________ | _________________
PRE FAB | 55412 | 0 | Install Top Stiffeners | 0 | 20 | FixedHrs | 20 | .375 | 0 | Install top stiffeners INSTALL (4) STIFFENERS ON LOWER ROOF SECTION | _________________ | _________________ | _________________
PRE FAB | 55413 | 0 | Build Bottom Head/Cone | 0 | 20 | FixedHrs | 20 | .450 | 0 | Build bottom head/cone BUILD BOTTOM IN (2) SECTIONS | _________________ | _________________ | _________________
INSPECTION | 55414 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 55415 | 0 | Bevel Bottom Head | 0 | 30 | FixedHrs | 30 | .460 | 0 | Bevel bottom head | _________________ | _________________ | _________________
FIT | 55416 | 0 | Fit Bottom Head to Shell | 0 | 100 | FixedHrs | 100 | .600 | 0 | Fit bottom head to shell FIT LOWER SHELL COURSE & WELD TO BOTTOM | _________________ | _________________ | _________________
FIT | 55417 | 0 | Tack Shell Courses | 0 | 80 | FixedHrs | 80 | .605 | 0 | Tack shell courses together FIT UPPER SHELL COURSE TO LOWER SHELL COURSE | _________________ | _________________ | _________________
FIT | 55418 | 0 | Weld Inside Round Seams | 0 | 50 | FixedHrs | 50 | .610 | 0 | Weld inside round seams | _________________ | _________________ | _________________
FIT | 55419 | 0 | L/O Shell, B&C Holes | 0 | 40 | FixedHrs | 40 | .620 | 0 | Lay out shell, burn and clean holes BEVEL HOLES CUT ON BURN TABLE | _________________ | _________________ | _________________
FIT | 55420 | 0 | Install Internal Parts | 0 | 60 | FixedHrs | 60 | .630 | 0 | Install internals - wear plates, rings, clips, etc. (3) WEAR PADS & (8) SHIPPING SUPPORTS | _________________ | _________________ | _________________
INSPECTION | 55421 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 55422 | 0 | Fit Top to Shell | 0 | 80 | FixedHrs | 80 | .640 | 0 | Fit top head to shell - tack | _________________ | _________________ | _________________
FIT | 55423 | 0 | Weld top to shell | 0 | 50 | FixedHrs | 50 | .641 | 0 | Weld top head to shell - inside | _________________ | _________________ | _________________
FIT | 55424 | 0 | Weld all Outside Seams | 0 | 120 | FixedHrs | 120 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________
FIT | 55425 | 0 | Install Insul/Vac Rings | 0 | 60 | FixedHrs | 60 | .715 | 0 | Install insulation/vacuum rings - tack INSTALL (12) VERTICAL SHELL STIFFENERS | _________________ | _________________ | _________________
FIT | 55426 | 0 | Install Support Parts | 0 | 28 | FixedHrs | 28 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (14) GUSSETS | _________________ | _________________ | _________________
FIT | 55427 | 0 | Set Nozzles in Shell | 0 | 56 | FixedHrs | 56 | .725 | 0 | Set nozzles in shell - tack FIT NOZZLES, MANWAY, AND MIXER MOUNTS | _________________ | _________________ | _________________
FIT | 55428 | 0 | Weld Shell Nozz & M/Ws | 0 | 120 | FixedHrs | 120 | .726 | 0 | Weld shell nozzles, manways, etc. | _________________ | _________________ | _________________
FIT | 55429 | 0 | Add Repads-Weld | 0 | 40 | FixedHrs | 40 | .730 | 0 | Add repads and weld | _________________ | _________________ | _________________
FIT | 55430 | 0 | Fit Handrail, I&W Clips | 0 | 60 | FixedHrs | 60 | .750 | 0 | Fit handrail - install and weld clips SEPARATE TANK IN (2) SECTIONS | _________________ | _________________ | _________________
FINISHING | 55431 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 55432 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 55433 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
INSPECTION | 55434 | 0 | Customer Inspection | 0 | 0 | FixedHrs | 0 | .OI4 | 0 | Customer Inspection | _________________ | _________________ | _________________
MOVE TANK | 55435 | 0 | Move to Shop Test Area | 0 | 20 | FixedHrs | 20 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 55436 | 0 | Dye Pen Test | 0 | 20 | FixedHrs | 20 | .900 | 0 | Dye pen test | _________________ | _________________ | _________________
INSPECTION | 55437 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
FINISHING | 55438 | 0 | Clean Tank Complete | 0 | 50 | FixedHrs | 50 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 55439 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
MOVE TANK | 55440 | 0 | Move to Paint Area | 0 | 4 | FixedHrs | 4 | .802 | 0 | Move to paint area | _________________ | _________________ | _________________
INSPECTION | 55441 | 0 | QC Inspection - Sandblast | 0 | 0 | FixedHrs | 0 | .QC9 | 0 | QC Inspection - Sandblast | _________________ | _________________ | _________________
INSPECTION | 55442 | 0 | QC Inspection - Paint | 0 | 0 | FixedHrs | 0 | .QC90 | 0 | QC Inspection - Paint | _________________ | _________________ | _________________
FINISHING | 55443 | 0 | Prepare Tank for Shipment | 0 | 10 | FixedHrs | 10 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
FINISHING | 55444 | 0 | Check BOM, Pack Parts | 0 | 5 | FixedHrs | 5 | .950 | 0 | Check bill of materials and pack loose parts | _________________ | _________________ | _________________
INSPECTION | 55445 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 55446 | 0 | Load on Truck | 0 | 25 | FixedHrs | 25 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
SHIPPING | 55447 | 0 | Take Parts - Machine Shop | 0 | 4 | FixedHrs | 4 | .971 | 0 | Take parts to machine shop | _________________ | _________________ | _________________
SHIPPING | 55448 | 0 | P/U Parts - Machine Shop | 0 | 4 | FixedHrs | 4 | .973 | 0 | Pick up parts from machine shop | _________________ | _________________ | _________________
| Part: | DISSOLVING TANK |  |  |  | Rev:

## Tasks with Hours
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 10
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 14
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 12
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
Hours | 6
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
Hours | 2
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
Hours | 4
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
Hours | 6
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
Hours | 5
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .145 | Install cladding on flange FOR MANWAY
Hours | 10
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .147 | Install cladding on blind/cover FOR MANWAY
Hours | 20
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 70
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
Hours | 35
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 4
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .235 | Build top and bottom stiffeners INCL CUT NOTCHES IN BEAMS
Hours | 65
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts MAKE (2) STACK CONNECTIONS (N14 A & B)
Hours | 48
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE OVERFLOW ASSEMBLY
Hours | 48
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC2 | QC Inspection - Components prior to shipping to Subcontractor
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean PREP *8) SHELL SECTIONS FOR ROLLING
Hours | 24
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .310 | Bevel shell plates
Hours | 48
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL (8) SHELL SECTIONS
Hours | 40
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone BUILD TOP IN (2) SECTIONS
Hours | 40
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes ***DO NOT CUT COLLAR CONNECTIONS***
Hours | 1
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .360 | Bevel top head
Hours | 30
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners INSTALL (4) STIFFENERS ON LOWER ROOF SECTION
Hours | 20
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone BUILD BOTTOM IN (2) SECTIONS
Hours | 20
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .460 | Bevel bottom head
Hours | 30
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell FIT LOWER SHELL COURSE & WELD TO BOTTOM
Hours | 100
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together FIT UPPER SHELL COURSE TO LOWER SHELL COURSE
Hours | 80
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
Hours | 50
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes BEVEL HOLES CUT ON BURN TABLE
Hours | 40
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. (3) WEAR PADS & (8) SHIPPING SUPPORTS
Hours | 60
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
Hours | 80
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .641 | Weld top head to shell - inside
Hours | 50
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 120
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack INSTALL (12) VERTICAL SHELL STIFFENERS
Hours | 60
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (14) GUSSETS
Hours | 28
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack FIT NOZZLES, MANWAY, AND MIXER MOUNTS
Hours | 56
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
Hours | 120
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld
Hours | 40
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .750 | Fit handrail - install and weld clips SEPARATE TANK IN (2) SECTIONS
Hours | 60
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI4 | Customer Inspection
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 20
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .900 | Dye pen test
Hours | 20
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 50
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
Hours | 4
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 10
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
Hours | 5
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 25
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .971 | Take parts to machine shop
Hours | 4
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .973 | Pick up parts from machine shop
Hours | 4
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .145 | Install cladding on flange FOR MANWAY
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .147 | Install cladding on blind/cover FOR MANWAY
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .235 | Build top and bottom stiffeners INCL CUT NOTCHES IN BEAMS
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts MAKE (2) STACK CONNECTIONS (N14 A & B)
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks MAKE OVERFLOW ASSEMBLY
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC2 | QC Inspection - Components prior to shipping to Subcontractor
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean PREP *8) SHELL SECTIONS FOR ROLLING
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .310 | Bevel shell plates
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams ROLL (8) SHELL SECTIONS
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone BUILD TOP IN (2) SECTIONS
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes ***DO NOT CUT COLLAR CONNECTIONS***
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .360 | Bevel top head
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners INSTALL (4) STIFFENERS ON LOWER ROOF SECTION
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone BUILD BOTTOM IN (2) SECTIONS
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .460 | Bevel bottom head
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell FIT LOWER SHELL COURSE & WELD TO BOTTOM
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .605 | Tack shell courses together FIT UPPER SHELL COURSE TO LOWER SHELL COURSE
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .610 | Weld inside round seams
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes BEVEL HOLES CUT ON BURN TABLE
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. (3) WEAR PADS & (8) SHIPPING SUPPORTS
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .641 | Weld top head to shell - inside
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack INSTALL (12) VERTICAL SHELL STIFFENERS
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT & WELD (14) GUSSETS
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack FIT NOZZLES, MANWAY, AND MIXER MOUNTS
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc.
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .730 | Add repads and weld
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .750 | Fit handrail - install and weld clips SEPARATE TANK IN (2) SECTIONS
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI4 | Customer Inspection
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .900 | Dye pen test
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .971 | Take parts to machine shop
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .973 | Pick up parts from machine shop
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 089-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_