## Build Plan w Hours
Job #: | 091-25
| Description: | API MANWAY |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 2 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 1 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 1 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 3 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 2 |  |  |  | 0 | 0
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .900 | Dye pen test DYE PEN ALL WELDS | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 091-25
| Description: | API MANWAY |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 2 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | 1 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 1 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 3 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 2 |  |  |  | 0 | 0
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .900 | Dye pen test DYE PEN ALL WELDS | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
FINISHING |  | .920 | Clean tank complete | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | API MANWAY | Customer PO: | PTW00-0000219484 | Quote: |  | API MANWAY | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-09-04 | Make Qty: | 1 | / | ea | Est Hours: | 14
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 54458 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 54459 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 54460 | 0 | Build Repads for Nozzles | 0 | 2 | FixedHrs | 2 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________
PRE FAB | 54461 | 0 | Make Manway Parts | 0 | 1 | FixedHrs | 1 | .115 | 0 | Make manway parts: cut clips, form handles, etc. | _________________ | _________________ | _________________
PRE FAB | 54462 | 0 | Brn MW Neck, Clean, Bevel | 0 | 1 | FixedHrs | 1 | .120 | 0 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel | _________________ | _________________ | _________________
PRE FAB | 54463 | 0 | Roll Manway Neck | 0 | 1 | FixedHrs | 1 | .125 | 0 | Roll manway neck | _________________ | _________________ | _________________
PRE FAB | 54464 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 3 | FixedHrs | 3 | .130 | 0 | Set up and weld manway flange and neck seam | _________________ | _________________ | _________________
PRE FAB | 54465 | 0 | Cut Parts on Burn Table | 0 | 2 | FixedHrs | 2 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
MOVE TANK | 54466 | 0 | Move to Shop Test Area | 0 | 1 | FixedHrs | 1 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 54467 | 0 | Dye Pen Test | 0 | 1 | FixedHrs | 1 | .900 | 0 | Dye pen test DYE PEN ALL WELDS | _________________ | _________________ | _________________
INSPECTION | 54470 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
FINISHING | 54468 | 0 | Clean Tank Complete | 0 | 2 | FixedHrs | 2 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 54469 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
| Part: | API MANWAY |  |  |  | Rev:

## Tasks with Hours
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 2
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
Hours | 1
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
Hours | 1
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
Hours | 1
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
Hours | 3
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 2
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 1
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .900 | Dye pen test DYE PEN ALL WELDS
Hours | 1
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 2
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .120 | Burn manway neck (CHECK BEFORE BURNING) - Clean and Bevel
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .900 | Dye pen test DYE PEN ALL WELDS
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 091-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_