## Build Plan w Hours
Job #: | 098-25
| Description: | MIST ELIMINATOR W/FACE WASH |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean FOR N3, N6 & N7 | 2 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld FOR N3, N6 & N7 | 3 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 8 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 4 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles FORM (2) SUPPORTS | 1 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts FORM (2) INTERNAL ANGLES | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
FIT |  | .320 | Set up and weld sides - rectangular tank SET UP AND BUILD HOUSING | 6 |  |  |  | 0 | 0
FIT |  | .325 | Install body flange on shell - tack FIT HOUSING ACCESS FLANGE | 1 |  |  |  | 0 | 0
FIT |  | .326 | Weld Body Flange on Shell WELD HOUSING ACCESS FLANGE | 3 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone FORM & WELD INLET TRANSITION | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack FOR N1 FLANGE + N4, N6 & N7 | 4 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. FOR N1 FLANGE + N4, N6 & N7 | 8 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners INLET TRANSITION STIFFENER | 2 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone FORM & WELD OUTLET TRANSITION | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack FOR N2 FLANGE + N5 | 2 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete FOR N2 FLANGE + N5 | 6 |  |  |  | 0 | 0
PRE FAB |  | .475 | Install bottom stiffeners OUTLET TRANSITION STIFFENER | 2 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell FIT 1ST TRANSITION TO HOUSING AND WELD COMPLETE | 3 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. HOUSING GUID PLATES & INTERNAL FORMED ANGLES | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack FIT 2ND TRANSITION TO HOUSING AND WELD COMPLETE | 3 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack FIT & WELD HOUSING STIFFENERS | 5 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell ON HOUSING COVER | 1 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack AND WELD COMPLETE (N3) | 2 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI4 | Customer Inspection | 0 |  |  |  | 1 | 1
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 1 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 098-25
| Description: | MIST ELIMINATOR W/FACE WASH |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean FOR N3, N6 & N7 | 2 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld FOR N3, N6 & N7 | 3 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 8 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 4 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles FORM (2) SUPPORTS | 1 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts FORM (2) INTERNAL ANGLES | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
FIT |  | .320 | Set up and weld sides - rectangular tank SET UP AND BUILD HOUSING | 6 |  |  |  | 0 | 0
FIT |  | .325 | Install body flange on shell - tack FIT HOUSING ACCESS FLANGE | 1 |  |  |  | 0 | 0
FIT |  | .326 | Weld Body Flange on Shell WELD HOUSING ACCESS FLANGE | 3 |  |  |  | 0 | 0
PRE FAB |  | .350 | Build top head/cone FORM & WELD INLET TRANSITION | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack FOR N1 FLANGE + N4, N6 & N7 | 4 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. FOR N1 FLANGE + N4, N6 & N7 | 8 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners INLET TRANSITION STIFFENER | 2 |  |  |  | 0 | 0
PRE FAB |  | .450 | Build bottom head/cone FORM & WELD OUTLET TRANSITION | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack FOR N2 FLANGE + N5 | 2 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete FOR N2 FLANGE + N5 | 6 |  |  |  | 0 | 0
PRE FAB |  | .475 | Install bottom stiffeners OUTLET TRANSITION STIFFENER | 2 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell FIT 1ST TRANSITION TO HOUSING AND WELD COMPLETE | 3 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. HOUSING GUID PLATES & INTERNAL FORMED ANGLES | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack FIT 2ND TRANSITION TO HOUSING AND WELD COMPLETE | 3 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack FIT & WELD HOUSING STIFFENERS | 5 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell ON HOUSING COVER | 1 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack AND WELD COMPLETE (N3) | 2 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI4 | Customer Inspection | 0 |  |  |  | 1 | 1
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 1 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | MIST ELIMINATOR W/FACE WASH | Customer PO: | 91687 | Quote: | 9356 | MIST ELIMINATOR W/FACE WASH | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-09-24 | Make Qty: | 1 | / | ea | Est Hours: | 108
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 65942 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 65943 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 65944 | 0 | Cut Nozzle Pipe and Clean | 0 | 2 | FixedHrs | 2 | .100 | 0 | Cut nozzle pipe and clean FOR N3, N6 & N7 | _________________ | _________________ | _________________
PRE FAB | 65945 | 0 | Build Nozzles-Weld | 0 | 3 | FixedHrs | 3 | .105 | 0 | Build nozzles and weld FOR N3, N6 & N7 | _________________ | _________________ | _________________
PRE FAB | 65946 | 0 | Cut Parts on Burn Table | 0 | 8 | FixedHrs | 8 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 65947 | 0 | Clean & Prep Parts | 0 | 4 | FixedHrs | 4 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 65948 | 0 | Build Supports | 0 | 1 | FixedHrs | 1 | .165 | 0 | Build supports: legs, lugs, saddles FORM (2) SUPPORTS | _________________ | _________________ | _________________
PRE FAB | 65949 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 65950 | 0 | Fab Miscellaneous Parts | 0 | 1 | FixedHrs | 1 | .252 | 0 | Fabricate miscellaneous parts FORM (2) INTERNAL ANGLES | _________________ | _________________ | _________________
INSPECTION | 65951 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
FIT | 65952 | 0 | S/U and Build Sides | 0 | 6 | FixedHrs | 6 | .320 | 0 | Set up and weld sides - rectangular tank SET UP AND BUILD HOUSING | _________________ | _________________ | _________________
FIT | 65953 | 0 | Install Body Flg-Shell | 0 | 1 | FixedHrs | 1 | .325 | 0 | Install body flange on shell - tack FIT HOUSING ACCESS FLANGE | _________________ | _________________ | _________________
FIT | 65954 | 0 | Weld Body Flg Shell | 0 | 3 | FixedHrs | 3 | .326 | 0 | Weld Body Flange on Shell WELD HOUSING ACCESS FLANGE | _________________ | _________________ | _________________
PRE FAB | 65955 | 0 | Build Top Head/Cone | 0 | 8 | FixedHrs | 8 | .350 | 0 | Build top head/cone FORM & WELD INLET TRANSITION | _________________ | _________________ | _________________
INSPECTION | 65956 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 65957 | 0 | L/O Top, B&C Holes | 0 | 1 | FixedHrs | 1 | .355 | 0 | Lay out top head, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________
PRE FAB | 65958 | 0 | Set Nozzles & Lugs - Top | 0 | 4 | FixedHrs | 4 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack FOR N1 FLANGE + N4, N6 & N7 | _________________ | _________________ | _________________
PRE FAB | 65959 | 0 | Weld Nozzles - Top Head | 0 | 8 | FixedHrs | 8 | .366 | 0 | Weld out top head nozzles, etc. FOR N1 FLANGE + N4, N6 & N7 | _________________ | _________________ | _________________
PRE FAB | 65960 | 0 | Install Top Stiffeners | 0 | 2 | FixedHrs | 2 | .375 | 0 | Install top stiffeners INLET TRANSITION STIFFENER | _________________ | _________________ | _________________
PRE FAB | 65961 | 0 | Build Bottom Head/Cone | 0 | 8 | FixedHrs | 8 | .450 | 0 | Build bottom head/cone FORM & WELD OUTLET TRANSITION | _________________ | _________________ | _________________
INSPECTION | 65962 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 65963 | 0 | L/O Bottom, B&C Holes | 0 | 1 | FixedHrs | 1 | .455 | 0 | Lay out bottom head, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________
PRE FAB | 65964 | 0 | Set Nozzles - Bottom Head | 0 | 2 | FixedHrs | 2 | .465 | 0 | Set nozzles in bottom head - tack FOR N2 FLANGE + N5 | _________________ | _________________ | _________________
PRE FAB | 65965 | 0 | Weld Nozzles - Bot. Head | 0 | 6 | FixedHrs | 6 | .466 | 0 | Weld nozzles in bottom head; weld complete FOR N2 FLANGE + N5 | _________________ | _________________ | _________________
PRE FAB | 65966 | 0 | Install Bottom Stiffeners | 0 | 2 | FixedHrs | 2 | .475 | 0 | Install bottom stiffeners OUTLET TRANSITION STIFFENER | _________________ | _________________ | _________________
INSPECTION | 65967 | 0 | ASME Hold Point | 0 | 0 | FixedHrs | 0 | .OI1 | 0 | ASME Hold Point | _________________ | _________________ | _________________
FIT | 65968 | 0 | Fit Bottom Head to Shell | 0 | 3 | FixedHrs | 3 | .600 | 0 | Fit bottom head to shell FIT 1ST TRANSITION TO HOUSING AND WELD COMPLETE | _________________ | _________________ | _________________
FIT | 65969 | 0 | Install Internal Parts | 0 | 3 | FixedHrs | 3 | .630 | 0 | Install internals - wear plates, rings, clips, etc. HOUSING GUID PLATES & INTERNAL FORMED ANGLES | _________________ | _________________ | _________________
INSPECTION | 65970 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 65971 | 0 | Fit Top to Shell | 0 | 3 | FixedHrs | 3 | .640 | 0 | Fit top head to shell - tack FIT 2ND TRANSITION TO HOUSING AND WELD COMPLETE | _________________ | _________________ | _________________
FIT | 65972 | 0 | Install Insul/Vac Rings | 0 | 5 | FixedHrs | 5 | .715 | 0 | Install insulation/vacuum rings - tack FIT & WELD HOUSING STIFFENERS | _________________ | _________________ | _________________
FIT | 65973 | 0 | Install Lift Lugs on Shl | 0 | 1 | FixedHrs | 1 | .717 | 0 | Install lift lugs on shell ON HOUSING COVER | _________________ | _________________ | _________________
FIT | 65974 | 0 | Set Nozzles in Shell | 0 | 2 | FixedHrs | 2 | .725 | 0 | Set nozzles in shell - tack AND WELD COMPLETE (N3) | _________________ | _________________ | _________________
FINISHING | 65975 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 65976 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 65977 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
INSPECTION | 65978 | 0 | Customer Inspection | 0 | 0 | FixedHrs | 0 | .OI4 | 0 | Customer Inspection | _________________ | _________________ | _________________
INSPECTION | 65979 | 0 | ASME Inspection Internal | 0 | 0 | FixedHrs | 0 | .OI2 | 0 | ASME Inspection Internal | _________________ | _________________ | _________________
MOVE TANK | 65980 | 0 | Move to Shop Test Area | 0 | 1 | FixedHrs | 1 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 65981 | 0 | Test Tank | 0 | 3 | FixedHrs | 3 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 65982 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
INSPECTION | 65983 | 0 | ASME Inspection Test | 0 | 0 | FixedHrs | 0 | .OI3 | 0 | ASME Inspection Test | _________________ | _________________ | _________________
FINISHING | 65984 | 0 | Clean Tank Complete | 0 | 10 | FixedHrs | 10 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________
INSPECTION | 65985 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
FINISHING | 65986 | 0 | Prepare Tank for Shipment | 0 | 1 | FixedHrs | 1 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
INSPECTION | 65987 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 65988 | 0 | Load on Truck | 0 | 1 | FixedHrs | 1 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
| Part: | MIST ELIMINATOR W/FACE WASH |  |  |  | Rev:

## Tasks with Hours
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean FOR N3, N6 & N7
Hours | 2
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld FOR N3, N6 & N7
Hours | 3
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 8
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
Hours | 4
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles FORM (2) SUPPORTS
Hours | 1
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts FORM (2) INTERNAL ANGLES
Hours | 1
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .320 | Set up and weld sides - rectangular tank SET UP AND BUILD HOUSING
Hours | 6
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .325 | Install body flange on shell - tack FIT HOUSING ACCESS FLANGE
Hours | 1
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .326 | Weld Body Flange on Shell WELD HOUSING ACCESS FLANGE
Hours | 3
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone FORM & WELD INLET TRANSITION
Hours | 8
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes ON BURN TABLE
Hours | 1
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack FOR N1 FLANGE + N4, N6 & N7
Hours | 4
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. FOR N1 FLANGE + N4, N6 & N7
Hours | 8
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners INLET TRANSITION STIFFENER
Hours | 2
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone FORM & WELD OUTLET TRANSITION
Hours | 8
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes ON BURN TABLE
Hours | 1
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack FOR N2 FLANGE + N5
Hours | 2
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete FOR N2 FLANGE + N5
Hours | 6
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .475 | Install bottom stiffeners OUTLET TRANSITION STIFFENER
Hours | 2
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell FIT 1ST TRANSITION TO HOUSING AND WELD COMPLETE
Hours | 3
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. HOUSING GUID PLATES & INTERNAL FORMED ANGLES
Hours | 3
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack FIT 2ND TRANSITION TO HOUSING AND WELD COMPLETE
Hours | 3
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack FIT & WELD HOUSING STIFFENERS
Hours | 5
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell ON HOUSING COVER
Hours | 1
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack AND WELD COMPLETE (N3)
Hours | 2
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI4 | Customer Inspection
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 1
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 3
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 10
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 1
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 1
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean FOR N3, N6 & N7
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld FOR N3, N6 & N7
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles FORM (2) SUPPORTS
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts FORM (2) INTERNAL ANGLES
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .320 | Set up and weld sides - rectangular tank SET UP AND BUILD HOUSING
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .325 | Install body flange on shell - tack FIT HOUSING ACCESS FLANGE
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .326 | Weld Body Flange on Shell WELD HOUSING ACCESS FLANGE
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .350 | Build top head/cone FORM & WELD INLET TRANSITION
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes ON BURN TABLE
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack FOR N1 FLANGE + N4, N6 & N7
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. FOR N1 FLANGE + N4, N6 & N7
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners INLET TRANSITION STIFFENER
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .450 | Build bottom head/cone FORM & WELD OUTLET TRANSITION
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes ON BURN TABLE
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack FOR N2 FLANGE + N5
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete FOR N2 FLANGE + N5
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .475 | Install bottom stiffeners OUTLET TRANSITION STIFFENER
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell FIT 1ST TRANSITION TO HOUSING AND WELD COMPLETE
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. HOUSING GUID PLATES & INTERNAL FORMED ANGLES
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack FIT 2ND TRANSITION TO HOUSING AND WELD COMPLETE
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack FIT & WELD HOUSING STIFFENERS
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell ON HOUSING COVER
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack AND WELD COMPLETE (N3)
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI4 | Customer Inspection
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 098-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_