## Build Plan w Hours
Job #: | 113-25
| Description: | ¦25-113Z~ |  |  | Delivery Date:
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Description | Run Rate | Oper/Serv |  |  |  | 0 | 0
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 5 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 8 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld | 2 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 1 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 2 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 2 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 10 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 5 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles | 6 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean MAKE (1) DOUBLE SHELL | 4 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAMS W/ COBOT | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL (2) LIFT LUGS | 6 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | 8 |  |  |  | 0 | 0
PRE FAB |  | .395 | Polish inside weld seams - top head | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete | 2 |  |  |  | 0 | 0
PRE FAB |  | .495 | Polish inside weld seams - bottom head | 1 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 5 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
FIT |  | .638 | Polish inside weld seams - shell INCL HOLE WATCH | 24 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD INSIDE (INCL HOLE WATCH) | 8 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack | 12 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | 8 |  |  |  | 0 | 0
FIT |  | .735 | Install dip pipe supports INCL HOLE WATCH | 4 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 2 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Location |  | Due Date |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Quantity | Name | Vendor |  |  |  | 0 | 0
35637 |  | ______________ | 0 | Build Head to Specifications |  |  |  | 0 | 0
40273 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35681 |  | ______________ | 0 | Plate 316L 1/4"x 60"x |  |  |  | 0 | 0
SA240-316/316L |  | 0 | 0 | 0 |  |  |  | 0 | 0
40282 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39765 |  | ______________ | 0 | SA193-B7 (ZINC PLATED) |  |  |  | 0 | 0
40628 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39766 |  | ______________ | 0 | SA194-2H (ZINC PLATED) |  |  |  | 0 | 0
40628 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39771 |  | ______________ | 0 | Gasket Ring 1/8"x24" 150# |  |  |  | 0 | 0
40634 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39772 |  | ______________ | 0 |  |  |  |  | 0 | 0
40634 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39773 |  | ______________ | 0 | Plate 316L 3/8"x 48"x |  |  |  | 0 | 0
SA240-316/316L |  | 0 | 0 | 0 |  |  |  | 0 | 0
40635 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39774 |  | ______________ | 0 | Plate 304L 1/4"x 60"x |  |  |  | 0 | 0
SA240-304/304L |  | 0 | 0 | 0 |  |  |  | 0 | 0
40635 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39775 |  | ______________ | 0 | Angle 304L 1/2" x 6" x 6" x 20' |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 113-25
| Description: | ¦25-113Z~ |  |  | Delivery Date:
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Description | Run Rate | Oper/Serv |  |  |  | 0 | 0
PRE FAB |  | .010 | Receive Material | 0 |  |  |  | 0 | 0
INSPECTION |  | .QC1 | UT top and bottom heads | 0 |  |  |  | 1 | 0
PRE FAB |  | .100 | Cut nozzle pipe and clean | 5 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld | 8 |  |  |  | 0 | 0
PRE FAB |  | .107 | Build Repads for Nozzles, drill and tap holes | 1 |  |  |  | 0 | 0
PRE FAB |  | .110 | Build dip tubes and weld | 2 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .125 | Roll manway neck | 1 |  |  |  | 0 | 0
PRE FAB |  | .130 | Set up and weld manway flange and neck seam | 2 |  |  |  | 0 | 0
PRE FAB |  | .135 | Build davit arm assembly and cover | 2 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 10 |  |  |  | 0 | 0
PRE FAB |  | .156 |  | 5 |  |  |  | 0 | 0
PRE FAB |  | .165 | Build supports: legs, lugs, saddles | 6 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 2 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean MAKE (1) DOUBLE SHELL | 4 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAMS W/ COBOT | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE | 2 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL (2) LIFT LUGS | 6 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | 8 |  |  |  | 0 | 0
PRE FAB |  | .395 | Polish inside weld seams - top head | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .455 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE | 1 |  |  |  | 0 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete | 2 |  |  |  | 0 | 0
PRE FAB |  | .495 | Polish inside weld seams - bottom head | 1 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 5 |  |  |  | 0 | 0
FIT |  | .620 | Lay out shell, burn and clean holes ON BURN TABLE | 1 |  |  |  | 0 | 0
FIT |  | .638 | Polish inside weld seams - shell INCL HOLE WATCH | 24 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack AND WELD INSIDE (INCL HOLE WATCH) | 8 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack | 12 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | 8 |  |  |  | 0 | 0
FIT |  | .735 | Install dip pipe supports INCL HOLE WATCH | 4 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 10 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete | 8 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 2 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Location |  | Due Date |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
|  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | Quantity | Name | Vendor |  |  |  | 0 | 0
35637 |  | ______________ | 0 | Build Head to Specifications |  |  |  | 0 | 0
40273 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
35681 |  | ______________ | 0 | Plate 316L 1/4"x 60"x |  |  |  | 0 | 0
SA240-316/316L |  | 0 | 0 | 0 |  |  |  | 0 | 0
40282 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39765 |  | ______________ | 0 | SA193-B7 (ZINC PLATED) |  |  |  | 0 | 0
40628 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39766 |  | ______________ | 0 | SA194-2H (ZINC PLATED) |  |  |  | 0 | 0
40628 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39771 |  | ______________ | 0 | Gasket Ring 1/8"x24" 150# |  |  |  | 0 | 0
40634 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39772 |  | ______________ | 0 |  |  |  |  | 0 | 0
40634 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39773 |  | ______________ | 0 | Plate 316L 3/8"x 48"x |  |  |  | 0 | 0
SA240-316/316L |  | 0 | 0 | 0 |  |  |  | 0 | 0
40635 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39774 |  | ______________ | 0 | Plate 304L 1/4"x 60"x |  |  |  | 0 | 0
SA240-304/304L |  | 0 | 0 | 0 |  |  |  | 0 | 0
40635 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
39775 |  | ______________ | 0 | Angle 304L 1/2" x 6" x 6" x 20' |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
¦25-113Z~
Part: | T-120 | Customer PO: | 967245922 | Quote: | 9315.4 | T-120 | Line: |  |  |  | Rev: |  | Drawing: |  |  | Order Qty: | 1 | / | ea | Order Date: | 2025-10-31 | Make Qty: | 1 | / | ea | Est Hours: | 166
Customer | Ship To | EPIC SYSTEMS GROUP. LLC - P&M 4142 MERAMEC BOTTOM ROAD ST. LOUIS, MO 63129 US | UBIQD, INC. 19 INDUSTRIAL PARK ROAD ATTN: MIKE KRAJCIK SANTA FE,NM 87506 United States
Contact | Ship Via |  | Best Way | Phone | Fax | 314-845-0077 |  | 314-845-6166
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 66396 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________ | ¦663969~ | PRE FAB
INSPECTION | 66397 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________ | ¦66397>~ | INSPECTION
PRE FAB | 66398 | 0 | Cut Nozzle Pipe and Clean | 0 | 5 | FixedHrs | 5 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________ | ¦66398C~ | PRE FAB
PRE FAB | 66399 | 0 | Build Nozzles-Weld | 0 | 8 | FixedHrs | 8 | .105 | 0 | Build nozzles and weld | _________________ | _________________ | _________________ | ¦66399H~ | PRE FAB
PRE FAB | 66400 | 0 | Build Repads for Nozzles | 0 | 1 | FixedHrs | 1 | .107 | 0 | Build Repads for Nozzles, drill and tap holes | _________________ | _________________ | _________________ | ¦66400a~ | PRE FAB
PRE FAB | 66401 | 0 | Build Dip Tubes-Weld | 0 | 2 | FixedHrs | 2 | .110 | 0 | Build dip tubes and weld | _________________ | _________________ | _________________ | ¦66401f~ | PRE FAB
PRE FAB | 66402 | 0 | Make Manway Parts | 0 | 2 | FixedHrs | 2 | .115 | 0 | Make manway parts: cut clips, form handles, etc. | _________________ | _________________ | _________________ | ¦66402k~ | PRE FAB
PRE FAB | 66403 | 0 | Roll Manway Neck | 0 | 1 | FixedHrs | 1 | .125 | 0 | Roll manway neck | _________________ | _________________ | _________________ | ¦66403p~ | PRE FAB
PRE FAB | 66404 | 0 | S/U Weld MW Flg, Neck Sem | 0 | 2 | FixedHrs | 2 | .130 | 0 | Set up and weld manway flange and neck seam | _________________ | _________________ | _________________ | ¦66404u~ | PRE FAB
PRE FAB | 66405 | 0 | Bld Davit Arm Aby Cover | 0 | 2 | FixedHrs | 2 | .135 | 0 | Build davit arm assembly and cover | _________________ | _________________ | _________________ | ¦66405z~ | PRE FAB
PRE FAB | 66406 | 0 | Cut Parts on Burn Table | 0 | 10 | FixedHrs | 10 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________ | ¦66406¥~ | PRE FAB
PRE FAB | 66407 | 0 | Clean & Prep Parts | 0 | 5 | FixedHrs | 5 | .156 | 0 |  | _________________ | _________________ | _________________ | ¦66407ª~ | PRE FAB
PRE FAB | 66408 | 0 | Build Supports | 0 | 6 | FixedHrs | 6 | .165 | 0 | Build supports: legs, lugs, saddles | _________________ | _________________ | _________________ | ¦66408"~ | PRE FAB
PRE FAB | 66409 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 2 | FixedHrs | 2 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________ | ¦66409'~ | PRE FAB
PRE FAB | 66410 | 0 | Wrap Top & Bottom Heads | 0 | 1 | FixedHrs | 1 | .300 | 0 | Wrap top and bottom heads | _________________ | _________________ | _________________ | ¦66410e~ | PRE FAB
INSPECTION | 66411 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________ | ¦66411j~ | INSPECTION
PRE FAB | 66412 | 0 | BI, SQ, T&C Shells | 0 | 4 | FixedHrs | 4 | .305 | 0 | Shells: bring in plate, square, trim and clean MAKE (1) DOUBLE SHELL | _________________ | _________________ | _________________ | ¦66412o~ | PRE FAB
PRE FAB | 66413 | 0 | Roll Shell, Tack-Weld I/S | 0 | 4 | FixedHrs | 4 | .315 | 0 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAMS W/ COBOT | _________________ | _________________ | _________________ | ¦66413t~ | PRE FAB
INSPECTION | 66414 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________ | ¦66414y~ | INSPECTION
PRE FAB | 66415 | 0 | L/O Top, B&C Holes | 0 | 2 | FixedHrs | 2 | .355 | 0 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE | _________________ | _________________ | _________________ | ¦66415¤~ | PRE FAB
PRE FAB | 66416 | 0 | Set Nozzles & Lugs - Top | 0 | 6 | FixedHrs | 6 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack INCL (2) LIFT LUGS | _________________ | _________________ | _________________ | ¦66416©~ | PRE FAB
PRE FAB | 66417 | 0 | Weld Nozzles - Top Head | 0 | 8 | FixedHrs | 8 | .366 | 0 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | _________________ | _________________ | _________________ | ¦66417!~ | PRE FAB
PRE FAB | 66418 | 0 | Polish I/S Weld Seam-Top | 0 | 3 | FixedHrs | 3 | .395 | 0 | Polish inside weld seams - top head | _________________ | _________________ | _________________ | ¦66418&~ | PRE FAB
INSPECTION | 66419 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________ | ¦66419+~ | INSPECTION
PRE FAB | 66420 | 0 | L/O Bottom, B&C Holes | 0 | 1 | FixedHrs | 1 | .455 | 0 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE | _________________ | _________________ | _________________ | ¦66420i~ | PRE FAB
PRE FAB | 66421 | 0 | Set Nozzles - Bottom Head | 0 | 1 | FixedHrs | 1 | .465 | 0 | Set nozzles in bottom head - tack | _________________ | _________________ | _________________ | ¦66421n~ | PRE FAB
PRE FAB | 66422 | 0 | Weld Nozzles - Bot. Head | 0 | 2 | FixedHrs | 2 | .466 | 0 | Weld nozzles in bottom head; weld complete | _________________ | _________________ | _________________ | ¦66422s~ | PRE FAB
PRE FAB | 66446 | 0 | Polish I/S Weld Seam-Btm | 0 | 1 | FixedHrs | 1 | .495 | 0 | Polish inside weld seams - bottom head | _________________ | _________________ | _________________ | ¦66446(~ | PRE FAB
INSPECTION | 66423 | 0 | ASME Hold Point | 0 | 0 | FixedHrs | 0 | .OI1 | 0 | ASME Hold Point | _________________ | _________________ | _________________ | ¦66423x~ | INSPECTION
FIT | 66424 | 0 | Fit Bottom Head to Shell | 0 | 5 | FixedHrs | 5 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE | _________________ | _________________ | _________________ | ¦66424£~ | FIT
FIT | 66425 | 0 | L/O Shell, B&C Holes | 0 | 1 | FixedHrs | 1 | .620 | 0 | Lay out shell, burn and clean holes ON BURN TABLE | _________________ | _________________ | _________________ | ¦66425¨~ | FIT
FIT | 66426 | 0 | Polish I/S Weld Seam-Shl | 0 | 24 | FixedHrs | 24 | .638 | 0 | Polish inside weld seams - shell INCL HOLE WATCH | _________________ | _________________ | _________________ | ¦66426®~ | FIT
INSPECTION | 66427 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________ | ¦66427%~ | INSPECTION
FIT | 66428 | 0 | Fit Top to Shell | 0 | 8 | FixedHrs | 8 | .640 | 0 | Fit top head to shell - tack AND WELD INSIDE (INCL HOLE WATCH) | _________________ | _________________ | _________________ | ¦66428*~ | FIT
MOVE TANK | 66429 | 0 | Move Tank to Detail Rolls | 0 | 1 | FixedHrs | 1 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________ | ¦66429/~ | MOVE TANK
FIT | 66430 | 0 | Install Insul/Vac Rings | 0 | 12 | FixedHrs | 12 | .715 | 0 | Install insulation/vacuum rings - tack | _________________ | _________________ | _________________ | ¦66430m~ | FIT
FIT | 66431 | 0 | Install Support Parts | 0 | 8 | FixedHrs | 8 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE | _________________ | _________________ | _________________ | ¦66431r~ | FIT
FIT | 66432 | 0 | Install Dip Pipe Supports | 0 | 4 | FixedHrs | 4 | .735 | 0 | Install dip pipe supports INCL HOLE WATCH | _________________ | _________________ | _________________ | ¦66432w~ | FIT
FINISHING | 66433 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________ | ¦66433¢~ | FINISHING
FIT | 66434 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________ | ¦66434§~ | FIT
INSPECTION | 66435 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________ | ¦66435¬~ | INSPECTION
INSPECTION | 66436 | 0 | ASME Inspection Internal | 0 | 0 | FixedHrs | 0 | .OI2 | 0 | ASME Inspection Internal | _________________ | _________________ | _________________ | ¦66436$~ | INSPECTION
MOVE TANK | 66437 | 0 | Move to Shop Test Area | 0 | 1 | FixedHrs | 1 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________ | ¦66437)~ | MOVE TANK
FINISHING | 66438 | 0 | Test Tank | 0 | 10 | FixedHrs | 10 | .910 | 0 | Test tank | _________________ | _________________ | _________________ | ¦66438.~ | FINISHING
INSPECTION | 66439 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________ | ¦664393~ | INSPECTION
INSPECTION | 66440 | 0 | ASME Inspection Test | 0 | 0 | FixedHrs | 0 | .OI3 | 0 | ASME Inspection Test | _________________ | _________________ | _________________ | ¦66440q~ | INSPECTION
FINISHING | 66441 | 0 | Clean Tank Complete | 0 | 8 | FixedHrs | 8 | .920 | 0 | Clean tank complete | _________________ | _________________ | _________________ | ¦66441v~ | FINISHING
INSPECTION | 66442 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________ | ¦66442¡~ | INSPECTION
FINISHING | 66443 | 0 | Prepare Tank for Shipment | 0 | 1 | FixedHrs | 1 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________ | ¦66443¦~ | FINISHING
INSPECTION | 66444 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________ | ¦66444«~ | INSPECTION
SHIPPING | 66445 | 0 | Load on Truck | 0 | 2 | FixedHrs | 2 | .960 | 0 | Load on truck | _________________ | _________________ | _________________ | ¦66445#~ | SHIPPING
Materials
| Picks | Comments | Material | Primary | Due Date | Requirement Key | Description | Location | Quantity
Detail Number:
| Buys | Comments | Material Description | Requirement Key | Vendor | PO | Due Date | Quantity | Qty | Name | Date
35637 |  | HEAD | 2 | ¦35637*~ | Build Head to Specifications | ea | ______________ | ______________ | ______________
40273 | 2026-01-27 | 1
35681 |  | PLT 316L 1/4 X 60 X | 2 | ¦35681®~ | Plate 316L 1/4"x 60"x | ea | ______________ | ______________ | ______________
SA240-316/316L
40282 | 2025-12-29 | 2
39765 |  | FULL THREDED STUD 1 1/4" - 7NC X 7" | 20 | ¦397657~ | SA193-B7 (ZINC PLATED) | ea | ______________ | ______________ | ______________
40628 | 2026-04-09 | 20
39766 |  | NUT, 1 1/4" - 7NC HH | 40 | ¦39766<~ | SA194-2H (ZINC PLATED) | ea | ______________ | ______________ | ______________
40628 | 2026-04-09 | 40
39771 |  | GASKET RING 1/8X24 150# | 1 | ¦39771'~ | Gasket Ring 1/8"x24" 150# | ea | ______________ | ______________ | ______________
40634 | 2026-04-02 | 1
39772 |  | 'FREIGHT | 1 | ¦39772,~ |  | ea | ______________ | ______________ | ______________
40634 | 2026-04-02 | 1
39773 |  | PLT 316L 3/8 X 48 X | 1 | ¦397731~ | Plate 316L 3/8"x 48"x | ea | ______________ | ______________ | ______________
SA240-316/316L
40635 | 2026-04-08 | 1
39774 |  | PLT 304L 1/4 X 60 X | 1 | ¦397746~ | Plate 304L 1/4"x 60"x | ea | ______________ | ______________ | ______________
SA240-304/304L
40635 | 2026-04-08 | 1
39775 |  | AG 304L 1/2 X 6 X 6 X 20' | 2 | ¦39775;~ | Angle 304L 1/2" x 6" x 6" x 20' | ea | ______________ | ______________ | ______________
40635 | 2026-04-08 | 2
39790 |  | PIPE 316L 4 SC80 WLD X | 1 | ¦39790*~ | Pipe 316L 4" Sch80 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40645 | 2026-04-27 | 1
39791 |  | FLANGE 316L 24"150 BLIND | 1 | ¦39791/~ | Flange 316L 24" 150# BLIND | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40645 | 2026-04-27 | 1
39792 |  | FLANGE 316L 3/4"150 RFSO | 1 | ¦397924~ | Flange 316L 3/4" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40645 | 2026-04-27 | 1
39793 |  | FLANGE 316L 3"150 RFSO | 1 | ¦397939~ | Flange 316L 3" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40645 | 2026-04-27 | 1
39794 |  | FLANGE 316L 1"150 RFSO | 2 | ¦39794>~ | Flange 316L 1" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40645 | 2026-04-27 | 2
39795 |  | FLANGE 316L 2"150 RFSO | 6 | ¦39795C~ | Flange 316L 2" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40645 | 2026-04-27 | 6
39796 |  | FLANGE 316L 4"150 RFSO | 1 | ¦39796H~ | Flange 316L 4" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40645 | 2026-04-27 | 1
39797 |  | FLANGE 316L 24"150 RFSO | 1 | ¦39797M~ | Flange 316L 24" 150# RFSO | ea | ______________ | ______________ | ______________
SA182F-316/316L B16.5
40645 | 2026-04-27 | 1
39798 |  | PIPE 316L 3/4 SC40 WLD X | 1 | ¦39798R~ | Pipe 316L 3/4" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40645 | 2026-04-27 | 1
39799 |  | PIPE 316L 3 SC40 WLD X | 1 | ¦39799W~ | Pipe 316L 3" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40645 | 2026-04-27 | 1
39800 |  | PIPE 316L 1 SC40 WLD X | 2 | ¦39800p~ | Pipe 316L 1" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40645 | 2026-04-27 | 2
39801 |  | PIPE 316L 2 SC40 WLD X | 6 | ¦39801u~ | Pipe 316L 2" Sch40 Welded | ea | ______________ | ______________ | ______________
SA312-316/316L
40645 | 2026-04-27 | 1
40645 | 2026-04-27 | 4
| Components | Job | Sch Start | Part | Rev | Total Est Hrs | Make Qty | Sch End
/
| Services | Vendor | Service | PO | Due Date |  | Operation Key | Description | Quantity
| Part: | T-120 |  |  |  | Rev:

## Tasks with Hours
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Description | Run Rate
Hours | Oper/Serv
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 5
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
Hours | 8
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
Hours | 1
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld
Hours | 2
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
Hours | 2
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
Hours | 1
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
Hours | 2
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
Hours | 2
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 10
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
Hours | 5
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles
Hours | 6
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 2
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
Hours | 1
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean MAKE (1) DOUBLE SHELL
Hours | 4
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAMS W/ COBOT
Hours | 4
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE
Hours | 2
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL (2) LIFT LUGS
Hours | 6
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS
Hours | 8
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .395 | Polish inside weld seams - top head
Hours | 3
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE
Hours | 1
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
Hours | 1
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete
Hours | 2
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .495 | Polish inside weld seams - bottom head
Hours | 1
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
Hours | 5
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes ON BURN TABLE
Hours | 1
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .638 | Polish inside weld seams - shell INCL HOLE WATCH
Hours | 24
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD INSIDE (INCL HOLE WATCH)
Hours | 8
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 1
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack
Hours | 12
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE
Hours | 8
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .735 | Install dip pipe supports INCL HOLE WATCH
Hours | 4
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 1
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 10
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
Hours | 8
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 1
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 2
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Location
Hours | Due Date
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Quantity | Name
Hours | Vendor
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | Build Head to Specifications
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | Plate 316L 1/4"x 60"x
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | SA193-B7 (ZINC PLATED)
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | SA194-2H (ZINC PLATED)
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
Hours | Gasket Ring 1/8"x24" 150#
_

## Tasks - No Hours
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Description | Run Rate
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .010 | Receive Material
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC1 | UT top and bottom heads
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .107 | Build Repads for Nozzles, drill and tap holes
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .110 | Build dip tubes and weld
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc.
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .125 | Roll manway neck
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .130 | Set up and weld manway flange and neck seam
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .135 | Build davit arm assembly and cover
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .165 | Build supports: legs, lugs, saddles
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean MAKE (1) DOUBLE SHELL
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams WELD OUTSIDE SEAMS W/ COBOT
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes CUT HOLES ON BURN TABLE
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack INCL (2) LIFT LUGS
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .395 | Polish inside weld seams - top head
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .455 | Lay out bottom head, burn and clean holes CUT HOLES ON BURN TABLE
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .495 | Polish inside weld seams - bottom head
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .620 | Lay out shell, burn and clean holes ON BURN TABLE
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .638 | Polish inside weld seams - shell INCL HOLE WATCH
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack AND WELD INSIDE (INCL HOLE WATCH)
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt AND WELD COMPLETE
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .735 | Install dip pipe supports INCL HOLE WATCH
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Location
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | Quantity | Name
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | ______________ | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 113-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_