## Build Plan w Hours
Job #: | 118-25
| Description: | MH-5301-HP-05000-CASING |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean | 4 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld FOR RFSO NOZZLES ONLY | 8 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. FOR L1, L2, M & N | 4 |  |  |  | 0 | 0
PRE FAB |  | .140 | Build hatch/door FOR L1, L2, M & N | 20 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 50 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 30 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 5 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes CHECK ALL BOLT HOLES CUT ON CNC TABLE; REAM AS REQD | 20 |  |  |  | 0 | 0
PRE FAB |  | .257 | Build Flanges FOR K1, K2, L, M, N, O, P1 & P2 | 20 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks BUIILD LEFT & RIGHT BOTTOM BRACKET ASSEMBLIES | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean LAYOUT & PREP (4) SHELL SECTIONS | 15 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams FORM (4) SHELL SECTIONS | 15 |  |  |  | 0 | 0
FIT |  | .320 | Set up and weld sides - rectangular tank FIT, TACK & WELD SHELL & CASING PLATES | 60 |  |  |  | 0 | 0
FIT |  | .325 | Install body flange on shell - tack MOUNT END FLANGE ON SHELL & WELD | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes BEVEL/PREP HOLES CUT ON CNC TABLE | 10 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 6 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 15 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners FIT & WELD (11) STIFFENERS + (4) CHANNEL STIFFENERS | 45 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack FOR NOZZLES 0 (BOTTOM) & P1, P2 (COVER) | 5 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete FOR NOZZLES O (BOTTOM) & P1, P2 (COVER) | 15 |  |  |  | 0 | 0
PRE FAB |  | .470 | Install and weld out repads - bottom head (8) BOTTOM SUPPORT PADS | 12 |  |  |  | 0 | 0
PRE FAB |  | .475 | Install bottom stiffeners FIT & WELD (12) BOTTOM SHELL STIFFENERS | 36 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. FIT & WELD (4) INTERNAL ANGLES ON BOTTOM | 16 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 6 |  |  |  | 0 | 0
FIT |  | .641 | Weld top head to shell - inside WELD TOP PLATE INSIDE & OUTSIDE | 20 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 4 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack INSTALL HORIZONTAL & VERTICAL SHELL STIFFENERS & WELD | 120 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell INCL L & R TOP SUPPORT BRACKETS | 6 |  |  |  | 0 | 0
FIT |  | .721 | Weld insulation / vacuum rings, lugs, supports, etc. FIT & WELD LEFT & RIGHT MOUNTING BRACKET ASSEMBLIES | 30 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack FOR NOZZLES I, J, L, & M | 5 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. FOR NOZZLES I, J, L & M (INCL HOLE WATCH) | 25 |  |  |  | 0 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 15 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 2 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 3 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 118-25
| Description: | MH-5301-HP-05000-CASING |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean | 4 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld FOR RFSO NOZZLES ONLY | 8 |  |  |  | 0 | 0
PRE FAB |  | .115 | Make manway parts: cut clips, form handles, etc. FOR L1, L2, M & N | 4 |  |  |  | 0 | 0
PRE FAB |  | .140 | Build hatch/door FOR L1, L2, M & N | 20 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 50 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 30 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 5 |  |  |  | 0 | 0
PRE FAB |  | .255 | Drill/punch holes CHECK ALL BOLT HOLES CUT ON CNC TABLE; REAM AS REQD | 20 |  |  |  | 0 | 0
PRE FAB |  | .257 | Build Flanges FOR K1, K2, L, M, N, O, P1 & P2 | 20 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks BUIILD LEFT & RIGHT BOTTOM BRACKET ASSEMBLIES | 20 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean LAYOUT & PREP (4) SHELL SECTIONS | 15 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams FORM (4) SHELL SECTIONS | 15 |  |  |  | 0 | 0
FIT |  | .320 | Set up and weld sides - rectangular tank FIT, TACK & WELD SHELL & CASING PLATES | 60 |  |  |  | 0 | 0
FIT |  | .325 | Install body flange on shell - tack MOUNT END FLANGE ON SHELL & WELD | 6 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .355 | Lay out top head, burn and clean holes BEVEL/PREP HOLES CUT ON CNC TABLE | 10 |  |  |  | 0 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 6 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. | 15 |  |  |  | 0 | 0
PRE FAB |  | .375 | Install top stiffeners FIT & WELD (11) STIFFENERS + (4) CHANNEL STIFFENERS | 45 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack FOR NOZZLES 0 (BOTTOM) & P1, P2 (COVER) | 5 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete FOR NOZZLES O (BOTTOM) & P1, P2 (COVER) | 15 |  |  |  | 0 | 0
PRE FAB |  | .470 | Install and weld out repads - bottom head (8) BOTTOM SUPPORT PADS | 12 |  |  |  | 0 | 0
PRE FAB |  | .475 | Install bottom stiffeners FIT & WELD (12) BOTTOM SHELL STIFFENERS | 36 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. FIT & WELD (4) INTERNAL ANGLES ON BOTTOM | 16 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 6 |  |  |  | 0 | 0
FIT |  | .641 | Weld top head to shell - inside WELD TOP PLATE INSIDE & OUTSIDE | 20 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 4 |  |  |  | 0 | 0
FIT |  | .715 | Install insulation/vacuum rings - tack INSTALL HORIZONTAL & VERTICAL SHELL STIFFENERS & WELD | 120 |  |  |  | 0 | 0
FIT |  | .717 | Install lift lugs on shell INCL L & R TOP SUPPORT BRACKETS | 6 |  |  |  | 0 | 0
FIT |  | .721 | Weld insulation / vacuum rings, lugs, supports, etc. FIT & WELD LEFT & RIGHT MOUNTING BRACKET ASSEMBLIES | 30 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack FOR NOZZLES I, J, L, & M | 5 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. FOR NOZZLES I, J, L & M (INCL HOLE WATCH) | 25 |  |  |  | 0 | 0
MOVE TANK |  | .801 | Move to shop test area | 2 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 15 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
MOVE TANK |  | .802 | Move to paint area | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC9 | QC Inspection - Sandblast | 0 |  |  |  | 1 | 0
INSPECTION |  | .QC90 | QC Inspection - Paint | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 2 |  |  |  | 0 | 0
FINISHING |  | .950 | Check bill of materials and pack loose parts | 2 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 3 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | MH-5301-HP-05000-CASING | Customer PO: | M111921SHM | Quote: | 9352.4 | MH-5301-HP-05000-CASING | Line: | 2 |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-11-07 | Make Qty: | 1 | / | ea | Est Hours: | 679
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 66133 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 66134 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 66135 | 0 | Cut Nozzle Pipe and Clean | 0 | 4 | FixedHrs | 4 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 66136 | 0 | Build Nozzles-Weld | 0 | 8 | FixedHrs | 8 | .105 | 0 | Build nozzles and weld FOR RFSO NOZZLES ONLY | _________________ | _________________ | _________________
PRE FAB | 66137 | 0 | Make Manway Parts | 0 | 4 | FixedHrs | 4 | .115 | 0 | Make manway parts: cut clips, form handles, etc. FOR L1, L2, M & N | _________________ | _________________ | _________________
PRE FAB | 66138 | 0 | Build Hatch/Door | 0 | 20 | FixedHrs | 20 | .140 | 0 | Build hatch/door FOR L1, L2, M & N | _________________ | _________________ | _________________
PRE FAB | 66139 | 0 | Cut Parts on Burn Table | 0 | 50 | FixedHrs | 50 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 66140 | 0 | Clean & Prep Parts | 0 | 30 | FixedHrs | 30 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 66141 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 5 | FixedHrs | 5 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 66142 | 0 | Drill/Punch holes | 0 | 20 | FixedHrs | 20 | .255 | 0 | Drill/punch holes CHECK ALL BOLT HOLES CUT ON CNC TABLE; REAM AS REQD | _________________ | _________________ | _________________
PRE FAB | 66143 | 0 | Build Flanges | 0 | 20 | FixedHrs | 20 | .257 | 0 | Build Flanges FOR K1, K2, L, M, N, O, P1 & P2 | _________________ | _________________ | _________________
PRE FAB | 66144 | 0 | Misc Fabrication | 0 | 20 | FixedHrs | 20 | .261 | 0 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks BUIILD LEFT & RIGHT BOTTOM BRACKET ASSEMBLIES | _________________ | _________________ | _________________
INSPECTION | 66145 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 66146 | 0 | BI, SQ, T&C Shells | 0 | 15 | FixedHrs | 15 | .305 | 0 | Shells: bring in plate, square, trim and clean LAYOUT & PREP (4) SHELL SECTIONS | _________________ | _________________ | _________________
PRE FAB | 66147 | 0 | Roll Shell, Tack-Weld I/S | 0 | 15 | FixedHrs | 15 | .315 | 0 | Roll shells, tack and weld inside seams FORM (4) SHELL SECTIONS | _________________ | _________________ | _________________
FIT | 66148 | 0 | S/U and Build Sides | 0 | 60 | FixedHrs | 60 | .320 | 0 | Set up and weld sides - rectangular tank FIT, TACK & WELD SHELL & CASING PLATES | _________________ | _________________ | _________________
FIT | 66149 | 0 | Install Body Flg-Shell | 0 | 6 | FixedHrs | 6 | .325 | 0 | Install body flange on shell - tack MOUNT END FLANGE ON SHELL & WELD | _________________ | _________________ | _________________
INSPECTION | 66150 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 66151 | 0 | L/O Top, B&C Holes | 0 | 10 | FixedHrs | 10 | .355 | 0 | Lay out top head, burn and clean holes BEVEL/PREP HOLES CUT ON CNC TABLE | _________________ | _________________ | _________________
PRE FAB | 66152 | 0 | Set Nozzles & Lugs - Top | 0 | 6 | FixedHrs | 6 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack | _________________ | _________________ | _________________
PRE FAB | 66153 | 0 | Weld Nozzles - Top Head | 0 | 15 | FixedHrs | 15 | .366 | 0 | Weld out top head nozzles, etc. | _________________ | _________________ | _________________
PRE FAB | 66154 | 0 | Install Top Stiffeners | 0 | 45 | FixedHrs | 45 | .375 | 0 | Install top stiffeners FIT & WELD (11) STIFFENERS + (4) CHANNEL STIFFENERS | _________________ | _________________ | _________________
INSPECTION | 66155 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 66156 | 0 | Set Nozzles - Bottom Head | 0 | 5 | FixedHrs | 5 | .465 | 0 | Set nozzles in bottom head - tack FOR NOZZLES 0 (BOTTOM) & P1, P2 (COVER) | _________________ | _________________ | _________________
PRE FAB | 66157 | 0 | Weld Nozzles - Bot. Head | 0 | 15 | FixedHrs | 15 | .466 | 0 | Weld nozzles in bottom head; weld complete FOR NOZZLES O (BOTTOM) & P1, P2 (COVER) | _________________ | _________________ | _________________
PRE FAB | 66158 | 0 | I&W Bottom Repads | 0 | 12 | FixedHrs | 12 | .470 | 0 | Install and weld out repads - bottom head (8) BOTTOM SUPPORT PADS | _________________ | _________________ | _________________
PRE FAB | 66159 | 0 | Install Bottom Stiffeners | 0 | 36 | FixedHrs | 36 | .475 | 0 | Install bottom stiffeners FIT & WELD (12) BOTTOM SHELL STIFFENERS | _________________ | _________________ | _________________
FIT | 66160 | 0 | Install Internal Parts | 0 | 16 | FixedHrs | 16 | .630 | 0 | Install internals - wear plates, rings, clips, etc. FIT & WELD (4) INTERNAL ANGLES ON BOTTOM | _________________ | _________________ | _________________
INSPECTION | 66161 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 66162 | 0 | Fit Top to Shell | 0 | 6 | FixedHrs | 6 | .640 | 0 | Fit top head to shell - tack | _________________ | _________________ | _________________
FIT | 66163 | 0 | Weld top to shell | 0 | 20 | FixedHrs | 20 | .641 | 0 | Weld top head to shell - inside WELD TOP PLATE INSIDE & OUTSIDE | _________________ | _________________ | _________________
MOVE TANK | 66164 | 0 | Move Tank to Detail Rolls | 0 | 4 | FixedHrs | 4 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 66165 | 0 | Install Insul/Vac Rings | 0 | 120 | FixedHrs | 120 | .715 | 0 | Install insulation/vacuum rings - tack INSTALL HORIZONTAL & VERTICAL SHELL STIFFENERS & WELD | _________________ | _________________ | _________________
FIT | 66166 | 0 | Install Lift Lugs on Shl | 0 | 6 | FixedHrs | 6 | .717 | 0 | Install lift lugs on shell INCL L & R TOP SUPPORT BRACKETS | _________________ | _________________ | _________________
FIT | 66167 | 0 | Weld rings, lugs, suppts | 0 | 30 | FixedHrs | 30 | .721 | 0 | Weld insulation / vacuum rings, lugs, supports, etc. FIT & WELD LEFT & RIGHT MOUNTING BRACKET ASSEMBLIES | _________________ | _________________ | _________________
FIT | 66168 | 0 | Set Nozzles in Shell | 0 | 5 | FixedHrs | 5 | .725 | 0 | Set nozzles in shell - tack FOR NOZZLES I, J, L, & M | _________________ | _________________ | _________________
FIT | 66169 | 0 | Weld Shell Nozz & M/Ws | 0 | 25 | FixedHrs | 25 | .726 | 0 | Weld shell nozzles, manways, etc. FOR NOZZLES I, J, L & M (INCL HOLE WATCH) | _________________ | _________________ | _________________
MOVE TANK | 66170 | 0 | Move to Shop Test Area | 0 | 2 | FixedHrs | 2 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 66171 | 0 | Test Tank | 0 | 15 | FixedHrs | 15 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 66172 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
MOVE TANK | 66173 | 0 | Move to Paint Area | 0 | 2 | FixedHrs | 2 | .802 | 0 | Move to paint area | _________________ | _________________ | _________________
INSPECTION | 66174 | 0 | QC Inspection - Sandblast | 0 | 0 | FixedHrs | 0 | .QC9 | 0 | QC Inspection - Sandblast | _________________ | _________________ | _________________
INSPECTION | 66175 | 0 | QC Inspection - Paint | 0 | 0 | FixedHrs | 0 | .QC90 | 0 | QC Inspection - Paint | _________________ | _________________ | _________________
FINISHING | 66176 | 0 | Prepare Tank for Shipment | 0 | 2 | FixedHrs | 2 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
FINISHING | 66177 | 0 | Check BOM, Pack Parts | 0 | 2 | FixedHrs | 2 | .950 | 0 | Check bill of materials and pack loose parts | _________________ | _________________ | _________________
INSPECTION | 66178 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 66179 | 0 | Load on Truck | 0 | 3 | FixedHrs | 3 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
| Part: | MH-5301-HP-05000-CASING |  |  |  | Rev:

## Tasks with Hours
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 4
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld FOR RFSO NOZZLES ONLY
Hours | 8
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc. FOR L1, L2, M & N
Hours | 4
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .140 | Build hatch/door FOR L1, L2, M & N
Hours | 20
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 50
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
Hours | 30
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 5
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes CHECK ALL BOLT HOLES CUT ON CNC TABLE; REAM AS REQD
Hours | 20
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .257 | Build Flanges FOR K1, K2, L, M, N, O, P1 & P2
Hours | 20
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks BUIILD LEFT & RIGHT BOTTOM BRACKET ASSEMBLIES
Hours | 20
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean LAYOUT & PREP (4) SHELL SECTIONS
Hours | 15
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams FORM (4) SHELL SECTIONS
Hours | 15
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .320 | Set up and weld sides - rectangular tank FIT, TACK & WELD SHELL & CASING PLATES
Hours | 60
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .325 | Install body flange on shell - tack MOUNT END FLANGE ON SHELL & WELD
Hours | 6
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes BEVEL/PREP HOLES CUT ON CNC TABLE
Hours | 10
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
Hours | 6
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
Hours | 15
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners FIT & WELD (11) STIFFENERS + (4) CHANNEL STIFFENERS
Hours | 45
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack FOR NOZZLES 0 (BOTTOM) & P1, P2 (COVER)
Hours | 5
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete FOR NOZZLES O (BOTTOM) & P1, P2 (COVER)
Hours | 15
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .470 | Install and weld out repads - bottom head (8) BOTTOM SUPPORT PADS
Hours | 12
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .475 | Install bottom stiffeners FIT & WELD (12) BOTTOM SHELL STIFFENERS
Hours | 36
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. FIT & WELD (4) INTERNAL ANGLES ON BOTTOM
Hours | 16
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
Hours | 6
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .641 | Weld top head to shell - inside WELD TOP PLATE INSIDE & OUTSIDE
Hours | 20
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 4
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack INSTALL HORIZONTAL & VERTICAL SHELL STIFFENERS & WELD
Hours | 120
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell INCL L & R TOP SUPPORT BRACKETS
Hours | 6
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .721 | Weld insulation / vacuum rings, lugs, supports, etc. FIT & WELD LEFT & RIGHT MOUNTING BRACKET ASSEMBLIES
Hours | 30
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack FOR NOZZLES I, J, L, & M
Hours | 5
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. FOR NOZZLES I, J, L & M (INCL HOLE WATCH)
Hours | 25
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 2
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 15
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
Hours | 2
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 2
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
Hours | 2
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 3
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld FOR RFSO NOZZLES ONLY
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .115 | Make manway parts: cut clips, form handles, etc. FOR L1, L2, M & N
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .140 | Build hatch/door FOR L1, L2, M & N
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .255 | Drill/punch holes CHECK ALL BOLT HOLES CUT ON CNC TABLE; REAM AS REQD
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .257 | Build Flanges FOR K1, K2, L, M, N, O, P1 & P2
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks BUIILD LEFT & RIGHT BOTTOM BRACKET ASSEMBLIES
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean LAYOUT & PREP (4) SHELL SECTIONS
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams FORM (4) SHELL SECTIONS
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .320 | Set up and weld sides - rectangular tank FIT, TACK & WELD SHELL & CASING PLATES
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .325 | Install body flange on shell - tack MOUNT END FLANGE ON SHELL & WELD
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .355 | Lay out top head, burn and clean holes BEVEL/PREP HOLES CUT ON CNC TABLE
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc.
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .375 | Install top stiffeners FIT & WELD (11) STIFFENERS + (4) CHANNEL STIFFENERS
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack FOR NOZZLES 0 (BOTTOM) & P1, P2 (COVER)
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete FOR NOZZLES O (BOTTOM) & P1, P2 (COVER)
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .470 | Install and weld out repads - bottom head (8) BOTTOM SUPPORT PADS
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .475 | Install bottom stiffeners FIT & WELD (12) BOTTOM SHELL STIFFENERS
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. FIT & WELD (4) INTERNAL ANGLES ON BOTTOM
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .641 | Weld top head to shell - inside WELD TOP PLATE INSIDE & OUTSIDE
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .715 | Install insulation/vacuum rings - tack INSTALL HORIZONTAL & VERTICAL SHELL STIFFENERS & WELD
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .717 | Install lift lugs on shell INCL L & R TOP SUPPORT BRACKETS
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .721 | Weld insulation / vacuum rings, lugs, supports, etc. FIT & WELD LEFT & RIGHT MOUNTING BRACKET ASSEMBLIES
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack FOR NOZZLES I, J, L, & M
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. FOR NOZZLES I, J, L & M (INCL HOLE WATCH)
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .802 | Move to paint area
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC9 | QC Inspection - Sandblast
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC90 | QC Inspection - Paint
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .950 | Check bill of materials and pack loose parts
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 118-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_