## Build Plan w Hours
Job #: | 124-25
| Description: | BUFFER TANK 1 OF 224 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean | 2 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld USE COBOT FOR N1 & N2 | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 6 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 3 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts CUT (4) ANCHOR ANGLES & PUNCH BOLT HOLES | 2 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks ROLL & WELD BACKING BAR | 2 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 1 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM INSIDE & OUTSIDE | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete | 1 |  |  |  | 0 | 0
PRE FAB |  | .500 | Build skirt - fit and weld shells ROLL SKIRT SHELL & WELD LONG SEAM INSIDE & OUTSIDE | 2 |  |  |  | 0 | 0
FIT |  | .530 | Build skirt - fit anchors / gussets | 1 |  |  |  | 0 | 0
FIT |  | .545 | Weld skirt anchors, gussets, nozzles, manways, etc. | 1 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 4 |  |  |  | 0 | 0
FIT |  | .625 | Install baffles and weld | 6 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. FIT & WELD BACKING BAR TO SHELL | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 1 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 2 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT & WELD TO BOTTOM HEAD | 4 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 1 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. SET & WELD NOZZLES BEFORE INSTALLING TOP HEADS | 3 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete CLEAN INSIDE BEFORE INSTALLING TOP HEAD | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 1 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Build Plan - No Hours
Job #: | 124-25
| Description: | BUFFER TANK 1 OF 224 |  |  | Delivery Date: | 0
Completed By
Work Center |  | Op # | Task | Est Hours | Name | Date | QC Sign Off
PRE FAB |  | .100 | Cut nozzle pipe and clean | 2 |  |  |  | 0 | 0
PRE FAB |  | .105 | Build nozzles and weld USE COBOT FOR N1 & N2 | 4 |  |  |  | 0 | 0
PRE FAB |  | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 6 |  |  |  | 0 | 0
PRE FAB |  | .156 | 0 | 3 |  |  |  | 0 | 0
PRE FAB |  | .200 | Make lift lugs, ground lugs, etc. | 1 |  |  |  | 0 | 0
PRE FAB |  | .252 | Fabricate miscellaneous parts CUT (4) ANCHOR ANGLES & PUNCH BOLT HOLES | 2 |  |  |  | 0 | 0
PRE FAB |  | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks ROLL & WELD BACKING BAR | 2 |  |  |  | 0 | 0
PRE FAB |  | .300 | Wrap top and bottom heads | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC3 | UT Shells | 0 |  |  |  | 1 | 0
PRE FAB |  | .305 | Shells: bring in plate, square, trim and clean | 1 |  |  |  | 0 | 0
PRE FAB |  | .315 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM INSIDE & OUTSIDE | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .365 | Set nozzles, lift lugs, etc. in top head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC4 | QC Inspection - Top/Bottom/Cones | 0 |  |  |  | 1 | 0
PRE FAB |  | .465 | Set nozzles in bottom head - tack | 1 |  |  |  | 0 | 0
PRE FAB |  | .466 | Weld nozzles in bottom head; weld complete | 1 |  |  |  | 0 | 0
PRE FAB |  | .500 | Build skirt - fit and weld shells ROLL SKIRT SHELL & WELD LONG SEAM INSIDE & OUTSIDE | 2 |  |  |  | 0 | 0
FIT |  | .530 | Build skirt - fit anchors / gussets | 1 |  |  |  | 0 | 0
FIT |  | .545 | Weld skirt anchors, gussets, nozzles, manways, etc. | 1 |  |  |  | 0 | 0
INSPECTION |  | .OI1 | ASME Hold Point | 0 |  |  |  | 1 | 1
FIT |  | .600 | Fit bottom head to shell AND WELD INSIDE | 4 |  |  |  | 0 | 0
FIT |  | .625 | Install baffles and weld | 6 |  |  |  | 0 | 0
FIT |  | .630 | Install internals - wear plates, rings, clips, etc. FIT & WELD BACKING BAR TO SHELL | 3 |  |  |  | 0 | 0
INSPECTION |  | .QC5 | QC Inspection - Internal | 0 |  |  |  | 1 | 0
FIT |  | .640 | Fit top head to shell - tack | 1 |  |  |  | 0 | 0
FIT |  | .645 | Weld all outside seams | 2 |  |  |  | 0 | 0
MOVE TANK |  | .800 | Move tank to detail rolls | 1 |  |  |  | 0 | 0
FIT |  | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT & WELD TO BOTTOM HEAD | 4 |  |  |  | 0 | 0
FIT |  | .725 | Set nozzles in shell - tack | 1 |  |  |  | 0 | 0
FIT |  | .726 | Weld shell nozzles, manways, etc. SET & WELD NOZZLES BEFORE INSTALLING TOP HEADS | 3 |  |  |  | 0 | 0
FINISHING |  | .765 | Install name tag | 1 |  |  |  | 0 | 0
FIT |  | .770 | Inspect tank, make repairs, get QC inspector | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC6 | QC Inspection - Fabrication | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI2 | ASME Inspection Internal | 0 |  |  |  | 1 | 1
MOVE TANK |  | .801 | Move to shop test area | 1 |  |  |  | 0 | 0
FINISHING |  | .910 | Test tank | 4 |  |  |  | 0 | 0
INSPECTION |  | .QC7 | QC Inspection - Test | 0 |  |  |  | 1 | 0
INSPECTION |  | .OI3 | ASME Inspection Test | 0 |  |  |  | 1 | 1
FINISHING |  | .920 | Clean tank complete CLEAN INSIDE BEFORE INSTALLING TOP HEAD | 5 |  |  |  | 0 | 0
INSPECTION |  | .QC8 | QC Inspection - Clean | 0 |  |  |  | 1 | 0
FINISHING |  | .940 | Prepare tank for shipment | 1 |  |  |  | 0 | 0
INSPECTION |  | .QC95 | QC Inspection - Final & Loose Items | 0 |  |  |  | 1 | 0
SHIPPING |  | .960 | Load on truck | 1 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 |  |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0
0 |  | 0 | 0 | 0 |  |  |  | 0 | 0

## Sheet2-PASTE HERE!
Part: | BUFFER TANK 1 OF 224 | Customer PO: | 130391459 | Quote: | 9391.4 |  | Line: |  |  |  | Rev: |  | Drawing: |  | Order Qty: | 1 | / | ea | Order Date: | 2025-12-15 | Make Qty: | 1 | / | ea | Est Hours: | 74
Job Notes:
| Linked SO Lines | Sales Order | Part | Order Qty | Remaining Qty | Due Date | SO Line | Description | Customer
| Delivery Schedule | Promised Date | Promised Quantity | Remaining Quantity | Comments
| Routing | Comments | WC/Vendor | Sch Start | Oper/Serv | Operation Key | Sch End | Description | Setup | Run Rate | Run | Name | Date | QC SignOff
PRE FAB | 55508 | 0 | Receive Material | 0 | 0 | FixedHrs | 0 | .010 | 0 | Receive Material | _________________ | _________________ | _________________
INSPECTION | 55509 | 0 | UT Top & Bottom Heads | 0 | 0 | FixedHrs | 0 | .QC1 | 0 | UT top and bottom heads | _________________ | _________________ | _________________
PRE FAB | 55510 | 0 | Cut Nozzle Pipe and Clean | 0 | 2 | FixedHrs | 2 | .100 | 0 | Cut nozzle pipe and clean | _________________ | _________________ | _________________
PRE FAB | 55511 | 0 | Build Nozzles-Weld | 0 | 4 | FixedHrs | 4 | .105 | 0 | Build nozzles and weld USE COBOT FOR N1 & N2 | _________________ | _________________ | _________________
PRE FAB | 55512 | 0 | Cut Parts on Burn Table | 0 | 6 | FixedHrs | 6 | .155 | 0 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | _________________ | _________________ | _________________
PRE FAB | 55513 | 0 | Clean & Prep Parts | 0 | 3 | FixedHrs | 3 | .156 | 0 |  | _________________ | _________________ | _________________
PRE FAB | 55514 | 0 | Bld Lift Lugs, Grd Lugs | 0 | 1 | FixedHrs | 1 | .200 | 0 | Make lift lugs, ground lugs, etc. | _________________ | _________________ | _________________
PRE FAB | 55515 | 0 | Fab Miscellaneous Parts | 0 | 2 | FixedHrs | 2 | .252 | 0 | Fabricate miscellaneous parts CUT (4) ANCHOR ANGLES & PUNCH BOLT HOLES | _________________ | _________________ | _________________
PRE FAB | 55516 | 0 | Misc Fabrication | 0 | 2 | FixedHrs | 2 | .261 | 0 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks ROLL & WELD BACKING BAR | _________________ | _________________ | _________________
PRE FAB | 55517 | 0 | Wrap Top & Bottom Heads | 0 | 1 | FixedHrs | 1 | .300 | 0 | Wrap top and bottom heads | _________________ | _________________ | _________________
INSPECTION | 55518 | 0 | UT Shells | 0 | 0 | FixedHrs | 0 | .QC3 | 0 | UT Shells | _________________ | _________________ | _________________
PRE FAB | 55519 | 0 | BI, SQ, T&C Shells | 0 | 1 | FixedHrs | 1 | .305 | 0 | Shells: bring in plate, square, trim and clean | _________________ | _________________ | _________________
PRE FAB | 55520 | 0 | Roll Shell, Tack-Weld I/S | 0 | 3 | FixedHrs | 3 | .315 | 0 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM INSIDE & OUTSIDE | _________________ | _________________ | _________________
INSPECTION | 55521 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 55522 | 0 | Set Nozzles & Lugs - Top | 0 | 1 | FixedHrs | 1 | .365 | 0 | Set nozzles, lift lugs, etc. in top head - tack | _________________ | _________________ | _________________
PRE FAB | 55523 | 0 | Weld Nozzles - Top Head | 0 | 3 | FixedHrs | 3 | .366 | 0 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | _________________ | _________________ | _________________
INSPECTION | 55524 | 0 | QC Inspection -Top/Bot/Co | 0 | 0 | FixedHrs | 0 | .QC4 | 0 | QC Inspection - Top/Bottom/Cones | _________________ | _________________ | _________________
PRE FAB | 55525 | 0 | Set Nozzles - Bottom Head | 0 | 1 | FixedHrs | 1 | .465 | 0 | Set nozzles in bottom head - tack | _________________ | _________________ | _________________
PRE FAB | 55526 | 0 | Weld Nozzles - Bot. Head | 0 | 1 | FixedHrs | 1 | .466 | 0 | Weld nozzles in bottom head; weld complete | _________________ | _________________ | _________________
PRE FAB | 55527 | 0 | Bld Skirt, Roll & Tack | 0 | 2 | FixedHrs | 2 | .500 | 0 | Build skirt - fit and weld shells ROLL SKIRT SHELL & WELD LONG SEAM INSIDE & OUTSIDE | _________________ | _________________ | _________________
FIT | 55528 | 0 | Bld Skirt, Fit Anchor/Gst | 0 | 1 | FixedHrs | 1 | .530 | 0 | Build skirt - fit anchors / gussets | _________________ | _________________ | _________________
FIT | 55529 | 0 | Weld Skirt Nozzles, Etc. | 0 | 1 | FixedHrs | 1 | .545 | 0 | Weld skirt anchors, gussets, nozzles, manways, etc. | _________________ | _________________ | _________________
INSPECTION | 55530 | 0 | ASME Hold Point | 0 | 0 | FixedHrs | 0 | .OI1 | 0 | ASME Hold Point | _________________ | _________________ | _________________
FIT | 55531 | 0 | Fit Bottom Head to Shell | 0 | 4 | FixedHrs | 4 | .600 | 0 | Fit bottom head to shell AND WELD INSIDE | _________________ | _________________ | _________________
FIT | 55532 | 0 | Install Baffles-Weld | 0 | 6 | FixedHrs | 6 | .625 | 0 | Install baffles and weld | _________________ | _________________ | _________________
FIT | 55533 | 0 | Install Internal Parts | 0 | 3 | FixedHrs | 3 | .630 | 0 | Install internals - wear plates, rings, clips, etc. FIT & WELD BACKING BAR TO SHELL | _________________ | _________________ | _________________
INSPECTION | 55534 | 0 | QC Inspection - Internal | 0 | 0 | FixedHrs | 0 | .QC5 | 0 | QC Inspection - Internal | _________________ | _________________ | _________________
FIT | 55535 | 0 | Fit Top to Shell | 0 | 1 | FixedHrs | 1 | .640 | 0 | Fit top head to shell - tack | _________________ | _________________ | _________________
FIT | 55536 | 0 | Weld all Outside Seams | 0 | 2 | FixedHrs | 2 | .645 | 0 | Weld all outside seams | _________________ | _________________ | _________________
MOVE TANK | 55537 | 0 | Move Tank to Detail Rolls | 0 | 1 | FixedHrs | 1 | .800 | 0 | Move tank to detail rolls | _________________ | _________________ | _________________
FIT | 55538 | 0 | Install Support Parts | 0 | 4 | FixedHrs | 4 | .720 | 0 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT & WELD TO BOTTOM HEAD | _________________ | _________________ | _________________
FIT | 55539 | 0 | Set Nozzles in Shell | 0 | 1 | FixedHrs | 1 | .725 | 0 | Set nozzles in shell - tack | _________________ | _________________ | _________________
FIT | 55553 | 0 | Weld Shell Nozz & M/Ws | 0 | 3 | FixedHrs | 3 | .726 | 0 | Weld shell nozzles, manways, etc. SET & WELD NOZZLES BEFORE INSTALLING TOP HEADS | _________________ | _________________ | _________________
FINISHING | 55540 | 0 | Install Name Tag | 0 | 1 | FixedHrs | 1 | .765 | 0 | Install name tag | _________________ | _________________ | _________________
FIT | 55541 | 0 | Inspect Tank, Make Repair | 0 | 1 | FixedHrs | 1 | .770 | 0 | Inspect tank, make repairs, get QC inspector | _________________ | _________________ | _________________
INSPECTION | 55542 | 0 | QC Inspection - Fab | 0 | 0 | FixedHrs | 0 | .QC6 | 0 | QC Inspection - Fabrication | _________________ | _________________ | _________________
INSPECTION | 55543 | 0 | ASME Inspection Internal | 0 | 0 | FixedHrs | 0 | .OI2 | 0 | ASME Inspection Internal | _________________ | _________________ | _________________
MOVE TANK | 55544 | 0 | Move to Shop Test Area | 0 | 1 | FixedHrs | 1 | .801 | 0 | Move to shop test area | _________________ | _________________ | _________________
FINISHING | 55545 | 0 | Test Tank | 0 | 4 | FixedHrs | 4 | .910 | 0 | Test tank | _________________ | _________________ | _________________
INSPECTION | 55546 | 0 | QC Inspection - Test | 0 | 0 | FixedHrs | 0 | .QC7 | 0 | QC Inspection - Test | _________________ | _________________ | _________________
INSPECTION | 55547 | 0 | ASME Inspection Test | 0 | 0 | FixedHrs | 0 | .OI3 | 0 | ASME Inspection Test | _________________ | _________________ | _________________
FINISHING | 55548 | 0 | Clean Tank Complete | 0 | 5 | FixedHrs | 5 | .920 | 0 | Clean tank complete CLEAN INSIDE BEFORE INSTALLING TOP HEAD | _________________ | _________________ | _________________
INSPECTION | 55549 | 0 | QC Inspection - Clean | 0 | 0 | FixedHrs | 0 | .QC8 | 0 | QC Inspection - Clean | _________________ | _________________ | _________________
FINISHING | 55550 | 0 | Prepare Tank for Shipment | 0 | 1 | FixedHrs | 1 | .940 | 0 | Prepare tank for shipment | _________________ | _________________ | _________________
INSPECTION | 55551 | 0 | QC Inspection - Final & L | 0 | 0 | FixedHrs | 0 | .QC95 | 0 | QC Inspection - Final & Loose Items | _________________ | _________________ | _________________
SHIPPING | 55552 | 0 | Load on Truck | 0 | 1 | FixedHrs | 1 | .960 | 0 | Load on truck | _________________ | _________________ | _________________
| Part: | BUFFER TANK 1 OF 224 |  |  |  | Rev:

## Tasks with Hours
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
Hours | 2
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld USE COBOT FOR N1 & N2
Hours | 4
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
Hours | 6
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
Hours | 3
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts CUT (4) ANCHOR ANGLES & PUNCH BOLT HOLES
Hours | 2
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks ROLL & WELD BACKING BAR
Hours | 2
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM INSIDE & OUTSIDE
Hours | 3
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS
Hours | 3
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .500 | Build skirt - fit and weld shells ROLL SKIRT SHELL & WELD LONG SEAM INSIDE & OUTSIDE
Hours | 2
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .530 | Build skirt - fit anchors / gussets
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .545 | Weld skirt anchors, gussets, nozzles, manways, etc.
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
Hours | 4
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .625 | Install baffles and weld
Hours | 6
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. FIT & WELD BACKING BAR TO SHELL
Hours | 3
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
Hours | 2
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT & WELD TO BOTTOM HEAD
Hours | 4
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. SET & WELD NOZZLES BEFORE INSTALLING TOP HEADS
Hours | 3
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
Hours | 4
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete CLEAN INSIDE BEFORE INSTALLING TOP HEAD
Hours | 5
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
Hours | 1
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
Hours | 0
_

## Tasks - No Hours
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .100 | Cut nozzle pipe and clean
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .105 | Build nozzles and weld USE COBOT FOR N1 & N2
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!)
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .156 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .200 | Make lift lugs, ground lugs, etc.
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .252 | Fabricate miscellaneous parts CUT (4) ANCHOR ANGLES & PUNCH BOLT HOLES
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks ROLL & WELD BACKING BAR
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .300 | Wrap top and bottom heads
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC3 | UT Shells
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .305 | Shells: bring in plate, square, trim and clean
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .315 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM INSIDE & OUTSIDE
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .365 | Set nozzles, lift lugs, etc. in top head - tack
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC4 | QC Inspection - Top/Bottom/Cones
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .465 | Set nozzles in bottom head - tack
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .466 | Weld nozzles in bottom head; weld complete
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .500 | Build skirt - fit and weld shells ROLL SKIRT SHELL & WELD LONG SEAM INSIDE & OUTSIDE
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .530 | Build skirt - fit anchors / gussets
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .545 | Weld skirt anchors, gussets, nozzles, manways, etc.
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI1 | ASME Hold Point
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .600 | Fit bottom head to shell AND WELD INSIDE
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .625 | Install baffles and weld
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .630 | Install internals - wear plates, rings, clips, etc. FIT & WELD BACKING BAR TO SHELL
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC5 | QC Inspection - Internal
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .640 | Fit top head to shell - tack
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .645 | Weld all outside seams
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .800 | Move tank to detail rolls
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT & WELD TO BOTTOM HEAD
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .725 | Set nozzles in shell - tack
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .726 | Weld shell nozzles, manways, etc. SET & WELD NOZZLES BEFORE INSTALLING TOP HEADS
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .765 | Install name tag
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .770 | Inspect tank, make repairs, get QC inspector
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC6 | QC Inspection - Fabrication
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI2 | ASME Inspection Internal
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .801 | Move to shop test area
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .910 | Test tank
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC7 | QC Inspection - Test
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .OI3 | ASME Inspection Test
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .920 | Clean tank complete CLEAN INSIDE BEFORE INSTALLING TOP HEAD
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC8 | QC Inspection - Clean
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .940 | Prepare tank for shipment
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .QC95 | QC Inspection - Final & Loose Items
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | .960 | Load on truck
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_
Job #: | 124-25 | Description | Assigned | Hrs Used | % Compl.
Op #: | 0 | 0
_