## Schedule
Savannah Tank and Equipment |  |  |  |  | PLAN | ACT |  |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
[5 empty] | 2026-01-12 | 2026-01-12 | time axis 2026-01-12 to 2027-02-22
[5 empty] | 7 | 7 |  |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
OVERHEAD | 0 | REL |  |  | 50 | 50 |  |  | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
| DUE | JOB # | QTE | PRE |  |  | WK | WK% | [59 empty] | REQ | BAL | JOB #
Vertiv Tank 1 | 2026-03-16 | 124-25 | 61 |  |  |  | 0 | 0% | 2026-02-02: 20; 2026-02-09: 20; 2026-02-16: 21 | 61 | 61 | 124-25 | 0
Vertiv Tank 2 | 2026-03-16 | 125-25 | 61 |  |  |  | 0 | 0% | 2026-02-02: 20; 2026-02-09: 20; 2026-02-16: 21 | 61 | 61 | 125-25 | 0
Vertiv Tank 3 | 2026-03-16 | 126-25 | 61 |  |  |  | 0 | 0% | 2026-02-02: 20; 2026-02-09: 20; 2026-02-16: 21 | 61 | 61 | 126-25 | 0
Vertiv Tank 4 | 2026-03-16 | 127-25 | 61 |  |  |  | 0 | 0% | 2026-02-02: 20; 2026-02-09: 20; 2026-02-16: 21 | 61 | 61 | 127-25 | 0
Vertiv Tank 5 | 2026-03-16 | 128-25 | 61 |  |  |  | 0 | 0% | 2026-02-02: 20; 2026-02-09: 20; 2026-02-16: 21 | 61 | 61 | 128-25 | 0
Vertiv Tank 6 | 2026-03-16 | 129-25 | 61 |  |  |  | 0 | 0% | 2026-02-02: 20; 2026-02-09: 20; 2026-02-16: 21 | 61 | 61 | 129-25 | 0
Vertiv Tank 7 | 2026-03-16 | 130-25 | 61 |  |  |  | 0 | 0% | 2026-02-02: 20; 2026-02-09: 20; 2026-02-16: 21 | 61 | 61 | 130-25 | 0
Vertiv Tank 8 | 2026-03-16 | 131-25 | 61 |  |  |  | 0 | 0% | 2026-02-09: 20; 2026-02-16: 20; 2026-02-23: 21 | 61 | 61 | 131-25 | 0
Vertiv Tank 9 | 2026-03-16 | 132-25 | 61 |  |  |  | 0 | 0% | 2026-02-09: 20; 2026-02-16: 20; 2026-02-23: 21 | 61 | 61 | 132-25 | 0
Vertiv Tank 10 | 2026-03-16 | 133-25 | 61 |  |  |  | 0 | 0% | 2026-02-09: 20; 2026-02-16: 20; 2026-02-23: 21 | 61 | 61 | 133-25 | 0
Vertiv Tank 11 | 2026-03-16 | 134-25 | 61 |  |  |  | 0 | 0% | 2026-02-09: 20; 2026-02-16: 20; 2026-02-23: 21 | 61 | 61 | 134-25 | 0
Vertiv Tank 12 | 2026-03-16 | 135-25 | 61 |  |  |  | 0 | 0% | 2026-02-09: 20; 2026-02-16: 20; 2026-02-23: 21 | 61 | 61 | 135-25 | 0
Vertiv Tank 13 | 2026-03-16 | 136-25 | 61 |  |  |  | 0 | 0% | 2026-02-09: 20; 2026-02-16: 20; 2026-02-23: 21 | 61 | 61 | 136-25 | 0
Vertiv Tank 14 | 2026-03-16 | 137-25 | 61 |  |  |  | 0 | 0% | 2026-02-16: 20; 2026-02-23: 20; 2026-03-02: 21 | 61 | 61 | 137-25 | 0
Vertiv Tank 15 | 2026-03-16 | 138-25 | 61 |  |  |  | 0 | 0% | 2026-02-16: 20; 2026-02-23: 20; 2026-03-02: 21 | 61 | 61 | 138-25 | 0
Vertiv Tank 16 | 2026-03-16 | 139-25 | 61 |  |  |  | 0 | 0% | 2026-02-16: 20; 2026-02-23: 20; 2026-03-02: 21 | 61 | 61 | 139-25 | 0
Vertiv Tank 17 | 2026-03-16 | 140-25 | 61 |  |  |  | 0 | 0% | 2026-02-16: 20; 2026-02-23: 20; 2026-03-02: 21 | 61 | 61 | 140-25 | 0
Vertiv Tank 18 | 2026-03-16 | 141-25 | 61 |  |  |  | 0 | 0% | 2026-02-16: 20; 2026-02-23: 20; 2026-03-02: 21 | 61 | 61 | 141-25 | 0
Vertiv Tank 19 | 2026-03-16 | 142-25 | 61 |  |  |  | 0 | 0% | 2026-02-23: 20; 2026-03-02: 20; 2026-03-09: 21 | 61 | 61 | 142-25 | 0
Vertiv Tank 20 | 2026-03-16 | 143-25 | 61 |  |  |  | 0 | 0% | 2026-02-23: 20; 2026-03-02: 20; 2026-03-09: 21 | 61 | 61 | 143-25 | 0
Vertiv Tank 21 | 2026-03-16 | 144-25 | 61 |  |  |  | 0 | 0% | 2026-02-23: 20; 2026-03-02: 20; 2026-03-09: 21 | 61 | 61 | 144-25 | 0
Vertiv Tank 22 | 2026-03-16 | 145-25 | 61 |  |  |  | 0 | 0% | 2026-02-23: 20; 2026-03-02: 20; 2026-03-09: 21 | 61 | 61 | 145-25 | 0
Vertiv Tank 23 | 2026-03-16 | 146-25 | 61 |  |  |  | 0 | 0% | 2026-02-23: 20; 2026-03-02: 20; 2026-03-09: 21 | 61 | 61 | 146-25 | 0
Vertiv Tank 24 | 2026-03-16 | 147-25 | 61 |  |  |  | 0 | 0% | 2026-02-23: 20; 2026-03-02: 20; 2026-03-09: 21 | 61 | 61 | 147-25 | 0
Vertiv Tank 25 | 2026-05-04 | 148-25 | 61 |  |  |  | 0 | 0% | 2026-03-02: 20; 2026-03-09: 20; 2026-03-16: 21 | 61 | 61 | 148-25 | 0
Vertiv Tank 26 | 2026-05-04 | 149-25 | 61 |  |  |  | 0 | 0% | 2026-03-02: 20; 2026-03-09: 20; 2026-03-16: 21 | 61 | 61 | 149-25 | 0
Vertiv Tank 27 | 2026-05-04 | 150-25 | 61 |  |  |  | 0 | 0% | 2026-03-02: 20; 2026-03-09: 20; 2026-03-16: 21 | 61 | 61 | 150-25 | 0
Vertiv Tank 28 | 2026-05-04 | 151-25 | 61 |  |  |  | 0 | 0% | 2026-03-02: 20; 2026-03-09: 20; 2026-03-16: 21 | 61 | 61 | 151-25 | 0
Vertiv Tank 29 | 2026-05-04 | 152-25 | 61 |  |  |  | 0 | 0% | 2026-03-02: 20; 2026-03-09: 20; 2026-03-16: 21 | 61 | 61 | 152-25 | 0
Vertiv Tank 30 | 2026-05-04 | 153-25 | 61 |  |  |  | 0 | 0% | 2026-03-09: 20; 2026-03-16: 20; 2026-03-23: 21 | 61 | 61 | 153-25 | 0
Vertiv Tank 31 | 2026-05-04 | 154-25 | 61 |  |  |  | 0 | 0% | 2026-03-09: 20; 2026-03-16: 20; 2026-03-23: 21 | 61 | 61 | 154-25 | 0
Vertiv Tank 32 | 2026-05-04 | 155-25 | 61 |  |  |  | 0 | 0% | 2026-03-09: 20; 2026-03-16: 20; 2026-03-23: 21 | 61 | 61 | 155-25 | 0
Vertiv Tank 33 | 2026-05-04 | 156-25 | 61 |  |  |  | 0 | 0% | 2026-03-09: 20; 2026-03-16: 20; 2026-03-23: 21 | 61 | 61 | 156-25 | 0
Vertiv Tank 34 | 2026-05-04 | 157-25 | 61 |  |  |  | 0 | 0% | 2026-03-09: 20; 2026-03-16: 20; 2026-03-23: 21 | 61 | 61 | 157-25 | 0
Vertiv Tank 35 | 2026-05-04 | 158-25 | 61 |  |  |  | 0 | 0% | 2026-03-16: 20; 2026-03-23: 20; 2026-03-30: 21 | 61 | 61 | 158-25 | 0
Vertiv Tank 36 | 2026-05-04 | 159-25 | 61 |  |  |  | 0 | 0% | 2026-03-16: 20; 2026-03-23: 20; 2026-03-30: 21 | 61 | 61 | 159-25 | 0
Vertiv Tank 37 | 2026-05-04 | 160-25 | 61 |  |  |  | 0 | 0% | 2026-03-16: 20; 2026-03-23: 20; 2026-03-30: 21 | 61 | 61 | 160-25 | 0
Vertiv Tank 38 | 2026-05-04 | 161-25 | 61 |  |  |  | 0 | 0% | 2026-03-16: 20; 2026-03-23: 20; 2026-03-30: 21 | 61 | 61 | 161-25 | 0
Vertiv Tank 39 | 2026-05-04 | 162-25 | 61 |  |  |  | 0 | 0% | 2026-03-16: 20; 2026-03-23: 20; 2026-03-30: 21 | 61 | 61 | 162-25 | 0
Vertiv Tank 40 | 2026-05-04 | 163-25 | 61 |  |  |  | 0 | 0% | 2026-03-23: 20; 2026-03-30: 20; 2026-04-06: 21 | 61 | 61 | 163-25 | 0
Vertiv Tank 41 | 2026-05-04 | 164-25 | 61 |  |  |  | 0 | 0% | 2026-03-23: 20; 2026-03-30: 20; 2026-04-06: 21 | 61 | 61 | 164-25 | 0
Vertiv Tank 42 | 2026-05-04 | 165-25 | 61 |  |  |  | 0 | 0% | 2026-03-23: 20; 2026-03-30: 20; 2026-04-06: 21 | 61 | 61 | 165-25 | 0
Vertiv Tank 43 | 2026-05-04 | 166-25 | 61 |  |  |  | 0 | 0% | 2026-03-23: 20; 2026-03-30: 20; 2026-04-06: 21 | 61 | 61 | 166-25 | 0
Vertiv Tank 44 | 2026-05-04 | 167-25 | 61 |  |  |  | 0 | 0% | 2026-03-23: 20; 2026-03-30: 20; 2026-04-06: 21 | 61 | 61 | 167-25 | 0
Vertiv Tank 45 | 2026-05-04 | 168-25 | 61 |  |  |  | 0 | 0% | 2026-03-30: 20; 2026-04-06: 20; 2026-04-13: 21 | 61 | 61 | 168-25 | 0
Vertiv Tank 46 | 2026-05-04 | 169-25 | 61 |  |  |  | 0 | 0% | 2026-03-30: 20; 2026-04-06: 20; 2026-04-13: 21 | 61 | 61 | 169-25 | 0
Vertiv Tank 47 | 2026-05-04 | 170-25 | 61 |  |  |  | 0 | 0% | 2026-03-30: 20; 2026-04-06: 20; 2026-04-13: 21 | 61 | 61 | 170-25 | 0
Vertiv Tank 48 | 2026-05-04 | 171-25 | 61 |  |  |  | 0 | 0% | 2026-03-30: 20; 2026-04-06: 20; 2026-04-13: 21 | 61 | 61 | 171-25 | 0
Vertiv Tank 49 | 2026-05-04 | 172-25 | 61 |  |  |  | 0 | 0% | 2026-03-30: 20; 2026-04-06: 20; 2026-04-13: 21 | 61 | 61 | 172-25 | 0
Vertiv Tank 50 | 2026-05-04 | 173-25 | 61 |  |  |  | 0 | 0% | 2026-04-06: 20; 2026-04-13: 20; 2026-04-20: 21 | 61 | 61 | 173-25 | 0
Vertiv Tank 51 | 2026-05-04 | 174-25 | 61 |  |  |  | 0 | 0% | 2026-04-06: 20; 2026-04-13: 20; 2026-04-20: 21 | 61 | 61 | 174-25 | 0
Vertiv Tank 52 | 2026-05-04 | 175-25 | 61 |  |  |  | 0 | 0% | 2026-04-06: 20; 2026-04-13: 20; 2026-04-20: 21 | 61 | 61 | 175-25 | 0
Vertiv Tank 53 | 2026-05-04 | 176-25 | 61 |  |  |  | 0 | 0% | 2026-04-06: 20; 2026-04-13: 20; 2026-04-20: 21 | 61 | 61 | 176-25 | 0
Vertiv Tank 54 | 2026-05-04 | 177-25 | 61 |  |  |  | 0 | 0% | 2026-04-06: 20; 2026-04-13: 20; 2026-04-20: 21 | 61 | 61 | 177-25 | 0
Vertiv Tank 55 | 2026-05-04 | 178-25 | 61 |  |  |  | 0 | 0% | 2026-04-13: 20; 2026-04-20: 20; 2026-04-27: 21 | 61 | 61 | 178-25 | 0
Vertiv Tank 56 | 2026-05-04 | 179-25 | 61 |  |  |  | 0 | 0% | 2026-04-13: 20; 2026-04-20: 20; 2026-04-27: 21 | 61 | 61 | 179-25 | 0
Vertiv Tank 57 | 2026-07-27 | 180-25 | 61 |  |  |  | 0 | 0% | 2026-04-13: 20; 2026-04-20: 20; 2026-04-27: 21 | 61 | 61 | 180-25 | 0
Vertiv Tank 58 | 2026-07-27 | 181-25 | 61 |  |  |  | 0 | 0% | 2026-04-13: 20; 2026-04-20: 20; 2026-04-27: 21 | 61 | 61 | 181-25 | 0
Vertiv Tank 59 | 2026-07-27 | 182-25 | 61 |  |  |  | 0 | 0% | 2026-04-13: 20; 2026-04-20: 20; 2026-04-27: 21 | 61 | 61 | 182-25 | 0
Vertiv Tank 60 | 2026-07-27 | 183-25 | 61 |  |  |  | 0 | 0% | 2026-04-20: 20; 2026-04-27: 20; 2026-05-04: 21 | 61 | 61 | 183-25 | 0
Vertiv Tank 61 | 2026-07-27 | 184-25 | 61 |  |  |  | 0 | 0% | 2026-04-20: 20; 2026-04-27: 20; 2026-05-04: 21 | 61 | 61 | 184-25 | 0
Vertiv Tank 62 | 2026-07-27 | 185-25 | 61 |  |  |  | 0 | 0% | 2026-04-20: 20; 2026-04-27: 20; 2026-05-04: 21 | 61 | 61 | 185-25 | 0
Vertiv Tank 63 | 2026-07-27 | 186-25 | 61 |  |  |  | 0 | 0% | 2026-04-20: 20; 2026-04-27: 20; 2026-05-04: 21 | 61 | 61 | 186-25 | 0
Vertiv Tank 64 | 2026-07-27 | 187-25 | 61 |  |  |  | 0 | 0% | 2026-04-20: 20; 2026-04-27: 20; 2026-05-04: 21 | 61 | 61 | 187-25 | 0
Vertiv Tank 65 | 2026-07-27 | 188-25 | 61 |  |  |  | 0 | 0% | 2026-04-27: 20; 2026-05-04: 20; 2026-05-11: 21 | 61 | 61 | 188-25 | 0
Vertiv Tank 66 | 2026-07-27 | 189-25 | 61 |  |  |  | 0 | 0% | 2026-04-27: 20; 2026-05-04: 20; 2026-05-11: 21 | 61 | 61 | 189-25 | 0
Vertiv Tank 67 | 2026-07-27 | 190-25 | 61 |  |  |  | 0 | 0% | 2026-04-27: 20; 2026-05-04: 20; 2026-05-11: 21 | 61 | 61 | 190-25 | 0
Vertiv Tank 68 | 2026-07-27 | 191-25 | 61 |  |  |  | 0 | 0% | 2026-04-27: 20; 2026-05-04: 20; 2026-05-11: 21 | 61 | 61 | 191-25 | 0
Vertiv Tank 69 | 2026-07-27 | 192-25 | 61 |  |  |  | 0 | 0% | 2026-04-27: 20; 2026-05-04: 20; 2026-05-11: 21 | 61 | 61 | 192-25 | 0
Vertiv Tank 70 | 2026-07-27 | 193-25 | 61 |  |  |  | 0 | 0% | 2026-05-04: 20; 2026-05-11: 20; 2026-05-18: 21 | 61 | 61 | 193-25 | 0
Vertiv Tank 71 | 2026-07-27 | 194-25 | 61 |  |  |  | 0 | 0% | 2026-05-04: 20; 2026-05-11: 20; 2026-05-18: 21 | 61 | 61 | 194-25 | 0
Vertiv Tank 72 | 2026-07-27 | 195-25 | 61 |  |  |  | 0 | 0% | 2026-05-04: 20; 2026-05-11: 20; 2026-05-18: 21 | 61 | 61 | 195-25 | 0
Vertiv Tank 73 | 2026-07-27 | 196-25 | 61 |  |  |  | 0 | 0% | 2026-05-04: 20; 2026-05-11: 20; 2026-05-18: 21 | 61 | 61 | 196-25 | 0
Vertiv Tank 74 | 2026-07-27 | 197-25 | 61 |  |  |  | 0 | 0% | 2026-05-04: 20; 2026-05-11: 20; 2026-05-18: 21 | 61 | 61 | 197-25 | 0
Vertiv Tank 75 | 2026-07-27 | 198-25 | 61 |  |  |  | 0 | 0% | 2026-05-11: 20; 2026-05-18: 20; 2026-05-25: 21 | 61 | 61 | 198-25 | 0
Vertiv Tank 76 | 2026-07-27 | 199-25 | 61 |  |  |  | 0 | 0% | 2026-05-11: 20; 2026-05-18: 20; 2026-05-25: 21 | 61 | 61 | 199-25 | 0
Vertiv Tank 77 | 2026-07-27 | 200-25 | 61 |  |  |  | 0 | 0% | 2026-05-11: 20; 2026-05-18: 20; 2026-05-25: 21 | 61 | 61 | 200-25 | 0
Vertiv Tank 78 | 2026-07-27 | 201-25 | 61 |  |  |  | 0 | 0% | 2026-05-11: 20; 2026-05-18: 20; 2026-05-25: 21 | 61 | 61 | 201-25 | 0
Vertiv Tank 79 | 2026-07-27 | 202-25 | 61 |  |  |  | 0 | 0% | 2026-05-11: 20; 2026-05-18: 20; 2026-05-25: 21 | 61 | 61 | 202-25 | 0
Vertiv Tank 80 | 2026-07-27 | 203-25 | 61 |  |  |  | 0 | 0% | 2026-05-18: 20; 2026-05-25: 20; 2026-06-01: 21 | 61 | 61 | 203-25 | 0
Vertiv Tank 81 | 2026-07-27 | 204-25 | 61 |  |  |  | 0 | 0% | 2026-05-18: 20; 2026-05-25: 20; 2026-06-01: 21 | 61 | 61 | 204-25 | 0
Vertiv Tank 82 | 2026-07-27 | 205-25 | 61 |  |  |  | 0 | 0% | 2026-05-18: 20; 2026-05-25: 20; 2026-06-01: 21 | 61 | 61 | 205-25 | 0
Vertiv Tank 83 | 2026-07-27 | 206-25 | 61 |  |  |  | 0 | 0% | 2026-05-18: 20; 2026-05-25: 20; 2026-06-01: 21 | 61 | 61 | 206-25 | 0
Vertiv Tank 84 | 2026-07-27 | 207-25 | 61 |  |  |  | 0 | 0% | 2026-05-18: 20; 2026-05-25: 20; 2026-06-01: 21 | 61 | 61 | 207-25 | 0
Vertiv Tank 85 | 2026-07-27 | 208-25 | 61 |  |  |  | 0 | 0% | 2026-06-01: 20; 2026-06-08: 20; 2026-06-15: 21 | 61 | 61 | 208-25 | 0
Vertiv Tank 86 | 2026-07-27 | 209-25 | 61 |  |  |  | 0 | 0% | 2026-06-01: 20; 2026-06-08: 20; 2026-06-15: 21 | 61 | 61 | 209-25 | 0
Vertiv Tank 87 | 2026-07-27 | 210-25 | 61 |  |  |  | 0 | 0% | 2026-06-01: 20; 2026-06-08: 20; 2026-06-15: 21 | 61 | 61 | 210-25 | 0
Vertiv Tank 88 | 2026-07-27 | 211-25 | 61 |  |  |  | 0 | 0% | 2026-06-01: 20; 2026-06-08: 20; 2026-06-15: 21 | 61 | 61 | 211-25 | 0
Vertiv Tank 89 | 2026-07-27 | 212-25 | 61 |  |  |  | 0 | 0% | 2026-06-01: 20; 2026-06-08: 20; 2026-06-15: 21 | 61 | 61 | 212-25 | 0
Vertiv Tank 90 | 2026-07-27 | 213-25 | 61 |  |  |  | 0 | 0% | 2026-06-08: 20; 2026-06-15: 20; 2026-06-22: 21 | 61 | 61 | 213-25 | 0
Vertiv Tank 91 | 2026-07-27 | 214-25 | 61 |  |  |  | 0 | 0% | 2026-06-08: 20; 2026-06-15: 20; 2026-06-22: 21 | 61 | 61 | 214-25 | 0
Vertiv Tank 92 | 2026-07-27 | 215-25 | 61 |  |  |  | 0 | 0% | 2026-06-08: 20; 2026-06-15: 20; 2026-06-22: 21 | 61 | 61 | 215-25 | 0
Vertiv Tank 93 | 2026-07-27 | 216-25 | 61 |  |  |  | 0 | 0% | 2026-06-08: 20; 2026-06-15: 20; 2026-06-22: 21 | 61 | 61 | 216-25 | 0
Vertiv Tank 94 | 2026-07-27 | 217-25 | 61 |  |  |  | 0 | 0% | 2026-06-08: 20; 2026-06-15: 20; 2026-06-22: 21 | 61 | 61 | 217-25 | 0
Vertiv Tank 95 | 2026-07-27 | 218-25 | 61 |  |  |  | 0 | 0% | 2026-06-15: 20; 2026-06-22: 20; 2026-06-29: 21 | 61 | 61 | 218-25 | 0
Vertiv Tank 96 | 2026-07-27 | 219-25 | 61 |  |  |  | 0 | 0% | 2026-06-15: 20; 2026-06-22: 20; 2026-06-29: 21 | 61 | 61 | 219-25 | 0
Vertiv Tank 97 | 2026-07-27 | 220-25 | 61 |  |  |  | 0 | 0% | 2026-06-15: 20; 2026-06-22: 20; 2026-06-29: 21 | 61 | 61 | 220-25 | 0
Vertiv Tank 98 | 2026-07-27 | 221-25 | 61 |  |  |  | 0 | 0% | 2026-06-15: 20; 2026-06-22: 20; 2026-06-29: 21 | 61 | 61 | 221-25 | 0
Vertiv Tank 99 | 2026-07-27 | 222-25 | 61 |  |  |  | 0 | 0% | 2026-06-15: 20; 2026-06-22: 20; 2026-06-29: 21 | 61 | 61 | 222-25 | 0
Vertiv Tank 100 | 2026-07-27 | 223-25 | 61 |  |  |  | 0 | 0% | 2026-06-22: 20; 2026-06-29: 20; 2026-07-06: 21 | 61 | 61 | 223-25 | 0
Vertiv Tank 101 | 2026-08-31 | 224-25 | 61 |  |  |  | 0 | 0% | 2026-06-22: 20; 2026-06-29: 20; 2026-07-06: 21 | 61 | 61 | 224-25 | 0
Vertiv Tank 102 | 2026-08-31 | 225-25 | 61 |  |  |  | 0 | 0% | 2026-06-22: 20; 2026-06-29: 20; 2026-07-06: 21 | 61 | 61 | 225-25 | 0
Vertiv Tank 103 | 2026-08-31 | 226-25 | 61 |  |  |  | 0 | 0% | 2026-06-22: 20; 2026-06-29: 20; 2026-07-06: 21 | 61 | 61 | 226-25 | 0
Vertiv Tank 104 | 2026-08-31 | 227-25 | 61 |  |  |  | 0 | 0% | 2026-06-22: 20; 2026-06-29: 20; 2026-07-06: 21 | 61 | 61 | 227-25 | 0
Vertiv Tank 105 | 2026-08-31 | 228-25 | 61 |  |  |  | 0 | 0% | 2026-06-29: 20; 2026-07-06: 20; 2026-07-13: 21 | 61 | 61 | 228-25 | 0
Vertiv Tank 106 | 2026-08-31 | 229-25 | 61 |  |  |  | 0 | 0% | 2026-06-29: 20; 2026-07-06: 20; 2026-07-13: 21 | 61 | 61 | 229-25 | 0
Vertiv Tank 107 | 2026-08-31 | 230-25 | 61 |  |  |  | 0 | 0% | 2026-06-29: 20; 2026-07-06: 20; 2026-07-13: 21 | 61 | 61 | 230-25 | 0
Vertiv Tank 108 | 2026-08-31 | 231-25 | 61 |  |  |  | 0 | 0% | 2026-06-29: 20; 2026-07-06: 20; 2026-07-13: 21 | 61 | 61 | 231-25 | 0
Vertiv Tank 109 | 2026-08-31 | 232-25 | 61 |  |  |  | 0 | 0% | 2026-06-29: 20; 2026-07-06: 20; 2026-07-13: 21 | 61 | 61 | 232-25 | 0
Vertiv Tank 110 | 2026-08-31 | 233-25 | 61 |  |  |  | 0 | 0% | 2026-07-13: 20; 2026-07-20: 20; 2026-07-27: 21 | 61 | 61 | 233-25 | 0
Vertiv Tank 111 | 2026-08-31 | 234-25 | 61 |  |  |  | 0 | 0% | 2026-07-13: 20; 2026-07-20: 20; 2026-07-27: 21 | 61 | 61 | 234-25 | 0
Vertiv Tank 112 | 2026-08-31 | 235-25 | 61 |  |  |  | 0 | 0% | 2026-07-13: 20; 2026-07-20: 20; 2026-07-27: 21 | 61 | 61 | 235-25 | 0
Vertiv Tank 113 | 2026-08-31 | 236-25 | 61 |  |  |  | 0 | 0% | 2026-07-13: 20; 2026-07-20: 20; 2026-07-27: 21 | 61 | 61 | 236-25 | 0
Vertiv Tank 114 | 2026-08-31 | 237-25 | 61 |  |  |  | 0 | 0% | 2026-07-13: 20; 2026-07-20: 20; 2026-07-27: 21 | 61 | 61 | 237-25 | 0
Vertiv Tank 115 | 2026-08-31 | 238-25 | 61 |  |  |  | 0 | 0% | 2026-07-20: 20; 2026-07-27: 20; 2026-08-03: 21 | 61 | 61 | 238-25 | 0
Vertiv Tank 116 | 2026-08-31 | 239-25 | 61 |  |  |  | 0 | 0% | 2026-07-20: 20; 2026-07-27: 20; 2026-08-03: 21 | 61 | 61 | 239-25 | 0
Vertiv Tank 117 | 2026-08-31 | 240-25 | 61 |  |  |  | 0 | 0% | 2026-07-20: 20; 2026-07-27: 20; 2026-08-03: 21 | 61 | 61 | 240-25 | 0
Vertiv Tank 118 | 2026-08-31 | 241-25 | 61 |  |  |  | 0 | 0% | 2026-07-20: 20; 2026-07-27: 20; 2026-08-03: 21 | 61 | 61 | 241-25 | 0
Vertiv Tank 119 | 2026-08-31 | 242-25 | 61 |  |  |  | 0 | 0% | 2026-07-20: 20; 2026-07-27: 20; 2026-08-03: 21 | 61 | 61 | 242-25 | 0
Vertiv Tank 120 | 2026-08-31 | 243-25 | 61 |  |  |  | 0 | 0% | 2026-07-27: 20; 2026-08-03: 20; 2026-08-10: 21 | 61 | 61 | 243-25 | 0
Vertiv Tank 121 | 2026-08-31 | 244-25 | 61 |  |  |  | 0 | 0% | 2026-07-27: 20; 2026-08-03: 20; 2026-08-10: 21 | 61 | 61 | 244-25 | 0
Vertiv Tank 122 | 2026-08-31 | 245-25 | 61 |  |  |  | 0 | 0% | 2026-07-27: 20; 2026-08-03: 20; 2026-08-10: 21 | 61 | 61 | 245-25 | 0
Vertiv Tank 123 | 2026-08-31 | 246-25 | 61 |  |  |  | 0 | 0% | 2026-07-27: 20; 2026-08-03: 20; 2026-08-10: 21 | 61 | 61 | 246-25 | 0
Vertiv Tank 124 | 2026-08-31 | 247-25 | 61 |  |  |  | 0 | 0% | 2026-07-27: 20; 2026-08-03: 20; 2026-08-10: 21 | 61 | 61 | 247-25 | 0
Vertiv Tank 125 | 2026-08-31 | 248-25 | 61 |  |  |  | 0 | 0% | 2026-08-03: 20; 2026-08-10: 20; 2026-08-17: 21 | 61 | 61 | 248-25 | 0
Vertiv Tank 126 | 2026-08-31 | 249-25 | 61 |  |  |  | 0 | 0% | 2026-08-03: 20; 2026-08-10: 20; 2026-08-17: 21 | 61 | 61 | 249-25 | 0
Vertiv Tank 127 | 2026-08-31 | 250-25 | 61 |  |  |  | 0 | 0% | 2026-08-03: 20; 2026-08-10: 20; 2026-08-17: 21 | 61 | 61 | 250-25 | 0
Vertiv Tank 128 | 2026-08-31 | 251-25 | 61 |  |  |  | 0 | 0% | 2026-08-03: 20; 2026-08-10: 20; 2026-08-17: 21 | 61 | 61 | 251-25 | 0
Vertiv Tank 129 | 2026-11-02 | 252-25 | 61 |  |  |  | 0 | 0% | 2026-08-03: 20; 2026-08-10: 20; 2026-08-17: 21 | 61 | 61 | 252-25 | 0
Vertiv Tank 130 | 2026-11-02 | 253-25 | 61 |  |  |  | 0 | 0% | 2026-08-10: 20; 2026-08-17: 20; 2026-08-24: 21 | 61 | 61 | 253-25 | 0
Vertiv Tank 131 | 2026-11-02 | 254-25 | 61 |  |  |  | 0 | 0% | 2026-08-10: 20; 2026-08-17: 20; 2026-08-24: 21 | 61 | 61 | 254-25 | 0
Vertiv Tank 132 | 2026-11-02 | 255-25 | 61 |  |  |  | 0 | 0% | 2026-08-10: 20; 2026-08-17: 20; 2026-08-24: 21 | 61 | 61 | 255-25 | 0
Vertiv Tank 133 | 2026-11-02 | 256-25 | 61 |  |  |  | 0 | 0% | 2026-08-10: 20; 2026-08-17: 20; 2026-08-24: 21 | 61 | 61 | 256-25 | 0
Vertiv Tank 134 | 2026-11-02 | 257-25 | 61 |  |  |  | 0 | 0% | 2026-08-10: 20; 2026-08-17: 20; 2026-08-24: 21 | 61 | 61 | 257-25 | 0
Vertiv Tank 135 | 2026-11-02 | 258-25 | 61 |  |  |  | 0 | 0% | 2026-08-17: 20; 2026-08-24: 20; 2026-08-31: 21 | 61 | 61 | 258-25 | 0
Vertiv Tank 136 | 2026-11-02 | 259-25 | 61 |  |  |  | 0 | 0% | 2026-08-17: 20; 2026-08-24: 20; 2026-08-31: 21 | 61 | 61 | 259-25 | 0
Vertiv Tank 137 | 2026-11-02 | 260-25 | 61 |  |  |  | 0 | 0% | 2026-08-17: 20; 2026-08-24: 20; 2026-08-31: 21 | 61 | 61 | 260-25 | 0
Vertiv Tank 138 | 2026-11-02 | 261-25 | 61 |  |  |  | 0 | 0% | 2026-08-17: 20; 2026-08-24: 20; 2026-08-31: 21 | 61 | 61 | 261-25 | 0
Vertiv Tank 139 | 2026-11-02 | 262-25 | 61 |  |  |  | 0 | 0% | 2026-08-17: 20; 2026-08-24: 20; 2026-08-31: 21 | 61 | 61 | 262-25 | 0
Vertiv Tank 140 | 2026-11-02 | 263-25 | 61 |  |  |  | 0 | 0% | 2026-08-24: 20; 2026-08-31: 20; 2026-09-07: 21 | 61 | 61 | 263-25 | 0
Vertiv Tank 141 | 2026-11-02 | 264-25 | 61 |  |  |  | 0 | 0% | 2026-08-24: 20; 2026-08-31: 20; 2026-09-07: 21 | 61 | 61 | 264-25 | 0
Vertiv Tank 142 | 2026-11-02 | 265-25 | 61 |  |  |  | 0 | 0% | 2026-08-24: 20; 2026-08-31: 20; 2026-09-07: 21 | 61 | 61 | 265-25 | 0
Vertiv Tank 143 | 2026-11-02 | 266-25 | 61 |  |  |  | 0 | 0% | 2026-08-24: 20; 2026-08-31: 20; 2026-09-07: 21 | 61 | 61 | 266-25 | 0
Vertiv Tank 144 | 2026-11-02 | 267-25 | 61 |  |  |  | 0 | 0% | 2026-08-24: 20; 2026-08-31: 20; 2026-09-07: 21 | 61 | 61 | 267-25 | 0
Vertiv Tank 145 | 2026-11-02 | 268-25 | 61 |  |  |  | 0 | 0% | 2026-08-31: 20; 2026-09-07: 20; 2026-09-14: 21 | 61 | 61 | 268-25 | 0
Vertiv Tank 146 | 2026-11-02 | 269-25 | 61 |  |  |  | 0 | 0% | 2026-08-31: 20; 2026-09-07: 20; 2026-09-14: 21 | 61 | 61 | 269-25 | 0
Vertiv Tank 147 | 2026-11-02 | 270-25 | 61 |  |  |  | 0 | 0% | 2026-08-31: 20; 2026-09-07: 20; 2026-09-14: 21 | 61 | 61 | 270-25 | 0
Vertiv Tank 148 | 2026-11-02 | 271-25 | 61 |  |  |  | 0 | 0% | 2026-08-31: 20; 2026-09-07: 20; 2026-09-14: 21 | 61 | 61 | 271-25 | 0
Vertiv Tank 149 | 2026-11-02 | 272-25 | 61 |  |  |  | 0 | 0% | 2026-08-31: 20; 2026-09-07: 20; 2026-09-14: 21 | 61 | 61 | 272-25 | 0
Vertiv Tank 150 | 2026-11-02 | 273-25 | 61 |  |  |  | 0 | 0% | 2026-09-14: 20; 2026-09-21: 20; 2026-09-28: 21 | 61 | 61 | 273-25 | 0
Vertiv Tank 151 | 2026-11-02 | 274-25 | 61 |  |  |  | 0 | 0% | 2026-09-14: 20; 2026-09-21: 20; 2026-09-28: 21 | 61 | 61 | 274-25 | 0
Vertiv Tank 152 | 2026-11-02 | 275-25 | 61 |  |  |  | 0 | 0% | 2026-09-14: 20; 2026-09-21: 20; 2026-09-28: 21 | 61 | 61 | 275-25 | 0
Vertiv Tank 153 | 2026-11-02 | 276-25 | 61 |  |  |  | 0 | 0% | 2026-09-14: 20; 2026-09-21: 20; 2026-09-28: 21 | 61 | 61 | 276-25 | 0
Vertiv Tank 154 | 2026-11-02 | 277-25 | 61 |  |  |  | 0 | 0% | 2026-09-14: 20; 2026-09-21: 20; 2026-09-28: 21 | 61 | 61 | 277-25 | 0
Vertiv Tank 155 | 2026-11-02 | 278-25 | 61 |  |  |  | 0 | 0% | 2026-09-21: 20; 2026-09-28: 20; 2026-10-05: 21 | 61 | 61 | 278-25 | 0
Vertiv Tank 156 | 2026-11-02 | 279-25 | 61 |  |  |  | 0 | 0% | 2026-09-21: 20; 2026-09-28: 20; 2026-10-05: 21 | 61 | 61 | 279-25 | 0
Vertiv Tank 157 | 2026-11-02 | 280-25 | 61 |  |  |  | 0 | 0% | 2026-09-21: 20; 2026-09-28: 20; 2026-10-05: 21 | 61 | 61 | 280-25 | 0
Vertiv Tank 158 | 2026-11-02 | 281-25 | 61 |  |  |  | 0 | 0% | 2026-09-21: 20; 2026-09-28: 20; 2026-10-05: 21 | 61 | 61 | 281-25 | 0
Vertiv Tank 159 | 2026-11-02 | 282-25 | 61 |  |  |  | 0 | 0% | 2026-09-21: 20; 2026-09-28: 20; 2026-10-05: 21 | 61 | 61 | 282-25 | 0
Vertiv Tank 160 | 2026-11-02 | 283-25 | 61 |  |  |  | 0 | 0% | 2026-09-28: 20; 2026-10-05: 20; 2026-10-12: 21 | 61 | 61 | 283-25 | 0
Vertiv Tank 161 | 2026-12-21 | 284-25 | 61 |  |  |  | 0 | 0% | 2026-09-28: 20; 2026-10-05: 20; 2026-10-12: 21 | 61 | 61 | 284-25 | 0
Vertiv Tank 162 | 2026-12-21 | 285-25 | 61 |  |  |  | 0 | 0% | 2026-09-28: 20; 2026-10-05: 20; 2026-10-12: 21 | 61 | 61 | 285-25 | 0
Vertiv Tank 163 | 2026-12-21 | 286-25 | 61 |  |  |  | 0 | 0% | 2026-09-28: 20; 2026-10-05: 20; 2026-10-12: 21 | 61 | 61 | 286-25 | 0
Vertiv Tank 164 | 2026-12-21 | 287-25 | 61 |  |  |  | 0 | 0% | 2026-09-28: 20; 2026-10-05: 20; 2026-10-12: 21 | 61 | 61 | 287-25 | 0
Vertiv Tank 165 | 2026-12-21 | 288-25 | 61 |  |  |  | 0 | 0% | 2026-10-05: 20; 2026-10-12: 20; 2026-10-19: 21 | 61 | 61 | 288-25 | 0
Vertiv Tank 166 | 2026-12-21 | 289-25 | 61 |  |  |  | 0 | 0% | 2026-10-05: 20; 2026-10-12: 20; 2026-10-19: 21 | 61 | 61 | 289-25 | 0
Vertiv Tank 167 | 2026-12-21 | 290-25 | 61 |  |  |  | 0 | 0% | 2026-10-05: 20; 2026-10-12: 20; 2026-10-19: 21 | 61 | 61 | 290-25 | 0
Vertiv Tank 168 | 2026-12-21 | 291-25 | 61 |  |  |  | 0 | 0% | 2026-10-05: 20; 2026-10-12: 20; 2026-10-19: 21 | 61 | 61 | 291-25 | 0
Vertiv Tank 169 | 2026-12-21 | 292-25 | 61 |  |  |  | 0 | 0% | 2026-10-05: 20; 2026-10-12: 20; 2026-10-19: 21 | 61 | 61 | 292-25 | 0
Vertiv Tank 170 | 2026-12-21 | 293-25 | 61 |  |  |  | 0 | 0% | 2026-10-12: 20; 2026-10-19: 20; 2026-10-26: 21 | 61 | 61 | 293-25 | 0
Vertiv Tank 171 | 2026-12-21 | 294-25 | 61 |  |  |  | 0 | 0% | 2026-10-12: 20; 2026-10-19: 20; 2026-10-26: 21 | 61 | 61 | 294-25 | 0
Vertiv Tank 172 | 2026-12-21 | 295-25 | 61 |  |  |  | 0 | 0% | 2026-10-12: 20; 2026-10-19: 20; 2026-10-26: 21 | 61 | 61 | 295-25 | 0
Vertiv Tank 173 | 2026-12-21 | 296-25 | 61 |  |  |  | 0 | 0% | 2026-10-12: 20; 2026-10-19: 20; 2026-10-26: 21 | 61 | 61 | 296-25 | 0
Vertiv Tank 174 | 2026-12-21 | 297-25 | 61 |  |  |  | 0 | 0% | 2026-10-12: 20; 2026-10-19: 20; 2026-10-26: 21 | 61 | 61 | 297-25 | 0
Vertiv Tank 175 | 2026-12-21 | 298-25 | 61 |  |  |  | 0 | 0% | 2026-10-19: 20; 2026-10-26: 20; 2026-11-02: 21 | 61 | 61 | 298-25 | 0
Vertiv Tank 176 | 2026-12-21 | 299-25 | 61 |  |  |  | 0 | 0% | 2026-10-19: 20; 2026-10-26: 20; 2026-11-02: 21 | 61 | 61 | 299-25 | 0
Vertiv Tank 177 | 2026-12-21 | 300-25 | 61 |  |  |  | 0 | 0% | 2026-10-19: 20; 2026-10-26: 20; 2026-11-02: 21 | 61 | 61 | 300-25 | 0
Vertiv Tank 178 | 2026-12-21 | 301-25 | 61 |  |  |  | 0 | 0% | 2026-10-19: 20; 2026-10-26: 20; 2026-11-02: 21 | 61 | 61 | 301-25 | 0
Vertiv Tank 179 | 2026-12-21 | 302-25 | 61 |  |  |  | 0 | 0% | 2026-10-19: 20; 2026-10-26: 20; 2026-11-02: 21 | 61 | 61 | 302-25 | 0
Vertiv Tank 180 | 2026-12-21 | 303-25 | 61 |  |  |  | 0 | 0% | 2026-10-26: 20; 2026-11-02: 20; 2026-11-09: 21 | 61 | 61 | 303-25 | 0
Vertiv Tank 181 | 2026-12-21 | 304-25 | 61 |  |  |  | 0 | 0% | 2026-10-26: 20; 2026-11-02: 20; 2026-11-09: 21 | 61 | 61 | 304-25 | 0
Vertiv Tank 182 | 2026-12-21 | 305-25 | 61 |  |  |  | 0 | 0% | 2026-10-26: 20; 2026-11-02: 20; 2026-11-09: 21 | 61 | 61 | 305-25 | 0
Vertiv Tank 183 | 2026-12-21 | 306-25 | 61 |  |  |  | 0 | 0% | 2026-10-26: 20; 2026-11-02: 20; 2026-11-09: 21 | 61 | 61 | 306-25 | 0
Vertiv Tank 184 | 2026-12-21 | 307-25 | 61 |  |  |  | 0 | 0% | 2026-10-26: 20; 2026-11-02: 20; 2026-11-09: 21 | 61 | 61 | 307-25 | 0
Vertiv Tank 185 | 2026-12-21 | 308-25 | 61 |  |  |  | 0 | 0% | 2026-11-02: 20; 2026-11-09: 20; 2026-11-16: 21 | 61 | 61 | 308-25 | 0
Vertiv Tank 186 | 2026-12-21 | 309-25 | 61 |  |  |  | 0 | 0% | 2026-11-02: 20; 2026-11-09: 20; 2026-11-16: 21 | 61 | 61 | 309-25 | 0
Vertiv Tank 187 | 2026-12-21 | 310-25 | 61 |  |  |  | 0 | 0% | 2026-11-02: 20; 2026-11-09: 20; 2026-11-16: 21 | 61 | 61 | 310-25 | 0
Vertiv Tank 188 | 2026-12-21 | 311-25 | 61 |  |  |  | 0 | 0% | 2026-11-02: 20; 2026-11-09: 20; 2026-11-16: 21 | 61 | 61 | 311-25 | 0
Vertiv Tank 189 | 2027-01-25 | 312-25 | 61 |  |  |  | 0 | 0% | 2026-11-02: 20; 2026-11-09: 20; 2026-11-16: 21 | 61 | 61 | 312-25 | 0
Vertiv Tank 190 | 2027-01-25 | 313-25 | 61 |  |  |  | 0 | 0% | 2026-11-09: 20; 2026-11-16: 20; 2026-11-23: 21 | 61 | 61 | 313-25 | 0
Vertiv Tank 191 | 2027-01-25 | 314-25 | 61 |  |  |  | 0 | 0% | 2026-11-09: 20; 2026-11-16: 20; 2026-11-23: 21 | 61 | 61 | 314-25 | 0
Vertiv Tank 192 | 2027-01-25 | 315-25 | 61 |  |  |  | 0 | 0% | 2026-11-09: 20; 2026-11-16: 20; 2026-11-23: 21 | 61 | 61 | 315-25 | 0
Vertiv Tank 193 | 2027-01-25 | 316-25 | 61 |  |  |  | 0 | 0% | 2026-11-09: 20; 2026-11-16: 20; 2026-11-23: 21 | 61 | 61 | 316-25 | 0
Vertiv Tank 194 | 2027-01-25 | 317-25 | 61 |  |  |  | 0 | 0% | 2026-11-09: 20; 2026-11-16: 20; 2026-11-23: 21 | 61 | 61 | 317-25 | 0
Vertiv Tank 195 | 2027-01-25 | 318-25 | 61 |  |  |  | 0 | 0% | 2026-11-16: 20; 2026-11-23: 20; 2026-11-30: 21 | 61 | 61 | 318-25 | 0
Vertiv Tank 196 | 2027-01-25 | 319-25 | 61 |  |  |  | 0 | 0% | 2026-11-16: 20; 2026-11-23: 20; 2026-11-30: 21 | 61 | 61 | 319-25 | 0
Vertiv Tank 197 | 2027-01-25 | 320-25 | 61 |  |  |  | 0 | 0% | 2026-11-16: 20; 2026-11-23: 20; 2026-11-30: 21 | 61 | 61 | 320-25 | 0
Vertiv Tank 198 | 2027-01-25 | 321-25 | 61 |  |  |  | 0 | 0% | 2026-11-16: 20; 2026-11-23: 20; 2026-11-30: 21 | 61 | 61 | 321-25 | 0
Vertiv Tank 199 | 2027-01-25 | 322-25 | 61 |  |  |  | 0 | 0% | 2026-11-16: 20; 2026-11-23: 20; 2026-11-30: 21 | 61 | 61 | 322-25 | 0
Vertiv Tank 200 | 2027-01-25 | 323-25 | 61 |  |  |  | 0 | 0% | 2026-11-30: 20; 2026-12-07: 20; 2026-12-14: 21 | 61 | 61 | 323-25 | 0
Vertiv Tank 201 | 2027-01-25 | 324-25 | 61 |  |  |  | 0 | 0% | 2026-11-30: 20; 2026-12-07: 20; 2026-12-14: 21 | 61 | 61 | 324-25 | 0
Vertiv Tank 202 | 2027-01-25 | 325-25 | 61 |  |  |  | 0 | 0% | 2026-11-30: 20; 2026-12-07: 20; 2026-12-14: 21 | 61 | 61 | 325-25 | 0
Vertiv Tank 203 | 2027-01-25 | 326-25 | 61 |  |  |  | 0 | 0% | 2026-11-30: 20; 2026-12-07: 20; 2026-12-14: 21 | 61 | 61 | 326-25 | 0
Vertiv Tank 204 | 2027-01-25 | 327-25 | 61 |  |  |  | 0 | 0% | 2026-11-30: 20; 2026-12-07: 20; 2026-12-14: 21 | 61 | 61 | 327-25 | 0
Vertiv Tank 205 | 2027-01-25 | 328-25 | 61 |  |  |  | 0 | 0% | 2026-12-07: 20; 2026-12-14: 20; 2026-12-21: 21 | 61 | 61 | 328-25 | 0
Vertiv Tank 206 | 2027-01-25 | 329-25 | 61 |  |  |  | 0 | 0% | 2026-12-07: 20; 2026-12-14: 20; 2026-12-21: 21 | 61 | 61 | 329-25 | 0
Vertiv Tank 207 | 2027-01-25 | 330-25 | 61 |  |  |  | 0 | 0% | 2026-12-07: 20; 2026-12-14: 20; 2026-12-21: 21 | 61 | 61 | 330-25 | 0
Vertiv Tank 208 | 2027-01-25 | 331-25 | 61 |  |  |  | 0 | 0% | 2026-12-07: 20; 2026-12-14: 20; 2026-12-21: 21 | 61 | 61 | 331-25 | 0
Vertiv Tank 209 | 2027-01-25 | 332-25 | 61 |  |  |  | 0 | 0% | 2026-12-07: 20; 2026-12-14: 20; 2026-12-21: 21 | 61 | 61 | 332-25 | 0
Vertiv Tank 210 | 2027-01-25 | 333-25 | 61 |  |  |  | 0 | 0% | 2026-12-14: 20; 2026-12-21: 20; 2026-12-28: 21 | 61 | 61 | 333-25 | 0
Vertiv Tank 211 | 2027-01-25 | 334-25 | 61 |  |  |  | 0 | 0% | 2026-12-14: 20; 2026-12-21: 20; 2026-12-28: 21 | 61 | 61 | 334-25 | 0
Vertiv Tank 212 | 2027-01-25 | 335-25 | 61 |  |  |  | 0 | 0% | 2026-12-14: 20; 2026-12-21: 20; 2026-12-28: 21 | 61 | 61 | 335-25 | 0
Vertiv Tank 213 | 2027-02-08 | 336-25 | 61 |  |  |  | 0 | 0% | 2026-12-14: 20; 2026-12-21: 20; 2026-12-28: 21 | 61 | 61 | 336-25 | 0
Vertiv Tank 214 | 2027-02-08 | 337-25 | 61 |  |  |  | 0 | 0% | 2026-12-14: 20; 2026-12-21: 20; 2026-12-28: 21 | 61 | 61 | 337-25 | 0
Vertiv Tank 215 | 2027-02-08 | 338-25 | 61 |  |  |  | 0 | 0% | 2026-12-21: 20; 2026-12-28: 20; 2027-01-04: 21 | 61 | 61 | 338-25 | 0
Vertiv Tank 216 | 2027-02-08 | 339-25 | 61 |  |  |  | 0 | 0% | 2026-12-21: 20; 2026-12-28: 20; 2027-01-04: 21 | 61 | 61 | 339-25 | 0
Vertiv Tank 217 | 2027-02-08 | 340-25 | 61 |  |  |  | 0 | 0% | 2026-12-21: 20; 2026-12-28: 20; 2027-01-04: 21 | 61 | 61 | 340-25 | 0
Vertiv Tank 218 | 2027-02-08 | 341-25 | 61 |  |  |  | 0 | 0% | 2026-12-21: 20; 2026-12-28: 20; 2027-01-04: 21 | 61 | 61 | 341-25 | 0
Vertiv Tank 219 | 2027-02-08 | 342-25 | 61 |  |  |  | 0 | 0% | 2026-12-21: 20; 2026-12-28: 20; 2027-01-04: 21 | 61 | 61 | 342-25 | 0
Vertiv Tank 220 | 2027-02-08 | 343-25 | 61 |  |  |  | 0 | 0% | 2027-01-04: 20; 2027-01-11: 20; 2027-01-18: 21 | 61 | 61 | 343-25 | 0
Vertiv Tank 221 | 2027-02-08 | 344-25 | 61 |  |  |  | 0 | 0% | 2027-01-04: 20; 2027-01-11: 20; 2027-01-18: 21 | 61 | 61 | 344-25 | 0
Vertiv Tank 222 | 2027-02-08 | 345-25 | 61 |  |  |  | 0 | 0% | 2027-01-04: 20; 2027-01-11: 20; 2027-01-18: 21 | 61 | 61 | 345-25 | 0
Vertiv Tank 223 | 2027-02-08 | 346-25 | 61 |  |  |  | 0 | 0% | 2027-01-04: 20; 2027-01-11: 20; 2027-01-18: 21 | 61 | 61 | 346-25 | 0
Vertiv Tank 224 | 2027-02-08 | 347-25 | 61 |  |  |  | 0 | 0% | 2027-01-04: 20; 2027-01-11: 20; 2027-01-18: 21 | 61 | 61 | 347-25 | 0
Work Order | [6 empty] | 0 | [60 empty] | 0 | 0 | 0 | 0
|  |  |  | TOT | 0 | 0 | 0 | PRO | 0 | 0 | 0 | 140 | 260 | 367 | 346 | 325 | 326 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 205 | 205 | 200 | 305 | 305 | 305 | 205 | 205 | 200 | 305 | 305 | 305 | 305 | 305 | 305 | 205 | 205 | 200 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 205 | 205 | 200 | 305 | 305 | 205 | 205 | 100 | 105 | 0 | 0 | 0 | 0 | 0 | 13542
|  |  |  | PCT | 0% | 0% |  | PCT | 0% | 0% | 0% | 40% | 74.29% | 104.9% | 98.86% | 92.86% | 93.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 73.21% | 58.57% | 57.14% | 87.14% | 87.14% | 87.14% | 73.21% | 58.57% | 57.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 73.21% | 58.57% | 57.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 73.21% | 58.57% | 57.14% | 87.14% | 87.14% | 73.21% | 58.57% | 28.57% | 30% | 0% | 0% | 0% | 0% | 0%
|  |  |  | BAL | 350 | 350 |  | BAL | 350 | 350 | 350 | 210 | 90 | -17 | 4 | 25 | 24 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 75 | 145 | 150 | 45 | 45 | 45 | 75 | 145 | 150 | 45 | 45 | 45 | 45 | 45 | 45 | 75 | 145 | 150 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 75 | 145 | 150 | 45 | 45 | 75 | 145 | 250 | 245 | 350 | 350 | 350 | 350 | 350 | 6636
| DUE | JOB # | QTE | PRE | PLAN | ACT | SUB | SUB% | [59 empty] | REQ | BAL | JOB # | time axis 2026-01-12 to 2027-02-22
|  |  |  | TOT | 350 | 350 |  | PROJ | 0 | 0 | 0 | 140 | 260 | 367 | 346 | 325 | 326 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 205 | 205 | 200 | 305 | 305 | 305 | 205 | 205 | 200 | 305 | 305 | 305 | 305 | 305 | 305 | 205 | 205 | 200 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 305 | 205 | 205 | 200 | 305 | 305 | 205 | 205 | 100 | 105 | 0 | 0 | 0 | 0 | 0 | 13664
| 48 HRS | 40 HRS |  | PCT |  |  |  | PCT | 0% | 0% | 0% | 40% | 74.29% | 104.9% | 98.86% | 92.86% | 93.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 73.21% | 58.57% | 57.14% | 87.14% | 87.14% | 87.14% | 73.21% | 58.57% | 57.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 73.21% | 58.57% | 57.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 87.14% | 73.21% | 58.57% | 57.14% | 87.14% | 87.14% | 73.21% | 58.57% | 28.57% | 30% | 0% | 0% | 0% | 0% | 0%
BACKLOG | 40.6667 | 48.8 |  | BAL |  |  |  | BAL | 350 | 350 | 350 | 210 | 90 | -17 | 4 | 25 | 24 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 75 | 145 | 150 | 45 | 45 | 45 | 75 | 145 | 150 | 45 | 45 | 45 | 45 | 45 | 45 | 75 | 145 | 150 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 75 | 145 | 150 | 45 | 45 | 75 | 145 | 250 | 245 | 350 | 350 | 350 | 350 | 350
Pre Fab
Plate roller for new production |  | 1
welder / fabricator 1 |  | 1
Fabrication
Shelbi Foltyn |  | 1
welder / fabricator 2 |  | 1
welder / fabricator 3 |  | 1
welder / fabricator 4 |  | 1
Clean/ Test
Testing / cleaner 1 |  | 1
.
Supervision / Overhead
Supervisor Finishing Department |  | 0
Total Direct |  | 7
Total Indirect |  | 0
Total |  | 7
Office
Nick |  | 1
Rutang |  | 1
Sherri |  | 1
Chris |  | 1
Shannon |  | 1
John |  | 1
Dustin |  | 1
David |  | 1
Office |  | 8
Total Headcount |  | 15
Formulas:
ACT = [PLAN]

## Build Plan 12(4)-25
Job #: | 124-25
| Description: | BUFFER TANK 1 OF 224
Work Center | Op # | Task | Est Hours
PRE FAB | .100 | Cut nozzle pipe and clean | 2
PRE FAB | .105 | Build nozzles and weld USE COBOT FOR N1 & N2 | 4
PRE FAB | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 6
PRE FAB | .156 |  | 3
PRE FAB | .200 | Make lift lugs, ground lugs, etc. | 1
PRE FAB | .252 | Fabricate miscellaneous parts CUT (4) ANCHOR ANGLES & PUNCH BOLT HOLES | 2
PRE FAB | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks ROLL & WELD BACKING BAR | 2
PRE FAB | .300 | Wrap top and bottom heads | 1
INSPECTION | .QC3 | UT Shells
PRE FAB | .305 | Shells: bring in plate, square, trim and clean | 1
PRE FAB | .315 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM INSIDE & OUTSIDE | 3
INSPECTION | .QC4 | QC Inspection - Top/Bottom/Cones | 0
PRE FAB | .365 | Set nozzles, lift lugs, etc. in top head - tack | 1
PRE FAB | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | 3
INSPECTION | .QC4 | QC Inspection - Top/Bottom/Cones
PRE FAB | .465 | Set nozzles in bottom head - tack | 1
PRE FAB | .466 | Weld nozzles in bottom head; weld complete | 1
PRE FAB | .500 | Build skirt - fit and weld shells ROLL SKIRT SHELL & WELD LONG SEAM INSIDE & OUTSIDE | 2
FIT | .530 | Build skirt - fit anchors / gussets | 1
FIT | .545 | Weld skirt anchors, gussets, nozzles, manways, etc. | 1
INSPECTION | .OI1 | ASME Hold Point
FIT | .600 | Fit bottom head to shell AND WELD INSIDE | 4
FIT | .625 | Install baffles and weld | 6
FIT | .630 | Install internals - wear plates, rings, clips, etc. FIT & WELD BACKING BAR TO SHELL | 3
INSPECTION | .QC5 | QC Inspection - Internal
FIT | .640 | Fit top head to shell - tack | 1
FIT | .645 | Weld all outside seams | 2
MOVE TANK | .800 | Move tank to detail rolls | 1
FIT | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT & WELD TO BOTTOM HEAD | 4
FIT | .725 | Set nozzles in shell - tack | 1
FIT | .726 | Weld shell nozzles, manways, etc. SET & WELD NOZZLES BEFORE INSTALLING TOP HEADS | 3
FINISHING | .765 | Install name tag | 1
FIT | .770 | Inspect tank, make repairs, get QC inspector | 1
INSPECTION | .QC6 | QC Inspection - Fabrication
INSPECTION | .OI2 | ASME Inspection Internal
MOVE TANK | .801 | Move to shop test area | 1
FINISHING | .910 | Test tank | 4
INSPECTION | .QC7 | QC Inspection - Test
INSPECTION | .OI3 | ASME Inspection Test
FINISHING | .920 | Clean tank complete CLEAN INSIDE BEFORE INSTALLING TOP HEAD | 5
INSPECTION | .QC8 | QC Inspection - Clean
FINISHING | .940 | Prepare tank for shipment | 1
INSPECTION | .QC95 | QC Inspection - Final & Loose Items
SHIPPING | .960 | Load on truck | 1
74

## Build Plan 12(5)-25
Job #: | 125-25
| Description: | BUFFER TANK 1 OF 224
Work Center | Op # | Task | Est Hours
PRE FAB | .100 | Cut nozzle pipe and clean | 2
PRE FAB | .105 | Build nozzles and weld USE COBOT FOR N1 & N2 | 4
PRE FAB | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 6
PRE FAB | .156 |  | 3
PRE FAB | .200 | Make lift lugs, ground lugs, etc. | 1
PRE FAB | .252 | Fabricate miscellaneous parts CUT (4) ANCHOR ANGLES & PUNCH BOLT HOLES | 2
PRE FAB | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks ROLL & WELD BACKING BAR | 2
PRE FAB | .300 | Wrap top and bottom heads | 1
INSPECTION | .QC3 | UT Shells
PRE FAB | .305 | Shells: bring in plate, square, trim and clean | 1
PRE FAB | .315 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM INSIDE & OUTSIDE | 3
INSPECTION | .QC4 | QC Inspection - Top/Bottom/Cones | 0
PRE FAB | .365 | Set nozzles, lift lugs, etc. in top head - tack | 1
PRE FAB | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | 3
INSPECTION | .QC4 | QC Inspection - Top/Bottom/Cones
PRE FAB | .465 | Set nozzles in bottom head - tack | 1
PRE FAB | .466 | Weld nozzles in bottom head; weld complete | 1
PRE FAB | .500 | Build skirt - fit and weld shells ROLL SKIRT SHELL & WELD LONG SEAM INSIDE & OUTSIDE | 2
FIT | .530 | Build skirt - fit anchors / gussets | 1
FIT | .545 | Weld skirt anchors, gussets, nozzles, manways, etc. | 1
INSPECTION | .OI1 | ASME Hold Point
FIT | .600 | Fit bottom head to shell AND WELD INSIDE | 4
FIT | .625 | Install baffles and weld | 6
FIT | .630 | Install internals - wear plates, rings, clips, etc. FIT & WELD BACKING BAR TO SHELL | 3
INSPECTION | .QC5 | QC Inspection - Internal
FIT | .640 | Fit top head to shell - tack | 1
FIT | .645 | Weld all outside seams | 2
MOVE TANK | .800 | Move tank to detail rolls | 1
FIT | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT & WELD TO BOTTOM HEAD | 4
FIT | .725 | Set nozzles in shell - tack | 1
FIT | .726 | Weld shell nozzles, manways, etc. SET & WELD NOZZLES BEFORE INSTALLING TOP HEADS | 3
FINISHING | .765 | Install name tag | 1
FIT | .770 | Inspect tank, make repairs, get QC inspector | 1
INSPECTION | .QC6 | QC Inspection - Fabrication
INSPECTION | .OI2 | ASME Inspection Internal
MOVE TANK | .801 | Move to shop test area | 1
FINISHING | .910 | Test tank | 4
INSPECTION | .QC7 | QC Inspection - Test
INSPECTION | .OI3 | ASME Inspection Test
FINISHING | .920 | Clean tank complete CLEAN INSIDE BEFORE INSTALLING TOP HEAD | 5
INSPECTION | .QC8 | QC Inspection - Clean
FINISHING | .940 | Prepare tank for shipment | 1
INSPECTION | .QC95 | QC Inspection - Final & Loose Items
SHIPPING | .960 | Load on truck | 1
74

## Build Plan 12(6)-25
Job #: | 124-25
| Description: | BUFFER TANK 1 OF 224
Work Center | Op # | Task | Est Hours
PRE FAB | .100 | Cut nozzle pipe and clean | 2
PRE FAB | .105 | Build nozzles and weld USE COBOT FOR N1 & N2 | 4
PRE FAB | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 6
PRE FAB | .156 |  | 3
PRE FAB | .200 | Make lift lugs, ground lugs, etc. | 1
PRE FAB | .252 | Fabricate miscellaneous parts CUT (4) ANCHOR ANGLES & PUNCH BOLT HOLES | 2
PRE FAB | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks ROLL & WELD BACKING BAR | 2
PRE FAB | .300 | Wrap top and bottom heads | 1
INSPECTION | .QC3 | UT Shells
PRE FAB | .305 | Shells: bring in plate, square, trim and clean | 1
PRE FAB | .315 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM INSIDE & OUTSIDE | 3
INSPECTION | .QC4 | QC Inspection - Top/Bottom/Cones | 0
PRE FAB | .365 | Set nozzles, lift lugs, etc. in top head - tack | 1
PRE FAB | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | 3
INSPECTION | .QC4 | QC Inspection - Top/Bottom/Cones
PRE FAB | .465 | Set nozzles in bottom head - tack | 1
PRE FAB | .466 | Weld nozzles in bottom head; weld complete | 1
PRE FAB | .500 | Build skirt - fit and weld shells ROLL SKIRT SHELL & WELD LONG SEAM INSIDE & OUTSIDE | 2
FIT | .530 | Build skirt - fit anchors / gussets | 1
FIT | .545 | Weld skirt anchors, gussets, nozzles, manways, etc. | 1
INSPECTION | .OI1 | ASME Hold Point
FIT | .600 | Fit bottom head to shell AND WELD INSIDE | 4
FIT | .625 | Install baffles and weld | 6
FIT | .630 | Install internals - wear plates, rings, clips, etc. FIT & WELD BACKING BAR TO SHELL | 3
INSPECTION | .QC5 | QC Inspection - Internal
FIT | .640 | Fit top head to shell - tack | 1
FIT | .645 | Weld all outside seams | 2
MOVE TANK | .800 | Move tank to detail rolls | 1
FIT | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT & WELD TO BOTTOM HEAD | 4
FIT | .725 | Set nozzles in shell - tack | 1
FIT | .726 | Weld shell nozzles, manways, etc. SET & WELD NOZZLES BEFORE INSTALLING TOP HEADS | 3
FINISHING | .765 | Install name tag | 1
FIT | .770 | Inspect tank, make repairs, get QC inspector | 1
INSPECTION | .QC6 | QC Inspection - Fabrication
INSPECTION | .OI2 | ASME Inspection Internal
MOVE TANK | .801 | Move to shop test area | 1
FINISHING | .910 | Test tank | 4
INSPECTION | .QC7 | QC Inspection - Test
INSPECTION | .OI3 | ASME Inspection Test
FINISHING | .920 | Clean tank complete CLEAN INSIDE BEFORE INSTALLING TOP HEAD | 5
INSPECTION | .QC8 | QC Inspection - Clean
FINISHING | .940 | Prepare tank for shipment | 1
INSPECTION | .QC95 | QC Inspection - Final & Loose Items
SHIPPING | .960 | Load on truck | 1
74

## Build Plan 12(7)-25
Job #: | 125-25
| Description: | BUFFER TANK 1 OF 224
Work Center | Op # | Task | Est Hours
PRE FAB | .100 | Cut nozzle pipe and clean | 2
PRE FAB | .105 | Build nozzles and weld USE COBOT FOR N1 & N2 | 4
PRE FAB | .155 | Burn and clean parts: lugs, supports, repads, base ring, etc. (CHECK!) | 6
PRE FAB | .156 |  | 3
PRE FAB | .200 | Make lift lugs, ground lugs, etc. | 1
PRE FAB | .252 | Fabricate miscellaneous parts CUT (4) ANCHOR ANGLES & PUNCH BOLT HOLES | 2
PRE FAB | .261 | Miscellaneous Fabrication - Braces, Mounting Plates, Cone Outlet Necks ROLL & WELD BACKING BAR | 2
PRE FAB | .300 | Wrap top and bottom heads | 1
INSPECTION | .QC3 | UT Shells
PRE FAB | .305 | Shells: bring in plate, square, trim and clean | 1
PRE FAB | .315 | Roll shells, tack and weld inside seams INCL WELD LONG SEAM INSIDE & OUTSIDE | 3
INSPECTION | .QC4 | QC Inspection - Top/Bottom/Cones | 0
PRE FAB | .365 | Set nozzles, lift lugs, etc. in top head - tack | 1
PRE FAB | .366 | Weld out top head nozzles, etc. INCL (2) LIFT LUGS | 3
INSPECTION | .QC4 | QC Inspection - Top/Bottom/Cones
PRE FAB | .465 | Set nozzles in bottom head - tack | 1
PRE FAB | .466 | Weld nozzles in bottom head; weld complete | 1
PRE FAB | .500 | Build skirt - fit and weld shells ROLL SKIRT SHELL & WELD LONG SEAM INSIDE & OUTSIDE | 2
FIT | .530 | Build skirt - fit anchors / gussets | 1
FIT | .545 | Weld skirt anchors, gussets, nozzles, manways, etc. | 1
INSPECTION | .OI1 | ASME Hold Point
FIT | .600 | Fit bottom head to shell AND WELD INSIDE | 4
FIT | .625 | Install baffles and weld | 6
FIT | .630 | Install internals - wear plates, rings, clips, etc. FIT & WELD BACKING BAR TO SHELL | 3
INSPECTION | .QC5 | QC Inspection - Internal
FIT | .640 | Fit top head to shell - tack | 1
FIT | .645 | Weld all outside seams | 2
MOVE TANK | .800 | Move tank to detail rolls | 1
FIT | .720 | Install supports - legs, lugs, anchors, saddles, skirt FIT SKIRT & WELD TO BOTTOM HEAD | 4
FIT | .725 | Set nozzles in shell - tack | 1
FIT | .726 | Weld shell nozzles, manways, etc. SET & WELD NOZZLES BEFORE INSTALLING TOP HEADS | 3
FINISHING | .765 | Install name tag | 1
FIT | .770 | Inspect tank, make repairs, get QC inspector | 1
INSPECTION | .QC6 | QC Inspection - Fabrication
INSPECTION | .OI2 | ASME Inspection Internal
MOVE TANK | .801 | Move to shop test area | 1
FINISHING | .910 | Test tank | 4
INSPECTION | .QC7 | QC Inspection - Test
INSPECTION | .OI3 | ASME Inspection Test
FINISHING | .920 | Clean tank complete CLEAN INSIDE BEFORE INSTALLING TOP HEAD | 5
INSPECTION | .QC8 | QC Inspection - Clean
FINISHING | .940 | Prepare tank for shipment | 1
INSPECTION | .QC95 | QC Inspection - Final & Loose Items
SHIPPING | .960 | Load on truck | 1
74