## Drawing Submittal
Drawing Submittal
On Track
At Risk
[5 empty] | Late |  | No Y | No Y
Job # | Customer | Rev. | Target | Actual | Days +/- | Status | Submitted | Approved
24-046 | SYMS Engineering | 4 | 1900-01-03 |  | -46069 |  | Y | y
24-047 | #N/A | #N/A | #N/A |  | #N/A |  | #N/A | #N/A
24-048 | #N/A | #N/A | #N/A |  | #N/A |  | #N/A | #N/A
25-052 | Kraton | 4 | 1900-01-03 |  | -46069 |  | Y | y
25-053 | Andritz | 0 | 2026-01-05 |  | -46 |  | N |  | Spool piece 4A-1 CERTIFIED on 8/22/25
25-054 | Chromascape | 3 | 2025-07-31 |  | -204 |  | Y | y
25-055 | Airgas | 2 | 2025-12-31 |  | -51 |  | Y | y
25-077 | Epic Systems | 3 | 2025-09-08 |  | -165 |  | Y | y
25-078 | Epic Systems | 3 | 2025-09-08 |  | -165 |  | Y | y
25-079 | Epic Systems | 3 | 2025-09-08 |  | -165 |  | Y | y
25-080 | Domtar | 2 | 2025-09-04 |  | -169 |  | Y | y
25-083 | Synthomer | 3 | 2026-02-09 |  | -11 |  | N | y
25-084 | Atlas Minerals | 4 | 1900-01-03 |  | -46069 |  | Y | y
25-085 | Noah Industrial | 2 | 2025-09-02 |  | -171 |  | Y | y
25-087 | Solvay | 2 | 2025-09-29 |  | -144 |  | Y | y
25-088 | CIL Isotopes | 2 | 2025-09-29 |  | -144 |  | Y | y
25-089 | Valmet | 2 | 2025-12-18 |  | -64 |  | Y | y |  | RS
25-090 | GAF | 1 | 2025-09-12 |  | -161 |  | Y | y
25-092 | Symrise | 3 | 2025-11-10 |  | -102 |  | Y | y
25-093 | Symrise | 3 | 2025-11-10 |  | -102 |  | Y | y
25-094 | Kimberly Clark | 2 | 2025-12-02 |  | -80 |  | Y | y
25-095 | Andritz | 3 | 2026-02-27 |  | 7 |  | Y
25-096 | Milliken | 2 | 2025-11-06 |  | -106 |  | Y | y
25-097 | Milliken | 2 | 2025-11-06 |  | -106 |  | Y | y
25-098 | Coastal Technologies | 2 | 2025-11-13 |  | -99 |  | Y | y
25-099 | Burke Industrial | 2 | 2025-11-19 |  | -93 |  | Y | y
25-101 | Harper Love | 2 | 2025-12-22 |  | -60 |  | Y | y |  | RS
25-102 | Epic Systems | 3 | 2026-02-26 |  | 6 |  | N
25-103 | Epic Systems | 3 | 2026-02-26 |  | 6 |  | N | y
25-104 | Epic Systems | 3 | 2026-02-26 |  | 6 |  | N | y
25-105 | Epic Systems | 3 | 2026-02-26 |  | 6 |  | N | y
25-106 | Epic Systems | 3 | 2026-02-26 |  | 6 |  | N
25-107 | Epic Systems | 1 | 2026-02-09 |  | -11 |  | N |  |  | Tank size confirmed on 2/9/26 | 2026-02-23
25-108 | Epic Systems | 2 | 2026-02-25 |  | 5 |  | Y
25-109 | Epic Systems | 4 | 1900-01-03 |  | -46069 |  | Y | y
25-110 | Epic Systems | 4 | 1900-01-03 |  | -46069 |  | Y
25-111 | Epic Systems | 4 | 1900-01-03 |  | -46069 |  | Y
25-112 | Epic Systems | 4 | 1900-01-03 |  | -46069 |  | Y
25-113 | Epic Systems | 3 | 2026-02-19 |  | -1 |  | Y
25-115 | Epic Systems | 3 | 2026-02-26 |  | 6 |  | N | y
25-116 | Polynt | 2 | 2026-02-19 |  | -1 |  | N
25-117 | Merrick | 3 | 2026-02-24 |  | 4 |  | Y | y
25-118 | Merrick | 3 | 2026-03-02 |  | 10 |  | Y | y
25-119 | Vertiv | 2 | 2025-12-17 |  | -65 |  | Y | y
25-121 | Kimberly Clark | 1 | 2026-02-24 |  | 4 |  | N
25-122 | Kimberly Clark | 1 | 2026-02-24 |  | 4 |  | N
25-123 | Kimberly Clark | 1 | 2026-01-29 |  | -22 |  | Y
25-356 | Synthomer | 2 | 2026-03-02 |  | 10 |  | Y |  |  | Questions answred on 2/10/26
25-357 | Sylvamo | 1 | 2026-02-18 |  | -2 |  | N
25-358 | Sylvamo | 1 | 2026-02-18 |  | -2 |  | N
26-002 | SNF | 1 | 2026-02-27 |  | 7 |  | Y
26-003 | SNF | 1 | 2026-02-27 |  | 7 |  | Y
26-004 | SNF | 1 | 2026-02-27 |  | 7 |  | Y
26-005 | US Sugar | 1 | 2026-02-18 |  | -2 |  | N |  |  | Awaiting customer input on (1) nozzle
26-014 | SNF | 1 | 2026-03-04 |  | 12 |  | Y
26-015 | SNF | 0 | 2026-03-18 |  | 26 |  | N
26-016 | SNF | 0 | 2026-03-11 |  | 19 |  | N
26-017 | SNF | 1 | 2026-03-04 |  | 12 |  | Y
26-018 | SNF | 1 | 2026-03-04 |  | 12 |  | Y
26-020 | US Sugar | 0 | 2026-03-06 |  | 14 |  | N
26-021 | US Sugar | 0 | 2026-03-06 |  | 14 |  | N
26-022 | Andritz | 0 | 2026-03-03 |  | 11 |  | N
Formulas:
Target = IF([Rev.]=0,VLOOKUP([Job #],'Date Calcs'!A:AF,8,),IF([Rev.]=1,VLOOKUP([Job #],'Date Calcs'!A:AF,10,),IF([Rev.]=2,VLOOKUP([Job #],'Date Calcs'!A:AF,12,),IF([Rev.]=3,VLOOKUP([Job #],'Date Calcs'!A:AF,14,),4))))

## Cust Dwg Return
Drawing Return From Customer
On Track
At Risk
[5 empty] | Late |  | Blanks only | Blanks only
Job # | Customer | Rev. | Target | Actual | Days +/- | Status | Returned | Approved
24-046 | SYMS Engineering | 3 | 2025-08-13 |  | -191 |  | 1 | y
25-052 | Kraton | 3 | 2025-08-05 |  | -199 |  |  | y
25-053 | Andritz |  |  |  | #VALUE! |  | FALSE
25-054 | Chromascape | 2 | 2025-07-24 |  | -211 |  |  | y
25-055 | Airgas | 1 | 2025-12-24 |  | -58 |  |  | y
25-074 | Kemira | 1 | 2025-07-29 |  | -206 |  |  | y
25-075 | Kemira | 2 | 2025-08-26 |  | -178 |  |  | y
25-076 | Irving tissue | 1 | 2025-08-26 |  | -178 |  |  | y
25-077 | Epic Systems | 2 | 2025-09-01 |  | -172 |  |  | y
25-078 | Epic Systems | 2 | 2025-09-01 |  | -172 |  |  | y
25-079 | Epic Systems | 2 | 2025-09-01 |  | -172 |  |  | y
25-080 | Domtar | 1 | 2025-08-28 |  | -176 |  |  | y
25-083 | Synthomer | 2 | 2025-11-11 |  | -101 |  | 1 | y
25-084 | Atlas Minerals | 3 | 2025-11-07 |  | -105 |  | 1 | y
25-085 | Noah Industrial | 1 | 2025-08-26 |  | -178 |  |  | y
25-087 | Solvay | 1 | 2025-09-22 |  | -151 |  |  | y
25-088 | CIL Isotopes | 1 | 2025-09-22 |  | -151 |  |  | y
25-089 | Valmet | 1 | 2025-12-11 |  | -71 |  |  | y
25-090 | GAF | 0 | 2025-09-05 |  | -168 |  |  | y
25-091 | US Sugar |  |  |  | #VALUE! |  | FALSE
25-092 | Symrise | 2 | 2025-11-03 |  | -109 |  |  | y
25-093 | Symrise | 2 | 2025-11-03 |  | -109 |  |  | y
25-094 | Kimberly Clark | 1 | 2025-11-25 |  | -87 |  |  | y
25-095 | Andritz | 2 | 2026-02-20 |  | 0
25-096 | Milliken | 1 | 2025-10-30 |  | -113 |  |  | y
25-097 | Milliken | 1 | 2025-10-30 |  | -113 |  |  | y
25-098 | Coastal Technologies | 1 | 2025-11-06 |  | -106 |  |  | y
25-099 | Burke Industrial | 1 | 2025-11-12 |  | -100 |  |  | y
25-101 | Harper Love | 1 | 2025-12-15 |  | -67 |  |  | y
25-102 | Epic Systems | 2 | 2026-02-11 |  | -9 |  | 1 | Y
25-103 | Epic Systems | 2 | 2026-02-11 |  | -9 |  | 1 | Y
25-104 | Epic Systems | 2 | 2026-02-11 |  | -9 |  | 1 | Y
25-105 | Epic Systems | 2 | 2026-02-11 |  | -9 |  | 1 | Y
25-106 | Epic Systems | 2 | 2026-02-12 |  | -8 |  | 1 | Y
25-107 | Epic Systems | 0 | 2025-12-10 |  | -72 |  | 1
25-108 | Epic Systems | 1 | 2026-02-18 |  | -2
25-109 | Epic Systems | 3 | 2026-02-06 |  | -14 |  | 1 | Y
25-110 | Epic Systems | 3 | 2026-02-06 |  | -14
25-111 | Epic Systems | 3 | 2026-02-06 |  | -14
25-112 | Epic Systems | 3 | 2026-02-06 |  | -14
25-113 | Epic Systems | 2 | 2026-02-12 |  | -8
25-114 | #N/A | #N/A | #N/A |  | #N/A |  | #N/A | #N/A
25-115 | Epic Systems | 2 | 2026-02-06 |  | -14 |  | 1 | Y
25-116 | Polynt | 1 | 2026-01-16 |  | -35 |  | 1
25-117 | Merrick | 2 | 2026-02-17 |  | -3 |  |  | y
25-118 | Merrick | 2 | 2026-02-23 |  | 3 |  |  | y
25-119 | Vertiv | 1 | 2025-12-10 |  | -72 |  |  | y
25-121 | Kimberly Clark | 0 | 2026-01-22 |  | -29 |  | 1
25-122 | Kimberly Clark | 0 | 2026-01-22 |  | -29 |  | 1
25-123 | Kimberly Clark | 0 | 2026-01-22 |  | -29
25-124 | Vertiv |  |  |  | #VALUE! |  | FALSE
25-356 | Synthomer | 1 | 2026-02-23 |  | 3
25-357 | Sylvamo | 0 | 2026-02-12 |  | -8 |  | 1
25-358 | Sylvamo | 0 | 2026-02-13 |  | -7 |  | 1
26-002 | SNF | 0 | 2026-02-20 |  | 0
26-003 | SNF | 0 | 2026-02-20 |  | 0
26-004 | SNF | 0 | 2026-02-20 |  | 0
26-005 | US Sugar | 0 | 2026-02-19 |  | -1 |  | 1
26-014 | SNF | 0 | 2026-02-25 |  | 5
26-015 | SNF |  |  |  | #VALUE! |  | FALSE
26-016 | SNF |  |  |  | #VALUE! |  | FALSE
26-017 | SNF | 0 | 2026-02-25 |  | 5
26-018 | SNF | 0 | 2026-02-25 |  | 5
26-020 | US Sugar |  |  |  | #VALUE! |  | FALSE
26-021 | US Sugar |  |  |  | #VALUE! |  | FALSE
26-022 | Andritz |  |  |  | #VALUE! |  | FALSE
Formulas:
Target = IF([Rev.]=" "," ",IF([Rev.]=0,VLOOKUP([Job #],'Date Calcs'!A:AF,9,),IF([Rev.]=1,VLOOKUP([Job #],'Date Calcs'!A:AF,11,),IF([Rev.]=2,VLOOKUP([Job #],'Date Calcs'!A:AF,13,),IF([Rev.]=3,VLOOKUP([Job #],'Date Calcs'!A:AF,15,),4)))))

## RTR v2
Shop Release Readiness
|  | Pre-Approval | [5 empty] | After Return of Approval Drawings | [21 empty] | Release to Shop By Ship Date
Job # | Customer | App. Prints |  | Long lead time |  | Prelim BOM |  | Final Calcs |  | A.I. | Cert Dwgs |  | Update BOM |  | Stock Check |  | Purch Recvd |  | Final BOM |  | Build Plan |  | Burn File |  | QC Checklist |  | Released |  | Drop Dead Date Week of | Build Plan | Days to go | QC Checklist | days to go | Burn File | days to go | All MAT. On hand | Purchase vs Release | Release to Shop | days to go | Ship Date Week Of | Difference drop dead to ship | Logistics Confirmed | Actual Ship Date | COMMENTS
24-046 | SYMS Engineering | Y | 4 | Y | -2 | Y | #VALUE! | Y | 4 |  | Y | -1 | Y | -276 | Y | -3 | Y | -269 | Y | 69 | Y | 85 | Y | 80 | Y | 94 | Y | 95 | 2026-05-21 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-16 | 35
25-053 | Andritz | Y |  | Y | 58 | Y | #VALUE! | [5 empty] | Y | -348 | Y | -173 | Y | -160 | Y | -168 | Y | -165 | Y | -139 |  |  | Y | -168 | 2026-07-27 | DONE | 0 | 2026-03-24 | 32 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-06-02 | 55
25-055 | Airgas | Y | 54 | Y | 166 | Y | #VALUE! | Y | 5 |  | Y | 0 | Y | -166 | Y | 12 |  |  | Y | 7 |  |  | Y | 40 | Y | 46 |  |  | 2026-06-17 | 2026-03-17 | 25 | DONE | 0 | DONE | 0 | 2026-03-24 | 7 | 2026-03-31 | 39 | 2026-05-26 | 22 |  |  | Head from California
25-066 | Reco | Y | 5 | Y | #VALUE! | Y | #VALUE! | Y | 5 |  | Y | 0 | Y | -237 | Y | -6 | Y | -5 | Y | -12 | Y | -17 | Y | 185 | Y | -10 | Y | 144 | 2026-03-30 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-03-09 | 21
25-067 | Reco | Y | 5 | Y | #VALUE! | Y | #VALUE! | Y | 5 |  | Y | 0 | Y | -237 | Y | -6 | Y | -5 | Y | -12 | Y | -17 | Y | 185 | Y | -10 | Y | 144 | 2026-03-30 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-03-09 | 21
25-068 | Reco | Y | 5 | Y | #VALUE! | Y | -5 | Y | 5 |  | Y | 0 | Y | -265 | Y | -6 | Y | -5 | Y | -12 | Y | -17 | Y | 185 | Y | -10 | Y | 172 | 2026-04-27 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-06 | 21
25-069 | Reco | Y | 5 | Y | #VALUE! | Y | -8 | Y | 5 |  | Y | 0 | Y | -265 | Y | -6 | Y | -5 | Y | -12 | Y | -17 | Y | 185 | Y | -10 | Y | 172 | 2026-04-27 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-06 | 21
25-070 | Reco | Y | 5 | Y | #VALUE! | Y | -1 | Y | 5 |  | Y | 0 | Y | -293 | Y | -6 | Y | -5 | Y | -12 | Y | -17 | Y | 185 | Y | -10 | Y | 181 | 2026-05-25 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-27 | 28
25-071 | Reco | Y | 5 | Y | #VALUE! | Y | -6 | Y | 5 |  | Y | 0 | Y | -293 | Y | -6 | Y | -5 | Y | -12 | Y | -17 | Y | 185 | Y | -10 | Y | 181 | 2026-05-25 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-27 | 28
25-083 | Synthomer | Y | 10 | Y | -5 | Y | -8 | Y | -92 |  | Y | -97 | Y | -273 | Y | -98 | Y | -46 | Y | -104 | Y | -91 | Y | -42 | Y | -84 | Y | -94 | 2026-05-05 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-06 | 29
25-084 | Atlas Minerals | Y | 0 | Y | -8 | Y | 3 | Y | -2 |  | Y | -7 | Y | -144 | Y | -25 | Y | -8 | Y | -20 | Y | -1 | Y | 34 | Y | 6 | Y | -4 | 2026-03-10 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-02-23 | 15
25-098 | Coastal Technologies | Y | 0 | Y | 2 | Y | 3 | Y | 4 |  | Y | -1 | Y | -129 | Y | 4 |  |  | Y | -105 | Y | 62 | Y | -45 | Y | 69 | Y | -39 | 2026-03-19 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-02-26 | 0 | DONE | 0 | 2026-03-09 | 10 |  |  | MINERAL WOOL & .024 ALUMINUM SHEET
25-099 | Burke Industrial | Y | -1 | Y | -3 | Y | 3 | Y | 5 |  | Y | 0 | Y | -104 | Y | 1 | Y | 0 | Y | -6 | Y | 58 | Y | 63 | Y | 71 | Y | 62 | 2026-02-25 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-03-09 | -12
25-101 | Harper Love | Y | -1 | Y | -7 | Y | 3 | Y | 5 |  | Y | 0 | Y | -124 | Y | -5 | Y | 50 | Y | -6 | Y | 28 | Y | 24 | Y | 35 | Y | 27 | 2026-04-13 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-05-14 | -31
25-102 | Epic Systems | Y | 0 | Y | 4 | Y | 3 | [21 empty] | 2026-07-02 | 2026-02-16 | -4 | 2026-02-16 | -4 | 2026-02-23 | 3 | 2026-02-23 | 7 | 2026-03-02 | 10 | 2026-04-27 | 66
25-103 | Epic Systems | Y | 0 | Y | 4 | Y | -36 | Y | -2 |  | Y | -7 | [16 empty] | 2026-06-25 | 2026-02-16 | -4 | 2026-02-16 | -4 | 2026-02-23 | 3 | 2026-02-23 | 7 | 2026-03-02 | 10 | 2026-04-27 | 59
25-104 | Epic Systems | Y | 0 | Y | 4 | Y | 59 | Y | -2 |  | Y | -7 | [16 empty] | 2026-06-25 | 2026-02-16 | -4 | 2026-02-16 | -4 | 2026-02-23 | 3 | 2026-02-23 | 7 | 2026-03-02 | 10 | 2026-04-27 | 59
25-105 | Epic Systems | Y | 0 | Y | 4 | Y | -7 | Y | -2 |  | Y | -7 | [16 empty] | 2026-06-25 | 2026-03-23 | 31 | 2026-03-23 | 31 | 2026-03-30 | 38 | 2026-03-30 | 7 | 2026-04-06 | 45 | 2026-06-01 | 24
25-106 | Epic Systems | Y | 0 | Y | 4 | Y | -7 | [21 empty] | 2026-07-02 | 2026-03-24 | 32 | 2026-03-24 | 32 | 2026-03-31 | 39 | 2026-03-31 | 7 | 2026-04-07 | 46 | 2026-06-02 | 30
25-107 | Epic Systems | Y | -96 | Y | -4 | Y | -3 | [21 empty] | 2026-06-15 | 2026-04-13 | 52 | 2026-04-13 | 52 | 2026-04-20 | 59 | 2026-04-20 | 7 | 2026-04-27 | 66 | 2026-06-22 | -7
25-108 | Epic Systems | Y | -1 | Y | 91 | Y | -3 | [21 empty] | 2026-06-15 | 2026-04-13 | 52 | 2026-04-13 | 52 | 2026-04-20 | 59 | 2026-04-20 | 7 | 2026-04-27 | 66 | 2026-06-22 | -7
25-109 | Epic Systems | Y | -1 | Y | -2 | Y | -18 | Y | -2 |  | Y | -7 | Y | -163 | Y | -44 | Y | -24 | Y | -50 | [8 empty] | 2026-06-25 | 2026-02-16 | -4 | 2026-02-16 | -4 | 2026-02-23 | 3 | DONE | 0 | 2026-03-02 | 10 | 2026-04-27 | 59
25-110 | Epic Systems | Y | -1 | Y | -6 | Y | -3 | [5 empty] | Y | -135 | Y | -16 | Y | 3 | Y | -11 | [8 empty] | 2026-06-05 | 2026-03-10 | 18 | 2026-03-10 | 18 | 2026-03-17 | 25 | DONE | 0 | 2026-03-24 | 32 | 2026-05-19 | 17
25-111 | Epic Systems | Y | -1 | Y | 18 | Y | -8 | [21 empty] | 2026-06-05 | 2026-03-10 | 18 | 2026-03-10 | 18 | 2026-03-17 | 25 | 2026-03-17 | 7 | 2026-03-24 | 32 | 2026-05-19 | 17
25-112 | Epic Systems | Y | -1 | Y | 18 | Y | 55 | [21 empty] | 2026-06-05 | 2026-03-11 | 19 | 2026-03-11 | 19 | 2026-03-18 | 26 | 2026-03-18 | 7 | 2026-03-25 | 33 | 2026-05-20 | 16
25-113 | Epic Systems | Y | 0 | Y | 3 | Y | 55 | [21 empty] | 2026-06-15 | 2026-03-05 | 13 | 2026-03-05 | 13 | 2026-03-12 | 20 | 2026-03-12 | 7 | 2026-03-19 | 27 | 2026-05-14 | 32
25-115 | Epic Systems | Y | -1 | Y | -2 | Y | -4 | Y | -2 |  | Y | -7 | [16 empty] | 2026-06-25 | 2026-03-05 | 13 | 2026-03-05 | 13 | 2026-03-12 | 20 | 2026-03-12 | 7 | 2026-03-19 | 27 | 2026-05-14 | 42
25-116 | Polynt | Y | 17 | Y | -8 | Y | -2 | [5 empty] | Y | -162 | Y | -43 | Y | -7 | Y | -48 | [8 empty] | 2026-06-25 | 2026-05-18 | 87 | 2026-05-18 | 87 | 2026-05-25 | 94 | DONE | 0 | 2026-06-01 | 101 | 2026-07-27 | -32
25-117 | Merrick | Y | 5 | Y | 55 | Y | -2 | Y | 6 |  | Y | 1 | Y | -137 | Y | -4 | Y | 16 | Y | -7 | Y | -11 | Y | -6 | Y | 2 | Y | -7 | 2026-06-30 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | DONE | 0 | 2026-04-06 | 85
25-118 | Merrick | Y | 5 | Y | 55 | Y | -2 | Y | 5 |  | Y | 0 |  |  |  |  | Y | 9 | Y | -10 | Y | -13 | [6 empty] | 2026-07-06 | DONE | 0 | 2026-02-16 | -4 | 2026-02-23 | 3 | DONE | 0 | 2026-03-02 | 10 | 2026-04-27 | 70
25-120 | Andritz | Y |  | Y | 55 | #REF! | #REF! | [21 empty] | 2026-06-12 | 2026-04-22 | 61 | 2026-04-22 | 61 | 2026-04-29 | 68 | 2026-04-29 | 7 | 2026-05-06 | 75 | 2026-07-08 | -26
25-121 | Kimberly Clark | Y | 7 | Y | -1 | Y | 7 | [21 empty] | 2026-06-30 | 2026-03-10 | 18 | 2026-03-10 | 18 | 2026-03-17 | 25 | 2026-03-17 | 7 | 2026-03-24 | 32 | 2026-05-19 | 42
25-122 | Kimberly Clark | Y | 7 | Y | -1 | Y | 6 | [21 empty] | 2026-06-30 | 2026-03-11 | 19 | 2026-03-11 | 19 | 2026-03-18 | 26 | 2026-03-18 | 7 | 2026-03-25 | 33 | 2026-05-20 | 41
25-123 | Kimberly Clark | Y | 7 | Y | -1 | Y | 6 | [21 empty] | 2026-06-04 | 2026-03-11 | 19 | 2026-03-11 | 19 | 2026-03-18 | 26 | 2026-03-18 | 7 | 2026-03-25 | 33 | 2026-05-20 | 15
25-356 | Synthomer | Y | 2 |  |  | Y | -1 | [21 empty] | 2026-06-15 | 2026-04-02 | 41 | 2026-04-02 | 41 | 2026-04-09 | 48 | 2026-04-09 | 7 | 2026-04-16 | 55 | 2026-06-11 | 4
25-357 | Sylvamo | Y | 2 | Y | 6 | Y | -1 | [21 empty] | 2026-06-10 | 2026-03-11 | 19 | 2026-03-11 | 19 | 2026-03-18 | 26 | 2026-03-18 | 7 | 2026-03-25 | 33 | 2026-05-20 | 21
25-358 | Sylvamo | Y | 3 | Y | 6 | Y | -4 | [21 empty] | 2026-06-10 | 2026-03-11 | 19 | 2026-03-11 | 19 | 2026-03-18 | 26 | 2026-03-18 | 7 | 2026-03-25 | 33 | 2026-05-20 | 21
26-002 | SNF | Y | 0 | Y | 3 | Y | 1 | [21 empty] | 2026-07-03 | 2026-04-21 | 60 | 2026-04-21 | 60 | 2026-04-28 | 67 | 2026-04-28 | 7 | 2026-05-05 | 74 | 2026-06-30 | 3
26-003 | SNF | Y | 0 | Y | 3 | [23 empty] | 2026-07-03 | 2026-04-21 | 60 | 2026-04-21 | 60 | 2026-04-28 | 67 | 2026-04-28 | 7 | 2026-05-05 | 74 | 2026-06-30 | 3
26-004 | SNF | Y | 0 | Y | 3 | Y | -29 | [21 empty] | 2026-07-03 | 2026-04-21 | 60 | 2026-04-21 | 60 | 2026-04-28 | 67 | 2026-04-28 | 7 | 2026-05-05 | 74 | 2026-06-30 | 3
26-005 | US Sugar | Y | -4 | Y | -4 | Y | 1 | [21 empty] | 2026-07-08 | 2026-03-18 | 26 | 2026-03-18 | 26 | 2026-03-25 | 33 | 2026-03-25 | 7 | 2026-04-01 | 40 | 2026-06-03 | 35
26-014 | SNF | Y | 2 | Y | 1 | Y | 1 | [21 empty] | 2026-06-24 | 2026-03-12 | 20 | 2026-03-12 | 20 | 2026-03-19 | 27 | 2026-03-19 | 7 | 2026-03-26 | 34 | 2026-05-28 | 27
26-015 | SNF | Y |  |  |  |  | #N/A | [21 empty] | 2026-07-29 | 2026-04-22 | 61 | 2026-04-22 | 61 | 2026-04-29 | 68 | 2026-04-29 | 7 | 2026-05-06 | 75 | 2026-06-24 | 35
26-016 | SNF | Y |  | Y | -13 |  | #N/A | [21 empty] | 2026-07-22 | 2026-03-19 | 27 | 2026-03-19 | 27 | 2026-03-26 | 34 | 2026-03-26 | 7 | 2026-04-02 | 41 | 2026-06-04 | 48
26-017 | SNF | Y | 2 | Y | 1 |  | #N/A | [21 empty] | 2026-07-22 | 2026-04-09 | 48 | 2026-04-09 | 48 | 2026-04-16 | 55 | 2026-04-16 | 7 | 2026-04-23 | 62 | 2026-06-25 | 27
26-018 | SNF | Y | 2 | Y | 1 |  | #N/A | [21 empty] | 2026-07-22 | 2026-04-09 | 48 | 2026-04-09 | 48 | 2026-04-16 | 55 | 2026-04-16 | 7 | 2026-04-23 | 62 | 2026-06-25 | 27
Formulas:
Drop Dead Date Week of = IFNA(VLOOKUP([Job #],Dates,22,FALSE),"")
Days to go = IFERROR([Release to Shop By Ship Date]-TODAY(),0)
days to go = IFERROR([QC Checklist]-TODAY(),0)
days to go = IFERROR([Burn File]-TODAY(),0)
Ship Date Week Of = IFNA(VLOOKUP([Job #],'Date Calcs from Ship Date'!A:C,3,0),"")
QC Checklist = IFNA(IF([QC Checklist]="Y","DONE",VLOOKUP([Job #],'Date Calcs from Ship Date'!A:AE,29,0)),"")
Release to Shop By Ship Date = IFNA(IF([Build Plan]="Y","DONE",VLOOKUP([Job #],'Date Calcs from Ship Date'!A:AE,27,0)),"")
All MAT. On hand = IF([Purch Recvd]="Y","DONE",VLOOKUP([Job #],'Date Calcs from Ship Date'!A:AE,25,0))
Release to Shop = IF([Released]="Y","DONE",VLOOKUP([Job #],'Date Calcs from Ship Date'!A:AE,30,0))
Burn File = IFNA(IF([Burn File]="Y","DONE",VLOOKUP([Job #],'Date Calcs from Ship Date'!A:AI,28,0)),"")

## Actual Dates
Actual Dates
[7 empty] | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Job | Submitted 0 | Submitted 1 | Submitted 2 | Submitted 3 | Rev | Aproved | App. Prints Submitted | Customer Response | Resubmit | Customer Response | Resubmit | Customer Response | Resubmit | Customer Response | Long lead time | Prelim BOM | Rev | Final Calcs | A.I. | Cert Dwgs | Customer Drop Dead Date | Update BOM | Stock Check | Order Balance | All Purchased Parts Recv'd | Final BOM | Build Plan | Burn File | QC Checklist | Release | Delivery Date | Due Date | Date Complete
24-046 | Y | Y | Y | Y | 3 | y | 2024-09-09 | 2025-05-05 | 2025-05-24 | 2025-07-08 | 2025-07-16 | 2025-07-30 | 2025-08-06 | 2025-08-08 | 2024-08-27 | 2024-08-26 | 4 | 2025-08-14 |  | 2025-08-14 | 2026-05-21 | 2025-08-19 | 2025-08-19 | 2025-11-06 | 2024-12-03 | 2025-11-06 | 2025-11-24 | 2025-11-18 | 2025-11-24 | 2025-12-05
25-010 | Y | Y | Y | Y | 2 | y | 2025-05-28 | 2025-06-26 | 2025-07-03 | 2025-08-21 | 2025-08-28 |  |  |  | 2025-02-19 | 2025-02-17 | 3 | 2025-08-28 |  | 2025-08-28 | 2025-12-04 | 2025-07-25 | 2025-07-25 | 2025-07-28 | 2025-08-04 | 2025-07-28 | 2025-12-08 | 2026-01-16 | 2025-01-16 | 2026-01-17
25-011 | Y | Y | Y | Y | 2 | y | 2025-04-25 | 2025-05-29 | 2025-06-04 | 2025-08-28 | 2025-09-04 |  |  |  | 2025-02-18 | 2025-02-17 | 3 | 2025-09-04 |  | 2025-09-04 | 2026-01-08 | 2025-06-26 | 2025-06-26 | 2025-06-27 |  | 2025-06-27 | 2025-10-31
25-012 | Y | Y | Y | Y | 2 | y | 2025-04-25 | 2025-05-29 | 2025-06-04 | 2025-08-28 | 2025-09-04 |  |  |  | 2025-02-18 | 2025-02-17 | 3 | 2025-09-04 |  | 2025-09-04 | 2026-01-08 | 2025-06-30 | 2025-06-30 | 2025-07-01 | 2025-12-11 | 2025-07-01 | 2025-01-07 | 2025-12-09 | 2026-01-07 | 2026-01-08
25-013 | Y | Y | Y | Y | 1 | y | 2025-03-25 | 2025-05-29 | 2025-06-04 | [5 empty] | 2025-02-18 | 2025-02-17 | 2 | 2025-06-04 |  | 2025-06-04 | 2025-10-08 | 2025-06-30 | 2025-06-30 | 2025-07-02 | 2025-08-18 | 2025-07-02 | 2025-10-22 | 2025-10-23 | 2025-10-25 | 2025-10-27
25-014 | Y | Y | Y | Y | 1 | y | 2025-04-02 | 2025-05-14 | 2025-05-28 | [5 empty] | 2025-02-18 | 2025-02-17 | 2 | 2025-05-28 |  | 2025-05-28 | 2025-10-01 | 2025-07-01 | 2025-07-01 | 2025-07-02 |  | 2025-07-02 | 2025-09-03 |  |  | 2025-09-03
25-015 | Y | Y | Y | Y | 1 | y | 2025-04-02 | 2025-05-14 | 2025-05-28 | [5 empty] | 2025-02-18 | 2025-02-17 | 2 | 2025-05-28 |  | 2025-05-28 | 2025-10-29 | 2025-07-16 | 2025-07-16 | 2025-07-17 |  | 2025-07-17 | 2025-08-27 |  |  | 2025-08-27
25-016 | Y | Y | Y | Y | 1 | y | 2025-04-02 | 2025-05-14 | 2025-05-28 | [5 empty] | 2025-02-18 | 2025-02-17 | 2 | 2025-05-28 |  | 2025-05-28 | 2025-10-29 | 2025-07-21 | 2025-07-21 | 2025-07-22 | 2025-09-15 | 2025-07-22 | 2025-11-18 | 2025-12-03 | 2025-12-03 | 2025-12-04
25-017 | Y | Y | Y | Y | 1 | y | 2025-03-10 | 2025-04-07 | 2025-04-22 | [5 empty] | 2025-02-18 | 2025-02-17 | 2 | 2025-04-22 |  | 2025-04-22 | 2025-09-23 | 2025-07-22 | 2025-07-22 | 2025-07-23 |  | 2025-07-23 | 2025-09-30 |  |  | 2025-09-30
25-018 | Y | Y | Y | Y | 2 | y | 2025-05-21 | 2025-07-14 | 2025-08-05 | 2025-08-21 | 2025-09-05 |  |  |  | 2025-02-18 | 2025-02-17 | 3 | 2025-09-05 |  | 2025-09-05 | 2026-02-06 | 2025-09-15 | 2025-09-17 | 2025-09-19 | 2026-02-13 | 2025-09-19 | 2025-10-22 | 2026-01-29 | 2026-01-28 | 2025-10-24
25-019 | Y | Y | Y | Y | 2 | y | 2025-05-13 | 2025-06-18 | 2025-06-26 | 2025-08-28 | 2025-09-05 |  |  |  | 2025-02-18 | 2025-02-17 | 3 | 2025-09-05 |  | 2025-09-05 | 2026-03-06 | 2025-09-13 | 2025-09-15 | 2025-09-17 | 2025-09-23 | 2025-09-17 | 2025-11-18 | 2025-12-11 | 2025-12-08 | 2025-12-04
25-020 | Y | Y | Y | Y | 3 | y | 2025-03-25 | 2025-05-29 | 2025-06-04 | 2025-07-24 | 2025-08-04 | 2025-08-21 | 2025-08-26 |  | 2025-02-18 | 2025-02-17 | 4 | 2025-08-26 |  | 2025-08-26 | 2026-02-24 | 2025-07-17 | 2025-07-17 | 2025-08-19 |  | 2025-08-19 | 2025-09-04 |  |  | 2025-09-04
25-021 | Y | Y | Y | Y | 2 | y | 2025-05-13 | 2025-06-18 | 2025-08-22 | 2025-08-28 | 2025-09-02 |  |  |  | 2025-02-18 | 2025-02-17 | 3 | 2025-09-02 |  | 2025-09-02 | 2026-03-03 | 2025-09-10 | 2025-09-10 | 2025-09-11 | 2025-09-15 | 2025-09-11 | 2025-09-16 | 2025-10-20 | 2025-09-18 | 2025-09-18
25-023 | Y | Y | Y | Y | 2 | y | 2025-02-12 | 2025-02-26 | 2025-03-05 | 2025-03-10 | 2025-03-10 |  |  |  | 2025-02-11 | 2025-02-11 | 3 | 2025-03-10 |  | 2025-03-10 | 2025-06-02 | 2025-03-13 | 2025-03-14 | 2025-03-18 |  | 2025-03-18 | 2025-03-12 |  |  | 2025-03-19
25-024 | Y | Y | Y | Y | 2 | y | 2025-02-12 | 2025-02-26 | 2025-03-05 | 2025-03-10 | 2025-03-10 |  |  |  | 2025-02-11 | 2025-02-11 | 3 | 2025-03-10 |  | 2025-03-10 | 2025-06-02 | 2025-03-13 | 2025-03-14 | 2025-03-18 |  | 2025-03-18 | 2025-03-12 |  |  | 2025-03-19
25-025 | Y | Y | Y | Y | 2 | y | 2025-02-26 | 2025-04-07 | 2025-04-17 | 2025-05-22 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 |  | 2025-05-28 | 2025-11-12 | 2025-05-28 | 2025-05-28 | 2025-05-28 |  | 2025-05-28 | 2025-06-03 |  |  | 2025-06-13
25-026 | Y | Y | Y | Y | 2 | y | 2025-02-26 | 2025-04-07 | 2025-04-17 | 2025-05-13 | 2025-05-20 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-20 |  | 2025-05-20 | 2025-11-04 | 2025-05-15 | 2025-05-15 | 2025-05-16 |  | 2025-05-16 | 2025-06-02 |  |  | 2025-06-13
25-027 | Y | Y | Y | Y | 2 | y | 2025-02-26 | 2025-04-07 | 2025-04-17 | 2025-05-13 | 2025-05-20 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-20 |  | 2025-05-20 | 2025-11-04 | 2025-05-19 | 2025-05-20 | 2025-05-21 |  | 2025-05-22 | 2025-06-03 |  |  | 2025-08-06
25-028 | Y | Y | Y | Y | 2 | y | 2025-03-03 | 2025-04-07 | 2025-04-17 | 2025-05-13 | 2025-05-20 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-20 |  | 2025-05-20 | 2025-11-04 | 2025-05-19 | 2025-05-20 | 2025-05-21 |  | 2025-05-22 | 2025-06-03 |  |  | 2025-08-06
25-029 | Y | Y | Y | Y | 2 | y | 2025-03-03 | 2025-04-07 | 2025-04-17 | 2025-05-13 | 2025-05-20 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-20 |  | 2025-05-20 | 2025-11-04 | 2025-05-19 | 2025-05-20 | 2025-05-21 |  | 2025-05-22 | 2025-06-09 |  |  | 2025-08-08
25-030 | Y | Y | Y | Y | 2 | y | 2025-03-05 | 2025-04-07 | 2025-04-17 | 2025-05-13 | 2025-05-20 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-20 |  | 2025-05-20 | 2025-11-04 | 2025-05-22 | 2025-05-22 | 2025-05-23 |  | 2025-05-23 | 2025-06-09 |  |  | 2025-08-08
25-031 | Y | Y | Y | Y | 2 | y | 2025-02-27 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 |  | 2025-05-28 | 2025-11-12 | 2025-05-30 | 228428 | 2025-06-02 |  | 2025-06-02 | 2025-06-12 |  |  | 2025-08-13
25-032 | Y | Y | Y | Y | 2 | y | 2025-02-27 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 |  | 2025-05-28 | 2025-11-12 | 2025-05-30 | 228428 | 2025-06-02 |  | 2025-06-02 | 2025-06-12 |  |  | 2025-08-15
25-033 | Y | Y | Y | Y | 2 | y | 2025-03-05 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 |  | 2025-05-28 | 2025-11-12 | 2025-06-04 | 2025-06-04 | 2025-06-04 |  | 2025-06-04 | 2025-06-16 |  |  | 2025-08-20
25-034 | Y | Y | Y | Y | 2 | y | 2025-02-26 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 |  | 2025-05-28 | 2025-11-12 | 2025-06-05 | 2025-06-05 | 2025-06-06 |  | 2025-06-06 | 2025-06-16 |  |  | 2025-07-02
25-035 | Y | Y | Y | Y | 2 | y | 2025-03-05 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 |  | 2025-05-28 | 2025-11-12 | 2025-06-05 | 2025-06-05 | 2025-06-05 |  | 2025-06-05 | 2025-06-16 |  |  | 2025-07-02
25-036 | Y | Y | Y | Y | 2 | y | 2025-02-26 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 |  | 2025-05-28 | 2025-11-12 | 2025-06-05 | 2025-06-05 | 2025-06-06 |  | 2025-06-06 | 2025-06-16 |  |  | 2025-07-02
25-037 | Y | Y | Y | Y | 2 | y | 2025-02-28 | 2025-04-07 | 2025-04-17 | 2025-05-21 | 2025-05-28 |  |  |  | 2025-02-18 | 2025-02-19 | 3 | 2025-05-28 |  | 2025-05-28 | 2025-11-12 | 2025-05-28 | 2025-05-28 | 2025-05-29 |  | 2025-05-29 | 2025-06-16 |  |  | 2025-06-18
25-039 | Y | Y | Y | Y | 1 | y | 2025-03-20 | 2025-05-01 | 2025-05-06 | [5 empty] | 2025-03-06 | 2025-03-05 | 2 | 2025-05-06 |  | 2025-05-06 | 2025-08-26 | 2025-05-09 | 2025-05-12 | 2025-05-13 |  | 2025-05-14 | 2025-05-08 |  |  | 2025-05-29
25-040 | Y | Y | Y | Y | 1 | y | 2025-02-18 | 2025-02-25 | 2025-03-13 | [5 empty] | 2025-03-05 | 2025-03-05 | 2 | 2025-03-13 |  | 2025-03-13 | 2025-08-14 | 2025-03-27 | 2025-09-16 | 2025-09-16 | 2025-07-01 | 2025-09-16 | 2025-09-16 | 2025-09-17 | 2025-09-16 | 2025-09-17
25-042 | Y | Y | Y | Y | 2 | y | 2025-03-25 | 2025-04-14 | 2025-04-15 | 2025-05-19 | 2025-05-22 |  |  |  | 2025-03-27 | 2025-03-27 | 3 | 2025-05-22 |  | 2025-05-22 | 2025-07-31 | 2025-05-27 | 2025-05-28 | 2025-05-29 |  | 2025-05-29 | 2025-06-20 |  |  | 2025-07-01
25-044 | Y | Y | Y | Y | 2 | y | 2025-05-14 | 2025-05-21 | 2025-05-27 | 2025-05-29 | 2025-05-30 |  |  |  | 2025-04-23 | 2025-04-18 | 3 | 2025-05-30 |  | 2025-05-30 | 2025-08-22 | 2025-06-12 | 2025-06-12 | 2025-06-17 |  | 2025-06-17 | 2025-06-18 |  |  | 2025-06-25
25-045 | N | Y | Y | Y |  |  | Actual Dates 16: 2025-04-09; Actual Dates 17: 2025-04-09; Actual Dates 18: 0; Actual Dates 19: 0; Actual Dates 22: 2025-05-17; Actual Dates 23: NA; Actual Dates 24: NA; Actual Dates 25: NA; Actual Dates 27: NA
25-052 | Y | Y | Y | Y | 3 | y | 2025-06-11 | 2025-07-01 | 2025-07-08 | 2025-07-14 | 2025-07-21 | 2025-07-22 | 2025-07-29 |  | 2025-05-23 | 2025-05-23 | 4 | 2025-07-29 |  | 2025-07-29 | 2025-11-04 | 2025-09-08 | 2025-09-09 | 2025-09-12 |  | 2025-09-12 | 2025-09-17 |  |  | 2025-09-23
25-053 | N | Y | Y | Y |  |  | Actual Dates 16: 2025-08-13; Actual Dates 17: 2025-08-12; Actual Dates 18: 0; Actual Dates 19: 0; Actual Dates 22: 2026-07-27; Actual Dates 23: 2025-08-13; Actual Dates 24: 2025-08-13; Actual Dates 25: 2025-08-25; Actual Dates 26: 2025-09-02; Actual Dates 27: 2025-08-25; Actual Dates 28: 2025-08-28; Actual Dates 29: 2025-09-24; Actual Dates 31: 2025-08-28
25-054 | Y | Y | Y | Y | 2 | y | 2025-06-27 | 2025-06-30 | 2025-07-10 | 2025-07-10 | 2025-07-17 |  |  |  | 2025-06-09 | 2025-06-09 | 3 | 2025-07-17 |  | 2025-07-17 | 2025-10-30 | 2025-07-29 | 2025-07-29 | 2025-07-30 |  | 2025-07-30 | 2025-09-17 |  |  | 2025-09-23
25-055 | Y | Y | Y | Y | 1 | y | 2025-11-25 | 2025-12-10 | 2025-12-17 | [5 empty] | 2025-12-09 | 2025-12-08 | 2 | 2025-12-17 |  | 2025-12-17 | 2026-06-17 | 2026-01-02 | 2026-01-05 | 2026-01-07 |  | 2026-01-07 |  | 2026-02-10 | 2026-02-08
25-056 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2025-11-10 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-08-20
25-057 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2025-11-10 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-08-20
25-058 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2025-12-08 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-09-03
25-059 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2025-12-08 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-09-03
25-060 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2026-01-05 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-09-26
25-061 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2026-01-05 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-09-26
25-062 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2026-02-02 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-11-10
25-063 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2026-02-02 | 2025-08-05 | 2025-08-05 | 2025-08-06 |  | 2025-08-06 | 2025-08-01 |  |  | 2025-11-10
25-064 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2026-03-02 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 |  |  | 2025-12-09
25-065 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2026-03-02 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 |  |  | 2025-12-09
25-066 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2026-03-30 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 | 2026-02-20 | 2025-08-01 | 2026-01-12
25-067 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2026-03-30 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 | 2026-02-20 | 2025-08-01 | 2026-01-12
25-068 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2026-04-27 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 | 2026-02-20 | 2025-08-01 | 2026-02-09
25-069 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2026-04-27 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 | 2026-02-20 | 2025-08-01 | 2026-02-09
25-070 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2026-05-25 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 | 2026-02-20 | 2025-08-01 | 2026-02-18
25-071 | Y | Y | Y | Y | 2 | y | 2025-07-09 | 2025-07-14 | 2025-07-23 | 2025-07-28 | 2025-08-04 |  |  |  | NA | NA | 3 | 2025-08-04 |  | 2025-08-04 | 2026-05-25 | 2025-08-05 | 2025-08-05 | 2025-08-06 | 2025-08-13 | 2025-08-06 | 2025-08-01 | 2026-02-20 | 2025-08-01 | 2026-02-18
25-072 | Y | Y | Y | Y | 1 | y | 2025-07-03 | 2025-07-07 | 2025-07-14 | [5 empty] | 2025-06-23 | 2025-06-20 | 2 | 2025-07-14 |  | 2025-07-14 | 2025-10-13 | 2025-07-18 | 2025-07-18 | 2025-07-21 |  | 2025-07-21 | 2025-07-23 |  |  | 2025-07-30
25-073 | Y | Y | Y | Y | 1 | y | 2025-07-03 | 2025-07-07 | 2025-07-14 | [5 empty] | 2025-06-23 | 2025-06-20 | 2 | 2025-07-14 |  | 2025-07-14 | 2025-10-13 | 2025-07-18 | 2025-07-18 | 2025-07-21 |  | 2025-07-21 | 2025-07-23 |  |  | 2025-07-30
25-074 | Y | Y | Y | Y | 1 | y | 2025-07-16 | 2025-07-17 | 2025-07-22 | [5 empty] | 2025-06-25 | 2025-06-24 | 2 | 2025-07-22 |  | 2025-07-22 | 2025-10-28 | 2025-07-30 | 2025-07-30 | 2025-08-01 |  | 2025-08-01 | 2025-09-10 |  |  | 2025-09-11
25-075 | Y | Y | Y | Y | 2 | y | 2025-07-16 | 2025-07-21 | 2025-07-30 | 2025-08-15 | 2025-08-19 |  |  |  | 2025-06-25 | 2025-06-24 | 3 | 2025-08-19 |  | 2025-08-19 | 2025-11-25 | 2025-08-28 | 2025-08-28 | 2025-08-29 |  | 2025-08-29 | 2025-10-22 |  |  | 2025-10-30
25-076 | Y | Y | Y | Y | 1 | y | 2025-07-28 | 2025-08-12 | 2025-08-19 | [5 empty] | NA | NA | 2 | 2025-08-19 |  | 2025-08-19 | 2026-02-17 | 2025-08-20 | 2025-08-20 | 2025-08-21 |  | 2025-08-21 | 2025-08-28 |  |  | 2025-08-28
25-077 | Y | Y | Y | Y | 2 | y | 2025-07-23 | 2025-08-06 | 2025-08-14 | 2025-08-18 | 2025-08-25 |  |  |  | 2025-09-01 | 2025-09-01 | 3 | 2025-08-25 |  | 2025-08-25 | 2026-02-23 | 2025-09-02 | 2025-09-02 | 2025-09-04 |  | 2025-06-04 | 2025-10-23 |  |  | 2025-10-31
25-078 | Y | Y | Y | Y | 2 | y | 2025-07-21 | 2025-08-01 | 2025-08-11 | 2025-08-18 | 2025-08-25 |  |  |  | 2025-09-02 | 2025-09-02 | 3 | 2025-08-25 |  | 2025-08-25 | 2026-02-23 | 2025-09-02 | 2025-09-02 | 2025-09-03 |  | 2025-09-03 | 2025-10-23 |  |  | 2025-11-05
25-079 | Y | Y | Y | Y | 2 | y | 2025-07-21 | 2025-08-01 | 2025-08-11 | 2025-08-18 | 2025-08-25 |  |  |  | 2025-09-02 | 2025-09-02 | 3 | 2025-08-25 |  | 2025-08-25 | 2026-02-23 | 2025-09-02 | 2025-09-02 | 2025-09-03 |  | 2025-09-03 | 2025-10-23 |  |  | 2025-11-05
25-080 | Y | Y | Y | Y | 1 | y | 2025-07-18 | 2025-07-31 | 2025-08-21 | [5 empty] | 2025-07-15 | 7/15/25025 | 2 | 2025-08-21 |  | 2025-08-21 | 2026-02-19 | 2025-09-05 | 2025-09-05 | 2025-09-10 |  | 2025-09-10 | 2025-09-23 |  |  | 2025-10-30
25-081 | N | Y | Y | Y |  |  | Actual Dates 16: NA; Actual Dates 17: NA; Actual Dates 18: 0; Actual Dates 19: 0; Actual Dates 23: NA; Actual Dates 24: NA; Actual Dates 25: NA; Actual Dates 27: NA
25-083 | Y | Y | Y | N | 2 | y | 2025-08-15 | 2025-10-14 | 2025-10-29 | 2025-10-30 | 2025-11-04 | 2026-02-02 |  |  | 2025-07-24 | 2025-07-24 | 3 | 2025-11-04 |  | 2025-11-04 | 2026-05-05 | 2025-11-10 | 2025-11-10 | 2025-11-11 | 2026-01-08 | 2025-11-11 | 2025-11-24 | 2026-01-13 | 2025-11-24 | 2025-11-24
25-084 | Y | Y | Y | Y | 3 | y | 2025-08-08 | 2025-08-11 | 2025-08-18 | 2025-10-15 | 2025-10-21 | 2025-10-24 | 2025-10-31 | 2025-11-04 | 2025-07-24 | 2025-07-24 | 4 | 2025-11-04 |  | 2025-11-04 | 2026-03-10 | 2025-10-24 | 2025-10-24 | 2025-11-05 | 2025-11-17 | 2025-11-05 | 2025-11-24 | 2025-12-30 | 2025-11-24 | 2025-11-24
25-085 | Y | Y | Y | Y | 1 | y | 2025-08-12 | 2025-08-14 | 2025-08-19 | [5 empty] | 2025-07-25 | 2025-07-24 | 2 | 2025-08-19 |  | 2025-08-19 | 2025-12-09 | 2025-08-21 | 2025-08-21 | 2025-08-27 |  | 2025-08-27 | 2025-09-22 |  |  | 2025-09-30
25-086 | N | Y | Y | Y |  |  | Actual Dates 16: 2025-08-13; Actual Dates 17: 2025-08-13; Actual Dates 18: 0; Actual Dates 19: 0; Actual Dates 22: 2026-02-18; Actual Dates 23: 2025-08-22; Actual Dates 24: 2025-08-22; Actual Dates 25: 2025-08-27; Actual Dates 27: 2025-08-27; Actual Dates 28: 2025-08-25; Actual Dates 31: 2025-08-26
25-087 | Y | Y | Y | Y | 1 | y | 2025-08-28 | 2025-09-08 | 2025-09-15 | [5 empty] | 2025-08-18 | 2025-08-14 | 2 | 2025-09-15 |  | 2025-09-15 | 2025-12-08 | 2005-09-19 | 2025-09-19 | 2025-09-22 |  | 2025-09-22 | 2025-09-22 |  |  | 2025-09-24
25-088 | Y | Y | Y | Y | 1 | y | Actual Dates 8: 2025-09-03; Actual Dates 9: 2025-09-09; Actual Dates 10: 2025-09-15; Actual Dates 18: 2; Actual Dates 19: 2025-09-15; Actual Dates 21: 2025-09-15; Actual Dates 22: 2025-11-03; Actual Dates 23: 2025-09-18; Actual Dates 24: 2025-09-18; Actual Dates 25: 2025-09-22; Actual Dates 27: 2025-09-22; Actual Dates 28: 2025-09-22; Actual Dates 31: 2025-10-23
25-089 | Y | Y | Y | Y | 1 | y | 2025-09-22 | 2025-11-21 | 2025-12-04 | [5 empty] | 2025-09-17 | 2025-09-12 | 2 | 2025-12-04 |  | 2025-12-04 | 2026-05-21 | 2025-12-08 | 2025-12-08 | 2025-12-09 | 2026-01-21 | 2025-12-09 | 2025-12-11 | 2026-02-19 | 2025-12-11 | 2025-12-16
25-090 | Y | Y | Y | Y | 0 | y | Actual Dates 8: 2025-08-22; Actual Dates 16: NA; Actual Dates 17: NA; Actual Dates 18: 1; Actual Dates 19: 2025-08-22; Actual Dates 21: 2025-08-22; Actual Dates 22: 2025-09-12; Actual Dates 23: NA; Actual Dates 24: NA; Actual Dates 25: NA; Actual Dates 27: NA
25-091 | N | Y | Y | Y |  |  | Actual Dates 16: NA; Actual Dates 17: NA; Actual Dates 18: 0; Actual Dates 19: 0; Actual Dates 22: 2025-10-09; Actual Dates 23: 2025-09-23; Actual Dates 24: 2025-09-23; Actual Dates 25: 2025-09-23; Actual Dates 27: 2025-09-23; Actual Dates 28: 2025-09-22; Actual Dates 31: 2025-09-23
25-092 | Y | Y | Y | Y | 2 | y | 2025-10-01 | 2025-10-07 | 2025-10-14 | 2025-10-23 | 2025-10-27 |  |  |  | 2025-09-18 | 2025-09-17 | 3 | 2025-10-27 |  | 2025-10-27 | 2026-03-02 | 2025-11-17 | 2025-11-18 | 2025-11-18 | 2025-12-01 | 2025-11-18 | 2026-01-09 | 2026-01-12 | 2026-01-09 | 2026-01-13
25-093 | Y | Y | Y | Y | 2 | y | 2025-10-01 | 2025-10-07 | 2025-10-14 | 2025-10-23 | 2025-10-27 |  |  |  | 2025-09-18 | 2025-09-17 | 3 | 2025-10-27 |  | 2025-10-27 | 2026-03-02 | 2025-11-17 | 2025-11-18 | 2025-11-18 | 2025-12-01 | 2025-11-18 | 2026-01-09 | 2026-01-15 | 2026-01-09 | 2026-01-13
25-094 | Y | Y | Y | Y | 1 | y | Actual Dates 8: 2025-10-06; Actual Dates 10: 2025-11-18; Actual Dates 16: NA; Actual Dates 17: NA; Actual Dates 18: 2; Actual Dates 19: 2025-11-18; Actual Dates 21: 2025-11-18; Actual Dates 22: 2026-02-24; Actual Dates 23: 2025-11-21; Actual Dates 24: 2025-11-21; Actual Dates 25: 2025-11-21; Actual Dates 27: 2025-11-21; Actual Dates 28: 2025-12-01; Actual Dates 31: 2025-12-09
25-095 | Y | Y | Y | Y | 2 |  | Actual Dates 8: 2025-10-16; Actual Dates 9: 2025-11-12; Actual Dates 10: 2025-11-19; Actual Dates 11: 2026-02-02; Actual Dates 12: 2026-02-13; Actual Dates 16: NA; Actual Dates 17: NA; Actual Dates 18: 3; Actual Dates 19: 0; Actual Dates 22: 2026-02-16; Actual Dates 23: NA; Actual Dates 24: NA; Actual Dates 25: NA; Actual Dates 27: NA
25-096 | Y | Y | Y | Y | 1 | y | 2025-10-15 | 2025-10-16 | 2025-10-23 | [5 empty] | 2025-09-25 | 2025-09-25 | 2 | 2025-10-23 |  | 2025-10-23 | 2026-01-08 | 2025-11-03 | 228585 | 2025-11-04 |  | 2025-11-04 | 2025-12-01 |  |  | 2025-12-08
25-097 | Y | Y | Y | Y | 1 | y | 2025-10-15 | 2025-10-16 | 2025-10-23 | [5 empty] | 2025-09-25 | 2025-09-25 | 2 | 2025-10-23 |  | 2025-10-23 | 2026-01-08 | 2025-11-03 | 228585 | 2025-11-04 |  | 2025-11-04 | 2025-12-01 |  |  | 2025-12-08
25-098 | Y | Y | Y | Y | 1 | y | 2025-10-22 | 2025-10-24 | 2025-10-30 | [5 empty] | 2025-10-10 | 2025-10-07 | 2 | 2025-10-30 |  | 2025-10-30 | 2026-03-19 | 2025-11-11 | 2025-11-11 | 2025-11-13 |  | 2025-11-13 | 2026-01-15 | 2026-01-13 | 2026-01-15 | 2026-01-21
25-099 | Y | Y | Y | Y | 1 | y | 2025-10-29 | 2025-10-29 | 2025-11-05 | [5 empty] | 2025-10-13 | 2025-10-10 | 2 | 2025-11-05 |  | 2025-11-05 | 2026-02-25 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-19 | 2025-11-13 | 2026-01-16 | 2026-01-22 | 2026-01-22 | 2026-01-23
25-101 | Y | Y | Y | Y | 1 | y | 2025-11-20 | 2025-12-01 | 2025-12-08 | [5 empty] | 2025-10-31 | 2025-10-30 | 2 | 2025-12-08 |  | 2025-12-08 | 2026-04-13 | 2025-12-10 | 2025-12-10 | 2025-12-16 | 2026-02-10 | 2025-12-16 | 2026-01-19 | 2026-01-16 | 2026-01-19 | 2026-01-21
25-102 | Y | Y | Y | N | 2 |  | Actual Dates 8: 2025-12-12; Actual Dates 9: 2026-01-12; Actual Dates 10: 2026-01-19; Actual Dates 11: 2026-02-02; Actual Dates 12: 2026-02-04; Actual Dates 13: 2026-02-19; Actual Dates 16: 2025-11-25; Actual Dates 17: 2025-11-24; Actual Dates 18: 3; Actual Dates 19: 0; Actual Dates 22: 2026-07-02
25-103 | Y | Y | Y | N | 2 | y | Actual Dates 8: 2025-12-12; Actual Dates 9: 2026-01-12; Actual Dates 10: 2026-01-22; Actual Dates 11: 2026-02-02; Actual Dates 12: 2026-02-04; Actual Dates 13: 2026-02-19; Actual Dates 16: 2025-11-25; Actual Dates 17: 2025-11-24; Actual Dates 18: 3; Actual Dates 19: 2026-02-19; Actual Dates 21: 2026-02-19; Actual Dates 22: 2026-06-25
25-104 | Y | Y | Y | N | 2 | y | Actual Dates 8: 2025-12-12; Actual Dates 9: 2026-01-12; Actual Dates 10: 2026-01-22; Actual Dates 11: 2026-02-02; Actual Dates 12: 2026-02-04; Actual Dates 13: 2026-02-19; Actual Dates 16: 2025-11-25; Actual Dates 17: 2025-11-24; Actual Dates 18: 3; Actual Dates 19: 2026-02-19; Actual Dates 21: 2026-02-19; Actual Dates 22: 2026-06-25
25-105 | Y | Y | Y | N | 2 | y | Actual Dates 8: 2025-12-12; Actual Dates 9: 2026-01-12; Actual Dates 10: 2026-01-28; Actual Dates 11: 2026-02-02; Actual Dates 12: 2026-02-04; Actual Dates 13: 2026-02-19; Actual Dates 16: 2025-11-25; Actual Dates 17: 2025-11-24; Actual Dates 18: 3; Actual Dates 19: 2026-02-19; Actual Dates 21: 2026-02-19; Actual Dates 22: 2026-06-25
25-106 | Y | Y | Y | N | 2 |  | Actual Dates 8: 2025-12-12; Actual Dates 9: 2026-01-12; Actual Dates 10: 2026-01-28; Actual Dates 11: 2026-02-02; Actual Dates 12: 2026-02-05; Actual Dates 13: 2026-02-19; Actual Dates 16: 2025-11-25; Actual Dates 17: 2025-11-24; Actual Dates 18: 3; Actual Dates 19: 0; Actual Dates 22: 2026-07-02
25-107 | Y | N | Y | Y | 0 |  | Actual Dates 8: 2025-11-26; Actual Dates 9: 2026-02-02; Actual Dates 16: 2026-02-12; Actual Dates 17: 2026-01-11; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-06-15
25-108 | Y | Y | Y | Y | 1 |  | Actual Dates 8: 2025-11-26; Actual Dates 9: 2026-02-02; Actual Dates 10: 2026-02-11; Actual Dates 16: 2026-02-12; Actual Dates 17: 2026-01-11; Actual Dates 18: 2; Actual Dates 19: 0; Actual Dates 22: 2026-06-15
25-109 | Y | Y | Y | Y | 3 | y | 2025-11-26 | 2025-12-12 | 2025-12-19 | 2026-01-12 | 2026-01-19 | 2026-01-23 | 2026-01-30 | 2026-02-19 | 2025-11-11 | 2025-11-06 | 4 | 2026-02-19 |  | 2026-02-19 | 2026-06-25 | 2026-01-20 | 2026-01-20 | 2026-01-21 | 2026-02-16 | 2026-01-21
25-110 | Y | Y | Y | Y | 3 |  | 2025-11-26 | 2025-12-12 | 2025-12-22 | 2026-01-12 | 2026-01-19 | 2026-01-23 | 2026-01-30 |  | 2025-11-07 | 2025-11-06 | 4 | 0 |  |  | 2026-06-05 | 2026-01-21 | 2026-01-21 | 2026-02-02 | 2026-02-16 | 2026-02-02
25-111 | Y | Y | Y | Y | 3 |  | Actual Dates 8: 2025-11-26; Actual Dates 9: 2025-12-12; Actual Dates 10: 2025-12-19; Actual Dates 11: 2026-01-12; Actual Dates 12: 2026-01-21; Actual Dates 13: 2026-01-23; Actual Dates 14: 2026-01-30; Actual Dates 16: 2025-12-01; Actual Dates 17: 2025-11-10; Actual Dates 18: 4; Actual Dates 19: 0; Actual Dates 22: 2026-06-05
25-112 | Y | Y | Y | Y | 3 |  | Actual Dates 8: 2025-11-26; Actual Dates 9: 2025-12-12; Actual Dates 10: 2025-12-19; Actual Dates 11: 2026-01-12; Actual Dates 12: 2026-01-21; Actual Dates 13: 2026-01-23; Actual Dates 14: 2026-01-30; Actual Dates 16: 2025-12-01; Actual Dates 17: 2025-11-10; Actual Dates 18: 4; Actual Dates 19: 0; Actual Dates 22: 2026-06-05
25-113 | Y | Y | Y | Y | 2 |  | Actual Dates 8: 2025-12-12; Actual Dates 9: 2026-01-12; Actual Dates 10: 2026-01-19; Actual Dates 11: 2026-02-02; Actual Dates 12: 2026-02-05; Actual Dates 16: 2025-12-01; Actual Dates 17: 2025-11-10; Actual Dates 18: 3; Actual Dates 19: 0; Actual Dates 22: 2026-06-15
25-115 | Y | Y | Y | N | 2 | y | Actual Dates 8: 2025-11-26; Actual Dates 9: 2026-01-12; Actual Dates 10: 2026-01-21; Actual Dates 11: 2026-01-23; Actual Dates 12: 2026-01-30; Actual Dates 13: 2026-02-19; Actual Dates 16: 2025-11-11; Actual Dates 17: 2025-11-10; Actual Dates 18: 3; Actual Dates 19: 2026-02-19; Actual Dates 21: 2026-02-19; Actual Dates 22: 2026-06-25
25-116 | Y | Y | N | Y | 1 |  | Actual Dates 8: 2025-12-19; Actual Dates 9: 2026-01-02; Actual Dates 10: 2026-01-09; Actual Dates 11: 2026-02-12; Actual Dates 16: 2025-11-10; Actual Dates 17: 2025-11-10; Actual Dates 18: 2; Actual Dates 19: 0; Actual Dates 22: 2026-06-25; Actual Dates 23: 2026-01-14; Actual Dates 24: 2026-01-14; Actual Dates 25: 2026-01-16; Actual Dates 26: 2026-02-26; Actual Dates 27: 2026-01-16
25-117 | Y | Y | Y | Y | 2 | y | 2026-01-14 | 2026-01-21 | 2026-01-28 | 2026-02-02 | 2026-02-10 |  |  |  | 2026-01-15 | 2026-01-15 | 3 | 2026-02-10 |  | 2026-02-10 | 2026-06-30 | 2026-02-12 | 2026-02-12 | 2026-02-16 | 2026-03-11 | 2026-02-16 | 2026-02-12 | 2026-02-18 | 2026-02-18 | 2026-02-19
25-118 | Y | Y | Y | Y | 2 | y | Actual Dates 8: 2026-01-14; Actual Dates 9: 2026-01-21; Actual Dates 10: 2026-02-02; Actual Dates 11: 2026-02-09; Actual Dates 12: 2026-02-16; Actual Dates 16: 2026-01-15; Actual Dates 17: 2026-01-15; Actual Dates 18: 3; Actual Dates 19: 2026-02-16; Actual Dates 21: 2026-02-16; Actual Dates 22: 2026-07-06; Actual Dates 26: 2026-03-11; Actual Dates 27: 2026-02-20; Actual Dates 28: 2026-02-17
25-119 | Y | Y | Y | Y | 1 | y | Actual Dates 8: 2025-11-24; Actual Dates 9: 2025-12-03; Actual Dates 10: 2025-12-03; Actual Dates 16: NA; Actual Dates 17: NA; Actual Dates 18: 2; Actual Dates 19: 2025-12-03; Actual Dates 21: 2025-12-03; Actual Dates 22: 2025-12-03
25-120 | N | Y | Y | Y |  |  | Actual Dates 16: 2026-01-29; Actual Dates 17: 2025-12-01; Actual Dates 18: 0; Actual Dates 19: 0; Actual Dates 22: 2026-06-12
25-121 | Y | N | Y | Y | 0 |  | Actual Dates 8: 2026-01-08; Actual Dates 9: 2026-02-17; Actual Dates 16: 2025-12-17; Actual Dates 17: 2025-12-16; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-06-30
25-122 | Y | N | Y | Y | 0 |  | Actual Dates 8: 2026-01-08; Actual Dates 9: 2026-02-17; Actual Dates 16: 2025-12-17; Actual Dates 17: 2025-12-16; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-06-30
25-123 | Y | Y | Y | Y | 0 |  | Actual Dates 8: 2026-01-08; Actual Dates 16: 2025-12-17; Actual Dates 17: 2025-12-16; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-06-04
25-124 | N | Y | Y | Y |  |  | Actual Dates 16: 2025-12-15; Actual Dates 17: 2025-12-11; Actual Dates 18: 0; Actual Dates 19: 0; Actual Dates 22: 2026-08-17; Actual Dates 23: 2026-01-06; Actual Dates 24: 2026-01-06; Actual Dates 25: 2026-01-07; Actual Dates 27: 2026-01-07; Actual Dates 28: 2026-01-09; Actual Dates 29: 2026-01-10; Actual Dates 31: 2026-02-03
25-356 | Y | Y | Y | Y | 1 |  | Actual Dates 8: 2026-01-28; Actual Dates 9: 2026-02-02; Actual Dates 10: 2026-02-16; Actual Dates 17: 2026-01-19; Actual Dates 18: 2; Actual Dates 19: 0; Actual Dates 22: 2026-06-15
25-357 | Y | N | Y | Y | 0 |  | Actual Dates 8: 2026-01-29; Actual Dates 9: 2026-02-11; Actual Dates 16: 2026-01-19; Actual Dates 17: 2026-01-19; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-06-10
25-358 | Y | N | Y | Y | 0 |  | Actual Dates 8: 2026-01-30; Actual Dates 9: 2026-02-11; Actual Dates 16: 2026-01-19; Actual Dates 17: 2026-01-19; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-06-10
26-002 | Y | Y | Y | Y | 0 |  | Actual Dates 8: 2026-02-06; Actual Dates 16: 2026-01-26; Actual Dates 17: 2026-01-22; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-07-03
26-003 | Y | Y | Y | Y | 0 |  | Actual Dates 8: 2026-02-06; Actual Dates 16: 2026-01-26; Actual Dates 17: 2026-01-22; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-07-03
26-004 | Y | Y | Y | Y | 0 |  | Actual Dates 8: 2026-02-06; Actual Dates 16: 2026-01-26; Actual Dates 17: 2026-01-22; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-07-03
26-005 | Y | N | Y | Y | 0 |  | Actual Dates 8: 2026-02-05; Actual Dates 9: 2026-02-11; Actual Dates 16: 2026-01-22; Actual Dates 17: 2026-01-22; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-07-08
26-014 | Y | Y | Y | Y | 0 |  | Actual Dates 8: 2026-02-11; Actual Dates 16: 2026-01-27; Actual Dates 17: 2026-01-27; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-06-24
26-015 | N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0; Actual Dates 22: 2026-07-29
26-016 | N | Y | Y | Y |  |  | Actual Dates 16: 2026-02-12; Actual Dates 17: 2026-01-27; Actual Dates 18: 0; Actual Dates 19: 0; Actual Dates 22: 2026-07-22
26-017 | Y | Y | Y | Y | 0 |  | Actual Dates 8: 2026-02-11; Actual Dates 16: 2026-01-27; Actual Dates 17: 2026-01-27; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-07-22
26-018 | Y | Y | Y | Y | 0 |  | Actual Dates 8: 2026-02-11; Actual Dates 16: 2026-01-27; Actual Dates 17: 2026-01-27; Actual Dates 18: 1; Actual Dates 19: 0; Actual Dates 22: 2026-07-22
26-020 | N | Y | Y | Y |  |  | Actual Dates 16: 2026-02-17; Actual Dates 17: 2026-02-17; Actual Dates 18: 0; Actual Dates 19: 0; Actual Dates 22: 2026-07-31
26-021 | N | Y | Y | Y |  |  | Actual Dates 16: 2026-02-17; Actual Dates 17: 2026-02-17; Actual Dates 18: 0; Actual Dates 19: 0; Actual Dates 22: 2026-07-31
26-022 | N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0; Actual Dates 22: 2026-07-14
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0
| N | Y | Y | Y |  |  | Actual Dates 18: 0; Actual Dates 19: 0

## Change Order (3) (hidden)
Change Order Status
|  | Status | [5 empty] | After Return of Approval Drawings | [15 empty] | Release to Shop
Job # | Customer | Project Scope |  | Material Escalation |  | Prelim BOM |  | Final Calcs |  | A.I. |  | Cert Dwgs |  | Update BOM |  | Stock Check |  | Order Balance |  | Final BOM |  | Build Plan |  | Target | Actual | Days +/- | Status
16-073 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16-074 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16-075 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
16-076 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-132 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-133 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-134 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-135 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-136 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-137 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-141 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-142 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-143 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-144 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-145 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-146 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-147 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-148 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-149 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-150 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-151 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-152 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-153 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-154 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-155 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
21-156 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-001 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-002 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-003 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-004 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-005 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-006 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-007 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-008 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-009 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-010 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-011 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-012 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-015 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-016 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-017 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-018 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-019 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-020 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-021 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-022 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-023 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-024 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-025 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-026 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-027 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-028 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-029 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-030 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-031 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-032 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-033 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-034 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-035 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-036 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-037 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-038 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-040 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-041 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-042 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-043 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-044 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-045 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-046 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-047 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-048 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-049 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-050 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-051 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-052 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-053 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-054 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-055 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-056 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-058 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-059 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-061 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-062 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-063 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-064 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-065 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-066 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-067 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-068 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-069 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-070 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-071 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-072 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-074 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-075 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
22-076 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A

## Date (hidden)
Today | 2026-02-20
|  | Dates | ='Actual Dates'!$A$4:$AB$350
|  | Jobs | ='Date Calcs'!$A$4:$AB$350
|  | Ship | ='Date Calcs from Ship Date'!$A$4:$AB$351

## Date Calcs
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
|  | Dates | # of weeks per quote |  |  |  | # of Days---> | 14 | 7 | 7 | 7 | 7 | 7 | 7 | 14 | 14 |  | 2 | 1 | 7 |  |  | 14 | 21 | 21 | 21 | 14 | 1 | 7 | 2
[7 empty] | from c | From h | From I | From J | From k | From L | From M | From N | from C | from C |  | From I,K,L or N | From S | From I,K,L or N |  |  | From I,K,L or N | From I,K,L or N | From I,K,L or N | From I,K,L or N | From I,K,L or N |  |  | From Z | From I,K,L or N
Job | Customer | Order Date | min design | max design | min build | max build | App. Prints Submitted | Customer Response | Resubmit | Customer Response | Resubmit | Customer Response | Resubmit | Customer Response | Long lead time | Prelim BOM |  | Final Calcs | A.I. | Cert Dwgs | Weeks on Hold by Customer | Customer Ship Date | Update BOM | Stock Check | Order Balance | Final BOM | Build Plan | Burn File | QC Checklist | Release Target | Delivery Date
24-046 | SYMS Engineering | 2024-08-15 | 2 | 3 | 18 | 30 | 2024-09-05 | 2024-09-23 | 2025-05-12 | 2025-05-31 | 2025-07-15 | 2025-07-23 | 2025-08-06 | 2025-08-13 | 2024-08-29 | 2024-08-29 |  | 2025-08-10 | 2025-08-11 | 2025-08-15 | 10 | 2026-05-22 | 2025-08-22 | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-08-31 | 2025-08-30 | 2025-08-22 | 2025-09-01 | 2026-03-06
25-010 | Kimberly Clark | 2025-01-28 | 4 | 5 | 12 | 14 | 2025-03-04 | 2025-06-11 | 2025-07-03 | 2025-07-10 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-02-11 | 2025-02-11 |  | 2025-08-23 | 2025-08-24 | 2025-08-28 |  | 2025-12-04 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-12 | 2025-09-04 | 2025-09-14 | 2025-11-27
25-011 | Kimberly Clark | 2025-01-28 | 4 | 5 | 16 | 18 | 2025-03-04 | 2025-05-09 | 2025-06-05 | 2025-06-11 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-02-11 | 2025-02-11 |  | 2025-08-30 | 2025-08-31 | 2025-09-04 |  | 2026-01-08 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-19 | 2025-09-11 | 2025-09-21 | 2026-01-01
25-012 | Kimberly Clark | 2025-01-28 | 4 | 5 | 16 | 18 | 2025-03-04 | 2025-05-09 | 2025-06-05 | 2025-06-11 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-02-11 | 2025-02-11 |  | 2025-08-30 | 2025-08-31 | 2025-09-04 |  | 2026-01-08 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-19 | 2025-09-11 | 2025-09-21 | 2026-01-01
25-013 | Kimberly Clark | 2025-01-28 | 4 | 5 | 16 | 18 | 2025-03-04 | 2025-04-08 | 2025-06-05 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-07-09 | 2025-02-11 | 2025-02-11 |  | 2025-05-31 | 2025-06-01 | 2025-06-05 |  | 2025-10-09 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-20 | 2025-06-12 | 2025-06-22 | 2025-10-02
25-014 | Kimberly Clark | 2025-01-28 | 4 | 5 | 16 | 18 | 2025-03-04 | 2025-04-16 | 2025-05-21 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-02-11 | 2025-02-11 |  | 2025-05-16 | 2025-05-17 | 2025-05-21 |  | 2025-09-24 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-05 | 2025-05-28 | 2025-06-07 | 2025-09-17
25-015 | Kimberly Clark | 2025-01-28 | 4 | 5 | 20 | 22 | 2025-03-04 | 2025-04-16 | 2025-05-21 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-02-11 | 2025-02-11 |  | 2025-05-16 | 2025-05-17 | 2025-05-21 |  | 2025-10-22 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-05 | 2025-05-28 | 2025-06-07 | 2025-10-15
25-016 | Kimberly Clark | 2025-01-28 | 4 | 5 | 20 | 22 | 2025-03-04 | 2025-04-16 | 2025-05-21 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-06-25 | 2025-07-02 | 2025-02-11 | 2025-02-11 |  | 2025-05-16 | 2025-05-17 | 2025-05-21 |  | 2025-10-22 | 2025-05-28 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-05 | 2025-05-28 | 2025-06-07 | 2025-10-15
25-017 | Kimberly Clark | 2025-01-28 | 4 | 5 | 20 | 22 | 2025-03-04 | 2025-03-24 | 2025-04-14 | 2025-04-29 | 2025-05-06 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-02-11 | 2025-02-11 |  | 2025-04-09 | 2025-04-10 | 2025-04-14 |  | 2025-09-15 | 2025-04-21 | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-29 | 2025-04-21 | 2025-05-01 | 2025-09-08
25-018 | Kimberly Clark | 2025-01-28 | 4 | 5 | 20 | 22 | 2025-03-04 | 2025-06-04 | 2025-07-21 | 2025-08-12 | 2025-08-28 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-02-11 | 2025-02-11 |  | 2025-08-23 | 2025-08-24 | 2025-08-28 |  | 2026-01-29 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-12 | 2025-09-04 | 2025-09-14 | 2026-01-22
25-019 | Kimberly Clark | 2025-01-28 | 4 | 5 | 24 | 26 | 2025-03-04 | 2025-05-27 | 2025-06-25 | 2025-07-03 | 2025-09-04 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-02-11 | 2025-02-11 |  | 2025-08-30 | 2025-08-31 | 2025-09-04 |  | 2026-03-05 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-19 | 2025-09-11 | 2025-09-21 | 2026-02-26
25-020 | Kimberly Clark | 2025-01-28 | 4 | 5 | 24 | 26 | 2025-03-04 | 2025-04-08 | 2025-06-05 | 2025-06-11 | 2025-07-31 | 2025-08-11 | 2025-08-28 | 2025-09-02 | 2025-02-11 | 2025-02-11 |  | 2025-08-23 | 2025-08-24 | 2025-08-28 |  | 2026-02-26 | 2025-09-04 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-12 | 2025-09-04 | 2025-09-14 | 2026-02-19
25-021 | Kimberly Clark | 2025-01-28 | 4 | 5 | 24 | 26 | 2025-03-04 | 2025-05-27 | 2025-06-25 | 2025-08-29 | 2025-09-04 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-02-11 | 2025-02-11 |  | 2025-08-30 | 2025-08-31 | 2025-09-04 |  | 2026-03-05 | 2025-09-11 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-19 | 2025-09-11 | 2025-09-21 | 2026-02-26
25-023 | Andritz | 2025-01-30 | 1 | 2 | 10 | 12 | 2025-02-13 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-17 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-02-13 | 2025-02-13 |  | 2025-03-12 | 2025-03-13 | 2025-03-17 |  | 2025-06-09 | 2025-03-24 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-04-01 | 2025-03-24 | 2025-04-03 | 2025-06-02
25-024 | Andritz | 2025-01-30 | 1 | 2 | 10 | 12 | 2025-02-13 | 2025-02-26 | 2025-03-05 | 2025-03-12 | 2025-03-17 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-02-13 | 2025-02-13 |  | 2025-03-12 | 2025-03-13 | 2025-03-17 |  | 2025-06-09 | 2025-03-24 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-04-01 | 2025-03-24 | 2025-04-03 | 2025-06-02
25-025 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-12 | 2025-04-14 | 2025-04-24 | 2025-05-29 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-24 | 2025-05-25 | 2025-05-29 |  | 2025-11-13 | 2025-06-05 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-13 | 2025-06-05 | 2025-06-15 | 2025-11-06
25-026 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-12 | 2025-04-14 | 2025-04-24 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-02-19 | 2025-02-19 |  | 2025-05-15 | 2025-05-16 | 2025-05-20 |  | 2025-11-04 | 2025-05-27 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-04 | 2025-05-27 | 2025-06-06 | 2025-10-28
25-027 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-12 | 2025-04-14 | 2025-04-24 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-02-19 | 2025-02-19 |  | 2025-05-15 | 2025-05-16 | 2025-05-20 |  | 2025-11-04 | 2025-05-27 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-04 | 2025-05-27 | 2025-06-06 | 2025-10-28
25-028 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-17 | 2025-04-14 | 2025-04-24 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-02-19 | 2025-02-19 |  | 2025-05-15 | 2025-05-16 | 2025-05-20 |  | 2025-11-04 | 2025-05-27 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-04 | 2025-05-27 | 2025-06-06 | 2025-10-28
25-029 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-17 | 2025-04-14 | 2025-04-24 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-02-19 | 2025-02-19 |  | 2025-05-15 | 2025-05-16 | 2025-05-20 |  | 2025-11-04 | 2025-05-27 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-04 | 2025-05-27 | 2025-06-06 | 2025-10-28
25-030 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-19 | 2025-04-14 | 2025-04-24 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-02-19 | 2025-02-19 |  | 2025-05-15 | 2025-05-16 | 2025-05-20 |  | 2025-11-04 | 2025-05-27 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-04 | 2025-05-27 | 2025-06-06 | 2025-10-28
25-031 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-13 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 |  | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-032 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-13 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 |  | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-033 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-19 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 |  | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-034 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-12 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 |  | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-035 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-19 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 |  | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-036 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-12 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 |  | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-037 | Irving Tissue | 2025-02-05 | 3 | 4 | 20 | 24 | 2025-03-05 | 2025-03-14 | 2025-04-14 | 2025-04-24 | 2025-05-28 | 2025-06-04 | 2025-06-11 | 2025-06-18 | 2025-02-19 | 2025-02-19 |  | 2025-05-23 | 2025-05-24 | 2025-05-28 |  | 2025-11-12 | 2025-06-04 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | 2025-06-04 | 2025-06-14 | 2025-11-05
25-039 | Zachry | 2025-02-26 | 2 | 3 | 14 | 16 | 2025-03-19 | 2025-04-03 | 2025-05-08 | 2025-05-13 | 2025-05-20 | 2025-05-27 | 2025-06-03 | 2025-06-10 | 2025-03-12 | 2025-03-12 |  | 2025-05-03 | 2025-05-04 | 2025-05-08 |  | 2025-08-28 | 2025-05-15 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-23 | 2025-05-15 | 2025-05-25 | 2025-08-21
25-040 | NAK Kiln | 2025-03-05 | 1 | 2 | 20 | 22 | 2025-03-19 | 2025-03-04 | 2025-03-04 | 2025-03-20 | 2025-03-27 | 2025-04-03 | 2025-04-10 | 2025-04-17 | 2025-03-19 | 2025-03-19 |  | 2025-02-27 | 2025-02-28 | 2025-03-04 |  | 2025-08-05 | 2025-03-11 | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-19 | 2025-03-11 | 2025-03-21 | 2025-07-29
25-042 | Andritz | 2025-03-19 | 2 | 3 | 8 | 10 | 2025-04-09 | 2025-04-08 | 2025-04-21 | 2025-04-22 | 2025-05-26 | 2025-05-29 | 2025-06-05 | 2025-06-12 | 2025-04-02 | 2025-04-02 |  | 2025-05-21 | 2025-05-22 | 2025-05-26 |  | 2025-08-04 | 2025-06-02 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-10 | 2025-06-02 | 2025-06-12 | 2025-07-28
25-044 | Noah Industrial | 2025-04-01 | 3 | 4 | 10 | 12 | 2025-04-29 | 2025-05-28 | 2025-05-28 | 2025-06-03 | 2025-06-05 | 2025-06-06 | 2025-06-13 | 2025-06-20 | 2025-04-15 | 2025-04-15 |  | 2025-05-31 | 2025-06-01 | 2025-06-05 |  | 2025-08-28 | 2025-06-12 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-20 | 2025-06-12 | 2025-06-22 | 2025-08-21
25-045 | ProPipe | 2025-04-05 | 1 | 1 | 1 | 2 | 2025-04-12 | 2025-04-26 | 2025-05-03 | 2025-05-10 | 2025-05-17 | 2025-05-24 | 2025-05-31 | 2025-06-07 | 2025-04-19 | 2025-04-19 |  | 2025-04-28 | 2025-04-29 | 2025-05-03 |  | 2025-05-17 | 2025-05-10 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-18 | 2025-05-10 | 2025-05-20 | 2025-05-10
25-052 | Kraton | 2025-05-19 | 2 | 3 | 12 | 14 | 2025-06-09 | 2025-06-25 | 2025-07-08 | 2025-07-15 | 2025-07-21 | 2025-07-28 | 2025-07-29 | 2025-08-05 | 2025-06-02 | 2025-06-02 |  | 2025-07-24 | 2025-07-25 | 2025-07-29 |  | 2025-11-04 | 2025-08-05 | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-12 | 2025-08-13 | 2025-08-05 | 2025-08-15 | 2025-10-28
25-053 | Andritz | 2025-06-02 | 2 | 31 | 8 | 10 | 2026-01-05 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2025-06-16 | 2025-06-16 |  | 2026-01-21 | 2026-01-22 | 2026-01-26 | 16 | 2026-07-27 | 2026-02-02 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-02 | 2026-02-12 | 2026-03-30
25-054 | Chromascape | 2025-06-03 | 3 | 4 | 13 | 15 | 2025-07-01 | 2025-07-11 | 2025-07-07 | 2025-07-17 | 2025-07-17 | 2025-07-24 | 2025-07-31 | 2025-08-07 | 2025-06-17 | 2025-06-17 |  | 2025-07-12 | 2025-07-13 | 2025-07-17 |  | 2025-10-30 | 2025-07-24 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-08-01 | 2025-07-24 | 2025-08-03 | 2025-10-23
25-055 | Airgas | 2025-06-12 | 3 | 16 | 22 | 26 | 2025-10-02 | 2025-12-09 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2026-01-14 | 2026-01-21 | 2025-06-26 | 2025-06-26 |  | 2025-12-12 | 2025-12-13 | 2025-12-17 |  | 2026-06-17 | 2025-12-24 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2026-01-01 | 2025-12-24 | 2026-01-03 | 2026-06-10
25-056 | Reco | 2025-06-13 | 2 | 3 | 12 | 14 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2025-11-10 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2025-11-03
25-057 | Reco | 2025-06-13 | 2 | 3 | 12 | 14 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2025-11-10 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2025-11-03
25-058 | Reco | 2025-06-13 | 2 | 3 | 16 | 18 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2025-12-08 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2025-12-01
25-059 | Reco | 2025-06-13 | 2 | 3 | 16 | 18 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2025-12-08 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2025-12-01
25-060 | Reco | 2025-06-13 | 2 | 3 | 20 | 22 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2026-01-05 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2025-12-29
25-061 | Reco | 2025-06-13 | 2 | 3 | 20 | 22 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2026-01-05 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2025-12-29
25-062 | Reco | 2025-06-13 | 2 | 3 | 24 | 26 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2026-02-02 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-01-26
25-063 | Reco | 2025-06-13 | 2 | 3 | 24 | 26 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2026-02-02 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-01-26
25-064 | Reco | 2025-06-13 | 2 | 3 | 28 | 30 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2026-03-02 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-02-23
25-065 | Reco | 2025-06-13 | 2 | 3 | 28 | 30 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2026-03-02 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-02-23
25-066 | Reco | 2025-06-13 | 2 | 3 | 32 | 34 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2026-03-30 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-03-23
25-067 | Reco | 2025-06-13 | 2 | 3 | 32 | 34 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2026-03-30 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-03-23
25-068 | Reco | 2025-06-13 | 2 | 3 | 36 | 38 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2026-04-27 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-04-20
25-069 | Reco | 2025-06-13 | 2 | 3 | 36 | 38 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2026-04-27 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-04-20
25-070 | Reco | 2025-06-13 | 2 | 3 | 40 | 42 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2026-05-25 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-05-18
25-071 | Reco | 2025-06-13 | 2 | 3 | 40 | 42 | 2025-07-04 | 2025-07-23 | 2025-07-21 | 2025-07-30 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-06-27 | 2025-06-27 |  | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 2026-05-25 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-19 | 2025-08-11 | 2025-08-21 | 2026-05-18
25-072 | Burke Industrial | 2025-06-16 | 2 | 3 | 11 | 13 | 2025-07-07 | 2025-07-17 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-06-30 | 2025-06-30 |  | 2025-07-09 | 2025-07-10 | 2025-07-14 |  | 2025-10-13 | 2025-07-21 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-29 | 2025-07-21 | 2025-07-31 | 2025-10-06
25-073 | Burke Industrial | 2025-06-16 | 2 | 3 | 11 | 13 | 2025-07-07 | 2025-07-17 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-06-30 | 2025-06-30 |  | 2025-07-09 | 2025-07-10 | 2025-07-14 |  | 2025-10-13 | 2025-07-21 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-29 | 2025-07-21 | 2025-07-31 | 2025-10-06
25-074 | Kemira | 2025-06-16 | 2 | 3 | 12 | 14 | 2025-07-07 | 2025-07-30 | 2025-07-24 | 2025-07-29 | 2025-08-05 | 2025-08-12 | 2025-08-19 | 2025-08-26 | 2025-06-30 | 2025-06-30 |  | 2025-07-19 | 2025-07-20 | 2025-07-24 |  | 2025-10-30 | 2025-07-31 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-08-08 | 2025-07-31 | 2025-08-10 | 2025-10-23
25-075 | Kemira | 2025-06-16 | 2 | 3 | 12 | 14 | 2025-07-07 | 2025-07-30 | 2025-07-28 | 2025-08-06 | 2025-08-22 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-06-30 | 2025-06-30 |  | 2025-08-17 | 2025-08-18 | 2025-08-22 |  | 2025-11-28 | 2025-08-29 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-05 | 2025-09-06 | 2025-08-29 | 2025-09-08 | 2025-11-21
25-076 | Irving tissue | 2025-06-17 | 2 | 4 | 22 | 26 | 2025-07-15 | 2025-08-11 | 2025-08-19 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-07-01 | 2025-07-01 |  | 2025-08-14 | 2025-08-15 | 2025-08-19 |  | 2026-02-17 | 2025-08-26 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-03 | 2025-08-26 | 2025-09-05 | 2026-02-10
25-077 | Epic Systems | 2025-06-25 | 2 | 3 | 22 | 26 | 2025-07-16 | 2025-08-06 | 2025-08-13 | 2025-08-21 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-07-09 | 2025-07-09 |  | 2025-08-20 | 2025-08-21 | 2025-08-25 |  | 2026-02-23 | 2025-09-01 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-09 | 2025-09-01 | 2025-09-11 | 2026-02-16
25-078 | Epic Systems | 2025-06-25 | 2 | 3 | 22 | 26 | 2025-07-16 | 2025-08-04 | 2025-08-08 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-07-09 | 2025-07-09 |  | 2025-08-20 | 2025-08-21 | 2025-08-25 |  | 2026-02-23 | 2025-09-01 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-09 | 2025-09-01 | 2025-09-11 | 2026-02-16
25-079 | Epic Systems | 2025-06-25 | 2 | 3 | 22 | 26 | 2025-07-16 | 2025-08-04 | 2025-08-08 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-07-09 | 2025-07-09 |  | 2025-08-20 | 2025-08-21 | 2025-08-25 |  | 2026-02-23 | 2025-09-01 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-09 | 2025-09-01 | 2025-09-11 | 2026-02-16
25-080 | Domtar | 2025-06-27 | 2 | 3 | 22 | 26 | 2025-07-18 | 2025-08-01 | 2025-08-07 | 2025-08-28 | 2025-09-04 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-07-11 | 2025-07-11 |  | 2025-08-02 | 2025-08-03 | 2025-08-07 |  | 2026-02-05 | 2025-08-14 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-22 | 2025-08-14 | 2025-08-24 | 2026-01-29
25-083 | Synthomer | 2025-07-15 | 2 | 3 | 22 | 26 | 2025-08-05 | 2025-08-29 | 2025-10-21 | 2025-11-05 | 2025-11-06 | 2025-11-11 | 2026-02-09 | 2026-02-16 | 2025-07-29 | 2025-07-29 |  | 2026-02-04 | 2026-02-05 | 2026-02-09 |  | 2026-08-10 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-16 | 2026-02-26 | 2026-08-03
25-084 | Atlas Minerals | 2025-07-18 | 2 | 3 | 13 | 15 | 2025-08-08 | 2025-08-22 | 2025-08-18 | 2025-08-25 | 2025-10-22 | 2025-10-28 | 2025-10-31 | 2025-11-07 | 2025-08-01 | 2025-08-01 |  | 2025-11-06 | 2025-11-07 | 2025-11-11 | 3 | 2026-03-17 | 2025-11-18 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-26 | 2025-11-18 | 2025-11-28 | 2026-02-17
25-085 | Noah Industrial | 2025-07-22 | 2 | 3 | 14 | 16 | 2025-08-12 | 2025-08-26 | 2025-08-21 | 2025-08-26 | 2025-09-02 | 2025-09-09 | 2025-09-16 | 2025-09-23 | 2025-08-05 | 2025-08-05 |  | 2025-08-16 | 2025-08-17 | 2025-08-21 |  | 2025-12-11 | 2025-08-28 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-04 | 2025-09-05 | 2025-08-28 | 2025-09-07 | 2025-12-04
25-086 | Tellus | 2025-07-30 | 0 | 0 | 22 | 26 | 2025-07-30 | 2025-08-13 | 2025-08-20 | 2025-08-27 | 2025-09-03 | 2025-09-10 | 2025-09-17 | 2025-09-24 | 2025-08-13 | 2025-08-13 |  | 2025-08-15 | 2025-08-16 | 2025-08-20 |  | 2026-02-18 | 2025-08-27 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-03 | 2025-09-04 | 2025-08-27 | 2025-09-06 | 2026-02-11
25-087 | Solvay | 2025-08-07 | 2 | 3 | 10 | 12 | 2025-08-28 | 2025-09-11 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-08-21 | 2025-08-21 |  | 2025-09-10 | 2025-09-11 | 2025-09-15 |  | 2025-12-08 | 2025-09-22 | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-30 | 2025-09-22 | 2025-10-02 | 2025-12-01
25-088 | CIL Isotopes | 2025-08-13 | 2 | 3 | 6 | 7 | 2025-09-03 | 2025-09-17 | 2025-09-16 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-08-27 | 2025-08-27 |  | 2025-09-11 | 2025-09-12 | 2025-09-16 |  | 2025-11-04 | 2025-09-23 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-01 | 2025-09-23 | 2025-10-03 | 2025-10-28
25-089 | Valmet | 2025-08-22 | 3 | 4.5 | 20 | 24 | 2025-09-22 12:00 | 2025-10-06 | 2025-11-28 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2025-09-05 | 2025-09-05 |  | 2025-11-23 | 2025-11-24 | 2025-11-28 |  | 2026-05-15 | 2025-12-05 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-12 | 2025-12-13 | 2025-12-05 | 2025-12-15 | 2026-05-08
25-090 | GAF | 2025-08-18 | 1 | 1 | 2 | 3 | 2025-08-25 | 2025-09-05 | 2025-09-12 | 2025-09-19 | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-09-01 | 2025-09-01 |  | 2025-09-07 | 2025-09-08 | 2025-09-12 |  | 2025-10-03 | 2025-09-19 | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-27 | 2025-09-19 | 2025-09-29 | 2025-09-26
25-091 | US Sugar | 2025-09-04 | 1 | 1 | 1 | 1 | 2025-09-11 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-09-18 | 2025-09-18 |  | 2025-09-27 | 2025-09-28 | 2025-10-02 |  | 2025-10-09 | 2025-10-09 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-16 | 2025-10-17 | 2025-10-09 | 2025-10-19 | 2025-10-02
25-092 | Symrise | 2025-09-10 | 3 | 4 | 16 | 18 | 2025-10-08 | 2025-10-15 | 2025-10-14 | 2025-10-21 | 2025-10-30 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-09-24 | 2025-09-24 |  | 2025-10-25 | 2025-10-26 | 2025-10-30 |  | 2026-03-05 | 2025-11-06 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-14 | 2025-11-06 | 2025-11-16 | 2026-02-26
25-093 | Symrise | 2025-09-10 | 3 | 4 | 16 | 18 | 2025-10-08 | 2025-10-15 | 2025-10-14 | 2025-10-21 | 2025-10-30 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-09-24 | 2025-09-24 |  | 2025-10-25 | 2025-10-26 | 2025-10-30 |  | 2026-03-05 | 2025-11-06 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-14 | 2025-11-06 | 2025-11-16 | 2026-02-26
25-094 | Kimberly Clark | 2025-09-15 | 2 | 3 | 12 | 14 | 2025-10-06 | 2025-10-20 | 2025-10-27 | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-16 | 2025-12-23 | 2025-09-29 | 2025-09-29 |  | 2025-10-22 | 2025-10-23 | 2025-10-27 |  | 2026-02-02 | 2025-11-03 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-11 | 2025-11-03 | 2025-11-13 | 2026-01-26
25-095 | Andritz | 2025-09-19 | 3 | 4 | 1 | 1 | 2025-10-17 | 2025-10-30 | 2025-11-19 | 2025-11-26 | 2026-02-09 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2025-10-03 | 2025-10-03 |  | 2026-02-04 | 2026-02-05 | 2026-02-09 |  | 2026-02-16 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-16 | 2026-02-26 | 2026-02-09
25-096 | Milliken | 2025-09-22 | 2 | 3 | 10 | 11 | 2025-10-13 | 2025-10-29 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-10-06 | 2025-10-06 |  | 2025-10-18 | 2025-10-19 | 2025-10-23 |  | 2026-01-08 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-07 | 2025-10-30 | 2025-11-09 | 2026-01-01
25-097 | Milliken | 2025-09-22 | 2 | 3 | 10 | 11 | 2025-10-13 | 2025-10-29 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-10-06 | 2025-10-06 |  | 2025-10-18 | 2025-10-19 | 2025-10-23 |  | 2026-01-08 | 2025-10-30 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-07 | 2025-10-30 | 2025-11-09 | 2026-01-01
25-098 | Coastal Technologies | 2025-09-24 | 3 | 4 | 16 | 18 | 2025-10-22 | 2025-11-05 | 2025-10-31 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-10-08 | 2025-10-08 |  | 2025-10-26 | 2025-10-27 | 2025-10-31 | 2 | 2026-03-20 | 2025-11-07 | 2025-11-14 | 2026-02-26 | 2026-02-26 | 2025-11-14 | 2026-02-27 | 2025-11-07 | 2026-03-01 | 2026-02-27
25-099 | Burke Industrial | 2025-10-02 | 3 | 4 | 14 | 16 | 2025-10-30 | 2025-11-12 | 2025-11-05 | 2025-11-12 | 2025-11-19 | 2025-11-26 | 2025-12-03 | 2025-12-10 | 2025-10-16 | 2025-10-16 |  | 2025-10-31 | 2025-11-01 | 2025-11-05 |  | 2026-02-25 | 2025-11-12 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-20 | 2025-11-12 | 2025-11-22 | 2026-02-18
25-101 | Harper Love | 2025-10-24 | 3 | 4 | 16 | 18 | 2025-11-21 | 2025-12-04 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2025-11-07 | 2025-11-07 |  | 2025-12-03 | 2025-12-04 | 2025-12-08 |  | 2026-04-13 | 2025-12-15 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-23 | 2025-12-15 | 2025-12-25 | 2026-04-06
25-102 | Epic Systems | 2025-11-07 | 3 | 5 | 16 | 18 | 2025-12-12 | 2025-12-26 | 2026-01-19 | 2026-01-26 | 2026-02-09 | 2026-02-11 | 2026-02-26 | 2026-03-05 | 2025-11-21 | 2025-11-21 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 |  | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-103 | Epic Systems | 2025-11-07 | 3 | 5 | 16 | 18 | 2025-12-12 | 2025-12-26 | 2026-01-19 | 2026-01-29 | 2026-02-09 | 2026-02-11 | 2026-02-26 | 2026-03-05 | 2025-11-21 | 2025-11-21 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 |  | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-104 | Epic Systems | 2025-11-07 | 3 | 5 | 16 | 18 | 2025-12-12 | 2025-12-26 | 2026-01-19 | 2026-01-29 | 2026-02-09 | 2026-02-11 | 2026-02-26 | 2026-03-05 | 2025-11-21 | 2025-11-21 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 |  | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-105 | Epic Systems | 2025-11-07 | 3 | 5 | 16 | 18 | 2025-12-12 | 2025-12-26 | 2026-01-19 | 2026-02-04 | 2026-02-09 | 2026-02-11 | 2026-02-26 | 2026-03-05 | 2025-11-21 | 2025-11-21 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 |  | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-106 | Epic Systems | 2025-11-07 | 3 | 5 | 16 | 18 | 2025-12-12 | 2025-12-26 | 2026-01-19 | 2026-02-04 | 2026-02-09 | 2026-02-12 | 2026-02-26 | 2026-03-05 | 2025-11-21 | 2025-11-21 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 |  | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-107 | Epic Systems | 2026-02-02 | 3 | 4 | 16 | 18 | 2026-03-02 | 2025-12-10 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-02-16 | 2026-02-16 |  | 2026-02-04 | 2026-02-05 | 2026-02-09 |  | 2026-06-15 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-16 | 2026-02-26 | 2026-06-08
25-108 | Epic Systems | 2025-10-30 | 3 | 4 | 16 | 18 | 2025-11-27 | 2025-12-10 | 2026-02-09 | 2026-02-18 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2025-11-13 | 2025-11-13 |  | 2026-02-04 | 2026-02-05 | 2026-02-09 |  | 2026-06-15 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-16 | 2026-02-26 | 2026-06-08
25-109 | Epic Systems | 2025-10-30 | 3 | 4 | 16 | 18 | 2025-11-27 | 2025-12-10 | 2025-12-19 | 2025-12-26 | 2026-01-19 | 2026-01-26 | 2026-01-30 | 2026-02-06 | 2025-11-13 | 2025-11-13 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 |  | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-110 | Epic Systems | 2025-10-30 | 3 | 4 | 16 | 18 | 2025-11-27 | 2025-12-10 | 2025-12-19 | 2025-12-29 | 2026-01-19 | 2026-01-26 | 2026-01-30 | 2026-02-06 | 2025-11-13 | 2025-11-13 |  | 2026-01-25 | 2026-01-26 | 2026-01-30 |  | 2026-06-05 | 2026-02-06 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-06 | 2026-02-16 | 2026-05-29
25-111 | Epic Systems | 2025-10-30 | 3 | 4 | 16 | 18 | 2025-11-27 | 2025-12-10 | 2025-12-19 | 2025-12-26 | 2026-01-19 | 2026-01-28 | 2026-01-30 | 2026-02-06 | 2025-11-13 | 2025-11-13 |  | 2026-01-25 | 2026-01-26 | 2026-01-30 |  | 2026-06-05 | 2026-02-06 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-06 | 2026-02-16 | 2026-05-29
25-112 | Epic Systems | 2025-10-30 | 3 | 4 | 16 | 18 | 2025-11-27 | 2025-12-10 | 2025-12-19 | 2025-12-26 | 2026-01-19 | 2026-01-28 | 2026-01-30 | 2026-02-06 | 2025-11-13 | 2025-11-13 |  | 2026-01-25 | 2026-01-26 | 2026-01-30 |  | 2026-06-05 | 2026-02-06 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-06 | 2026-02-16 | 2026-05-29
25-113 | Epic Systems | 2025-11-14 | 3 | 4 | 16 | 18 | 2025-12-12 | 2025-12-26 | 2026-01-19 | 2026-01-26 | 2026-02-09 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2025-11-28 | 2025-11-28 |  | 2026-02-04 | 2026-02-05 | 2026-02-09 |  | 2026-06-15 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-16 | 2026-02-26 | 2026-06-08
25-115 | Epic Systems | 2025-10-30 | 3 | 4 | 16 | 18 | 2025-11-27 | 2025-12-10 | 2026-01-19 | 2026-01-28 | 2026-01-30 | 2026-02-06 | 2026-02-26 | 2026-03-05 | 2025-11-13 | 2025-11-13 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 |  | 2026-07-02 | 2026-03-05 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-05 | 2026-03-15 | 2026-06-25
25-116 | Polynt | 2025-11-04 | 3 | 4 | 16 | 18 | 2025-12-02 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2025-11-18 | 2025-11-18 |  | 2026-02-14 | 2026-02-15 | 2026-02-19 |  | 2026-06-25 | 2026-02-26 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-05 | 2026-03-06 | 2026-02-26 | 2026-03-08 | 2026-06-18
25-117 | Merrick | 2025-11-07 | 3 | 9 | 18 | 20 | 2026-01-09 | 2026-01-28 | 2026-01-28 | 2026-02-04 | 2026-02-09 | 2026-02-17 | 2026-02-24 | 2026-03-03 | 2025-11-21 | 2025-11-21 |  | 2026-02-04 | 2026-02-05 | 2026-02-09 |  | 2026-06-29 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-16 | 2026-02-26 | 2026-06-22
25-118 | Merrick | 2025-11-07 | 3 | 9 | 18 | 20 | 2026-01-09 | 2026-01-28 | 2026-01-28 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2025-11-21 | 2025-11-21 |  | 2026-02-11 | 2026-02-12 | 2026-02-16 |  | 2026-07-06 | 2026-02-23 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-03 | 2026-02-23 | 2026-03-05 | 2026-06-29
25-119 | Vertiv | 2025-11-14 | 1 | 2 |  |  | 2025-11-28 | 2025-12-08 | 2025-12-10 | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-31 | 2026-01-07 | 2025-11-28 | 2025-11-28 |  | 2025-12-05 | 2025-12-06 | 2025-12-10 |  | 2025-12-10 | 2025-12-17 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-25 | 2025-12-17 | 2025-12-27 | 2025-12-03
25-120 | Andritz | 2025-11-21 | 0 | 0 | 22 | 26 | 2025-11-21 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2025-12-05 | 2025-12-05 |  | 2025-12-07 | 2025-12-08 | 2025-12-12 |  | 2026-06-12 | 2025-12-19 | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-26 | 2025-12-27 | 2025-12-19 | 2025-12-29 | 2026-06-05
25-121 | Kimberly Clark | 2025-12-04 | 3 | 4 | 16 | 18 | 2026-01-01 | 2026-01-22 | 2026-02-24 | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2025-12-18 | 2025-12-18 |  | 2026-02-19 | 2026-02-20 | 2026-02-24 |  | 2026-06-30 | 2026-03-03 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-03 | 2026-03-13 | 2026-06-23
25-122 | Kimberly Clark | 2025-12-04 | 3 | 4 | 16 | 18 | 2026-01-01 | 2026-01-22 | 2026-02-24 | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2025-12-18 | 2025-12-18 |  | 2026-02-19 | 2026-02-20 | 2026-02-24 |  | 2026-06-30 | 2026-03-03 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-10 | 2026-03-11 | 2026-03-03 | 2026-03-13 | 2026-06-23
25-123 | Kimberly Clark | 2025-12-04 | 3 | 4 | 16 | 18 | 2026-01-01 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2025-12-18 | 2025-12-18 |  | 2026-01-24 | 2026-01-25 | 2026-01-29 |  | 2026-06-04 | 2026-02-05 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-12 | 2026-02-13 | 2026-02-05 | 2026-02-15 | 2026-05-28
25-124 | Vertiv | 2025-12-15 | 0 | 0 | 16 | 32 | 2025-12-15 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2025-12-29 | 2025-12-29 |  | 2025-12-31 | 2026-01-01 | 2026-01-05 |  | 2026-08-17 | 2026-01-12 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-20 | 2026-01-12 | 2026-01-22 | 2026-08-10
25-356 | Synthomer | 2025-12-29 | 3 | 4 | 16 | 18 | 2026-01-26 | 2026-02-11 | 2026-02-09 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-01-12 | 2026-01-12 |  | 2026-02-04 | 2026-02-05 | 2026-02-09 |  | 2026-06-15 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-16 | 2026-02-26 | 2026-06-08
25-357 | Sylvamo | 2025-12-30 | 3 | 4 | 14 | 16 | 2026-01-27 | 2026-02-12 | 2026-02-18 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-01-13 | 2026-01-13 |  | 2026-02-13 | 2026-02-14 | 2026-02-18 |  | 2026-06-10 | 2026-02-25 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-05 | 2026-02-25 | 2026-03-07 | 2026-06-03
25-358 | Sylvamo | 2025-12-30 | 3 | 4 | 14 | 16 | 2026-01-27 | 2026-02-13 | 2026-02-18 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-01-13 | 2026-01-13 |  | 2026-02-13 | 2026-02-14 | 2026-02-18 |  | 2026-06-10 | 2026-02-25 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-05 | 2026-02-25 | 2026-03-07 | 2026-06-03
26-002 | SNF | 2026-01-09 | 3 | 4 | 16 | 18 | 2026-02-06 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-01-23 | 2026-01-23 |  | 2026-02-22 | 2026-02-23 | 2026-02-27 |  | 2026-07-03 | 2026-03-06 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-06 | 2026-03-16 | 2026-06-26
26-003 | SNF | 2026-01-09 | 3 | 4 | 16 | 18 | 2026-02-06 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-01-23 | 2026-01-23 |  | 2026-02-22 | 2026-02-23 | 2026-02-27 |  | 2026-07-03 | 2026-03-06 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-06 | 2026-03-16 | 2026-06-26
26-004 | SNF | 2026-01-09 | 3 | 4 | 16 | 18 | 2026-02-06 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-01-23 | 2026-01-23 |  | 2026-02-22 | 2026-02-23 | 2026-02-27 |  | 2026-07-03 | 2026-03-06 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-14 | 2026-03-06 | 2026-03-16 | 2026-06-26
26-005 | US Sugar | 2026-01-12 | 3 | 4 | 18 | 20 | 2026-02-09 | 2026-02-19 | 2026-02-18 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-01-26 | 2026-01-26 |  | 2026-02-13 | 2026-02-14 | 2026-02-18 |  | 2026-07-08 | 2026-02-25 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-04 | 2026-03-05 | 2026-02-25 | 2026-03-07 | 2026-07-01
26-014 | SNF | 2026-01-12 | 3 | 4 | 14 | 16 | 2026-02-09 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-01-26 | 2026-01-26 |  | 2026-02-27 | 2026-02-28 | 2026-03-04 |  | 2026-06-24 | 2026-03-11 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-11 | 2026-03-21 | 2026-06-17
26-015 | SNF | 2026-02-18 | 3 | 4 | 14 | 16 | 2026-03-18 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22 | 2026-04-29 | 2026-05-06 | 2026-05-13 | 2026-03-04 | 2026-03-04 |  | 2026-04-03 | 2026-04-04 | 2026-04-08 |  | 2026-07-29 | 2026-04-15 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-22 | 2026-04-23 | 2026-04-15 | 2026-04-25 | 2026-07-22
26-016 | SNF | 2026-02-11 | 3 | 4 | 14 | 16 | 2026-03-11 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-04-22 | 2026-04-29 | 2026-05-06 | 2026-02-25 | 2026-02-25 |  | 2026-03-27 | 2026-03-28 | 2026-04-01 |  | 2026-07-22 | 2026-04-08 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-15 | 2026-04-16 | 2026-04-08 | 2026-04-18 | 2026-07-15
26-017 | SNF | 2026-01-12 | 3 | 4 | 18 | 20 | 2026-02-09 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-01-26 | 2026-01-26 |  | 2026-02-27 | 2026-02-28 | 2026-03-04 |  | 2026-07-22 | 2026-03-11 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-11 | 2026-03-21 | 2026-07-15
26-018 | SNF | 2026-01-12 | 3 | 4 | 18 | 20 | 2026-02-09 | 2026-02-25 | 2026-03-04 | 2026-03-11 | 2026-03-18 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-01-26 | 2026-01-26 |  | 2026-02-27 | 2026-02-28 | 2026-03-04 |  | 2026-07-22 | 2026-03-11 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-19 | 2026-03-11 | 2026-03-21 | 2026-07-15
26-020 | US Sugar | 2026-02-06 | 3 | 4 | 16 | 18 | 2026-03-06 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-02-20 | 2026-02-20 |  | 2026-03-22 | 2026-03-23 | 2026-03-27 |  | 2026-07-31 | 2026-04-03 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-03 | 2026-04-13 | 2026-07-24
26-021 | US Sugar | 2026-02-06 | 3 | 4 | 16 | 18 | 2026-03-06 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-02-20 | 2026-02-20 |  | 2026-03-22 | 2026-03-23 | 2026-03-27 |  | 2026-07-31 | 2026-04-03 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-11 | 2026-04-03 | 2026-04-13 | 2026-07-24
26-022 | Andritz | 2026-02-10 | 2 | 3 | 14 | 16 | 2026-03-03 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-02-24 | 2026-02-24 |  | 2026-03-19 | 2026-03-20 | 2026-03-24 |  | 2026-07-14 | 2026-03-31 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-08 | 2026-03-31 | 2026-04-10 | 2026-07-07
Formulas:
from c = [Order Date]+[max design]*7
From h = IF(VLOOKUP([Job],Dates,8,)=0,[from c]+I2,VLOOKUP([Job],Dates,8,)+I2)
From I = IF(VLOOKUP([Job],Dates,9,)=0,[From h]+J2,VLOOKUP([Job],Dates,9,)+J2)
From J = IF(VLOOKUP([Job],Dates,10,)=0,[From I]+K2,VLOOKUP([Job],Dates,10,)+K2)
From k = IF(VLOOKUP([Job],Dates,11,)=0,[From J]+L2,VLOOKUP([Job],Dates,11,)+L2)
From L = IF(VLOOKUP([Job],Dates,12,)=0,[From k]+M2,VLOOKUP([Job],Dates,12,)+M2)
From M = IF(VLOOKUP([Job],Dates,13,)=0,[From L]+N2,VLOOKUP([Job],Dates,13,)+N2)
From N = IF(VLOOKUP([Job],Dates,14,)=0,[From M]+O2,VLOOKUP([Job],Dates,14,)+O2)
from C = [Order Date]+P2
from C = [Order Date]+Q2
From S = [From I,K,L or N]+T2
From I,K,L or N = [From I,K,L or N]+U2-S2
From I,K,L or N = [From I,K,L or N]+X2-S2
Customer Ship Date = ([max build]*7)+([Weeks on Hold by Customer]*7)+[From I,K,L or N]
Burn File = [From I,K,L or N]+AC2
QC Checklist = [From I,K,L or N]+AD2
From Z = IF([from C]>[Burn File],[from C]+AC2,[Burn File]+AE2)

## Date Calcs from Ship Date
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
|  | Dates | # of weeks per schedule |  |  |  |  | # of Days---> | 14 | 7 | 7 | 7 | 7 | 7 | 7 | 84 | 2 |  | 5 | 1 | 7 | 7 | 21 | 21 | 2 | 14 | 7 | 14 | 2
to c
Job | Customer | Ship Date | Fabrication | Testing | Painting / Sandblasting | Cleaning | Shipping Prep | App. Prints Submitted | Customer Response | Resubmit | Customer Response | Resubmit | Customer Response | Resubmit | Customer Response | Long lead time | Prelim BOM |  | Final Calcs | A.I. | Cert Dwgs | Update BOM | Stock Check | Order Balance | Final BOM | Build Plan | Burn File | QC Checklist | Release Target | Ship Date
25-084 | Atlas Minerals | 2026-02-23 | 2 | 1 | 1 | 0 | 1 | 2025-08-07 | 2025-08-28 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-20 | 2025-10-18 |  | 2025-11-26 | 2025-11-27 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2026-01-05 | 2025-12-20 | 2025-12-22 | 2026-01-05 | 2025-12-15 | 2026-01-12 | 2026-02-23
26-019 | Genera | 2026-02-23 | 1 | 0 | 0 | 0 | 1 | 2025-08-28 | 2025-09-18 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-10 | 2025-11-08 |  | 2025-12-17 | 2025-12-18 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-26 | 2026-01-10 | 2026-01-12 | 2026-01-26 | 2026-01-05 | 2026-02-02 | 2026-02-23
25-018 | Kimberly Clark | 2026-03-02 | 1 | 0 | 0 | 1 | 1 | 2025-08-28 | 2025-09-18 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-10 | 2025-11-08 |  | 2025-12-17 | 2025-12-18 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-26 | 2026-01-10 | 2026-01-12 | 2026-01-26 | 2026-01-05 | 2026-02-02 | 2026-03-02
25-089 | Valmet | 2026-03-02 | 4 | 0 | 0 | 1 | 1 | 2025-08-07 | 2025-08-28 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-20 | 2025-10-18 |  | 2025-11-26 | 2025-11-27 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2026-01-05 | 2025-12-20 | 2025-12-22 | 2026-01-05 | 2025-12-15 | 2026-01-12 | 2026-03-02
25-013 | Kimberly Clark | 2026-03-09 | 4 | 1 | 0 | 1 | 1 | 2025-08-07 | 2025-08-28 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-20 | 2025-10-18 |  | 2025-11-26 | 2025-11-27 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2026-01-05 | 2025-12-20 | 2025-12-22 | 2026-01-05 | 2025-12-15 | 2026-01-12 | 2026-03-09
25-066 | Reco/Nudyne | 2026-03-09 | 4 | 1 | 1 | 0 | 1 | 2025-08-07 | 2025-08-28 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-20 | 2025-10-18 |  | 2025-11-26 | 2025-11-27 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2026-01-05 | 2025-12-20 | 2025-12-22 | 2026-01-05 | 2025-12-15 | 2026-01-12 | 2026-03-09
25-067 | Reco/Nudyne | 2026-03-09 | 4 | 1 | 1 | 0 | 1 | 2025-08-07 | 2025-08-28 | 2025-09-11 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-20 | 2025-10-18 |  | 2025-11-26 | 2025-11-27 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2026-01-05 | 2025-12-20 | 2025-12-22 | 2026-01-05 | 2025-12-15 | 2026-01-12 | 2026-03-09
25-098 | Coastal Tech | 2026-03-09 | 3 | 1 | 0 | 1 | 1 | 2025-08-14 | 2025-09-04 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-27 | 2025-10-25 |  | 2026-01-17 | 2026-01-18 | 2026-01-22 | 2026-01-29 | 2026-02-05 | 2026-02-26 | 2025-12-27 | 2025-12-29 | 2026-01-12 | 2026-02-05 | 2026-01-19 | 2026-03-09
25-099 | Burke | 2026-03-09 | 3 | 1 | 0 | 1 | 1 | 2025-08-14 | 2025-09-04 | 2025-09-18 | 2025-09-25 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-27 | 2025-10-25 |  | 2025-12-03 | 2025-12-04 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2026-01-12 | 2025-12-27 | 2025-12-29 | 2026-01-12 | 2025-12-22 | 2026-01-19 | 2026-03-09
25-092 | Symrise | 2026-03-30 | 3 | 1 | 0 | 0 | 1 | 2025-09-11 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-24 | 2025-11-22 |  | 2025-12-31 | 2026-01-01 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-02-09 | 2026-01-24 | 2026-01-26 | 2026-02-09 | 2026-01-19 | 2026-02-16 | 2026-03-30
25-093 | Symrise | 2026-03-30 | 3 | 1 | 0 | 0 | 1 | 2025-09-11 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-24 | 2025-11-22 |  | 2025-12-31 | 2026-01-01 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-02-09 | 2026-01-24 | 2026-01-26 | 2026-02-09 | 2026-01-19 | 2026-02-16 | 2026-03-30
25-040 | Nak Kiln | 2026-03-30 | 3 | 1 | 0 | 1 | 1 | 2025-09-04 | 2025-09-25 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-17 | 2025-11-15 |  | 2025-12-24 | 2025-12-25 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-02-02 | 2026-01-17 | 2026-01-19 | 2026-02-02 | 2026-01-12 | 2026-02-09 | 2026-03-30
25-083 | Synthomer | 2026-04-06 | 4 | 1 | 0 | 1 | 1 | 2025-09-04 | 2025-09-25 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-17 | 2025-11-15 |  | 2025-12-24 | 2025-12-25 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-02-02 | 2026-01-17 | 2026-01-19 | 2026-02-02 | 2026-01-12 | 2026-02-09 | 2026-04-06
25-068 | Reco/Nudyne | 2026-04-06 | 5 | 1 | 1 | 0 | 1 | 2025-08-28 | 2025-09-18 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-10 | 2025-11-08 |  | 2025-12-17 | 2025-12-18 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-26 | 2026-01-10 | 2026-01-12 | 2026-01-26 | 2026-01-05 | 2026-02-02 | 2026-04-06
25-069 | Reco/Nudyne | 2026-04-06 | 5 | 1 | 1 | 0 | 1 | 2025-08-28 | 2025-09-18 | 2025-10-02 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-10 | 2025-11-08 |  | 2025-12-17 | 2025-12-18 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-26 | 2026-01-10 | 2026-01-12 | 2026-01-26 | 2026-01-05 | 2026-02-02 | 2026-04-06
25-117 | Merrick | 2026-04-06 | 4 | 1 | 0 | 1 | 1 | 2025-09-04 | 2025-09-25 | 2025-10-09 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-17 | 2025-11-15 |  | 2025-12-24 | 2025-12-25 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-02-02 | 2026-01-24 | 2026-01-26 | 2026-02-02 | 2026-01-26 | 2026-02-09 | 2026-04-06
24-046 | Syms | 2026-04-16 | 4 | 1 | 0 | 1 | 1 | 2025-09-14 | 2025-10-05 | 2025-10-19 | 2025-10-26 | 2025-11-02 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-27 | 2025-11-25 |  | 2026-01-03 | 2026-01-04 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-02-12 | 2026-02-03 | 2026-02-05 | 2026-02-12 | 2026-02-05 | 2026-02-19 | 2026-04-16
25-070 | Reco/Nudyne | 2026-04-27 | 6 | 1 | 1 | 0 | 1 | 2025-09-11 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-24 | 2025-11-22 |  | 2025-12-31 | 2026-01-01 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-02-09 | 2026-01-31 | 2026-02-02 | 2026-02-09 | 2026-02-02 | 2026-02-16 | 2026-04-27
25-071 | Reco/Nudyne | 2026-04-27 | 6 | 1 | 1 | 0 | 1 | 2025-09-11 | 2025-10-02 | 2025-10-16 | 2025-10-23 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-24 | 2025-11-22 |  | 2025-12-31 | 2026-01-01 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-02-09 | 2026-01-31 | 2026-02-02 | 2026-02-09 | 2026-02-02 | 2026-02-16 | 2026-04-27
25-118 | Merrick | 2026-04-27 | 4 | 1 | 0 | 1 | 1 | 2025-09-25 | 2025-10-16 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-08 | 2025-12-06 |  | 2026-01-14 | 2026-01-15 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-23 | 2026-02-14 | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-03-02 | 2026-04-27
25-109 | Epic | 2026-04-27 | 4 | 1 | 0 | 1 | 1 | 2025-09-25 | 2025-10-16 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-08 | 2025-12-06 |  | 2026-01-14 | 2026-01-15 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-23 | 2026-02-14 | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-03-02 | 2026-04-27
25-102 | Epic | 2026-04-27 | 4 | 1 | 0 | 1 | 1 | 2025-09-25 | 2025-10-16 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-08 | 2025-12-06 |  | 2026-01-14 | 2026-01-15 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-23 | 2026-02-14 | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-03-02 | 2026-04-27
25-103 | Epic | 2026-04-27 | 4 | 1 | 0 | 1 | 1 | 2025-09-25 | 2025-10-16 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-08 | 2025-12-06 |  | 2026-01-14 | 2026-01-15 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-23 | 2026-02-14 | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-03-02 | 2026-04-27
25-104 | Epic | 2026-04-27 | 4 | 1 | 0 | 1 | 1 | 2025-09-25 | 2025-10-16 | 2025-10-30 | 2025-11-06 | 2025-11-13 | 2025-11-20 | 2025-11-27 | 2025-12-04 | 2025-12-08 | 2025-12-06 |  | 2026-01-14 | 2026-01-15 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-23 | 2026-02-14 | 2026-02-16 | 2026-02-23 | 2026-02-16 | 2026-03-02 | 2026-04-27
25-101 | Harper Love | 2026-05-14 | 5 | 1 | 1 | 0 | 1 | 2025-10-05 | 2025-10-26 | 2025-11-09 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-18 | 2025-12-16 |  | 2026-01-24 | 2026-01-25 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-03-05 | 2026-02-24 | 2026-02-26 | 2026-03-05 | 2026-02-26 | 2026-03-12 | 2026-05-14
25-115 | Epic | 2026-05-14 | 4 | 1 | 0 | 1 | 1 | 2025-10-12 | 2025-11-02 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-25 | 2025-12-23 |  | 2026-01-31 | 2026-02-01 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-03-12 | 2026-03-03 | 2026-03-05 | 2026-03-12 | 2026-03-05 | 2026-03-19 | 2026-05-14
25-113 | Epic | 2026-05-14 | 4 | 1 | 0 | 1 | 1 | 2025-10-12 | 2025-11-02 | 2025-11-16 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-25 | 2025-12-23 |  | 2026-01-31 | 2026-02-01 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-03-12 | 2026-03-03 | 2026-03-05 | 2026-03-12 | 2026-03-05 | 2026-03-19 | 2026-05-14
25-053 | Andritz | 2026-06-02 | 4 | 1 | 0 | 1 | 1 | 2025-10-31 | 2025-11-21 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2026-01-02 | 2026-01-09 | 2026-01-13 | 2026-01-11 |  | 2026-02-19 | 2026-02-20 | 2026-02-24 | 2026-03-03 | 2026-03-10 | 2026-03-31 | 2026-03-22 | 2026-03-24 | 2026-03-31 | 2026-03-24 | 2026-04-07 | 2026-06-02
25-105 | Epic | 2026-06-01 | 4 | 1 | 0 | 1 | 1 | 2025-10-30 | 2025-11-20 | 2025-12-04 | 2025-12-11 | 2025-12-18 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-12 | 2026-01-10 |  | 2026-02-18 | 2026-02-19 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-30 | 2026-03-21 | 2026-03-23 | 2026-03-30 | 2026-03-23 | 2026-04-06 | 2026-06-01
25-106 | Epic | 2026-06-02 | 4 | 1 | 0 | 1 | 1 | 2025-10-31 | 2025-11-21 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2026-01-02 | 2026-01-09 | 2026-01-13 | 2026-01-11 |  | 2026-02-19 | 2026-02-20 | 2026-02-24 | 2026-03-03 | 2026-03-10 | 2026-03-31 | 2026-03-22 | 2026-03-24 | 2026-03-31 | 2026-03-24 | 2026-04-07 | 2026-06-02
25-055 | AIR GAS | 2026-05-26 | 4 | 1 | 0 | 1 | 1 | 2025-10-24 | 2025-11-14 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2026-01-02 | 2026-01-06 | 2026-01-04 |  | 2026-02-12 | 2026-02-13 | 2026-02-17 | 2026-02-24 | 2026-03-03 | 2026-03-24 | 2026-03-15 | 2026-03-17 | 2026-03-24 | 2026-03-17 | 2026-03-31 | 2026-05-26
25-107 | Epic | 2026-06-22 | 4 | 1 | 0 | 1 | 1 | 2025-11-20 | 2025-12-11 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-02 | 2026-01-31 |  | 2026-03-11 | 2026-03-12 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-20 | 2026-04-11 | 2026-04-13 | 2026-04-20 | 2026-04-13 | 2026-04-27 | 2026-06-22
25-108 | Epic | 2026-06-22 | 4 | 1 | 0 | 1 | 1 | 2025-11-20 | 2025-12-11 | 2025-12-25 | 2026-01-01 | 2026-01-08 | 2026-01-15 | 2026-01-22 | 2026-01-29 | 2026-02-02 | 2026-01-31 |  | 2026-03-11 | 2026-03-12 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-20 | 2026-04-11 | 2026-04-13 | 2026-04-20 | 2026-04-13 | 2026-04-27 | 2026-06-22
25-110 | Epic | 2026-05-19 | 4 | 1 | 0 | 1 | 1 | 2025-10-17 | 2025-11-07 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2025-12-30 | 2025-12-28 |  | 2026-02-05 | 2026-02-06 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-17 | 2026-03-08 | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-24 | 2026-05-19
25-111 | Epic | 2026-05-19 | 4 | 1 | 0 | 1 | 1 | 2025-10-17 | 2025-11-07 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2025-12-30 | 2025-12-28 |  | 2026-02-05 | 2026-02-06 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-17 | 2026-03-08 | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-24 | 2026-05-19
25-112 | Epic | 2026-05-20 | 4 | 1 | 0 | 1 | 1 | 2025-10-18 | 2025-11-08 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2025-12-31 | 2025-12-29 |  | 2026-02-06 | 2026-02-07 | 2026-02-11 | 2026-02-18 | 2026-02-25 | 2026-03-18 | 2026-03-09 | 2026-03-11 | 2026-03-18 | 2026-03-11 | 2026-03-25 | 2026-05-20
25-116 | Polynt | 2026-07-27 | 4 | 1 | 0 | 1 | 1 | 2025-12-25 | 2026-01-15 | 2026-01-29 | 2026-02-05 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-09 | 2026-03-07 |  | 2026-04-15 | 2026-04-16 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-25 | 2026-05-16 | 2026-05-18 | 2026-05-25 | 2026-05-18 | 2026-06-01 | 2026-07-27
25-121 | Kimberly Clark | 2026-05-19 | 4 | 1 | 0 | 1 | 1 | 2025-10-17 | 2025-11-07 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2025-12-30 | 2025-12-28 |  | 2026-02-05 | 2026-02-06 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-17 | 2026-03-08 | 2026-03-10 | 2026-03-17 | 2026-03-10 | 2026-03-24 | 2026-05-19
25-122 | Kimberly Clark | 2026-05-20 | 4 | 1 | 0 | 1 | 1 | 2025-10-18 | 2025-11-08 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2025-12-31 | 2025-12-29 |  | 2026-02-06 | 2026-02-07 | 2026-02-11 | 2026-02-18 | 2026-02-25 | 2026-03-18 | 2026-03-09 | 2026-03-11 | 2026-03-18 | 2026-03-11 | 2026-03-25 | 2026-05-20
25-123 | Kimberly Clark | 2026-05-20 | 4 | 1 | 0 | 1 | 1 | 2025-10-18 | 2025-11-08 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2025-12-31 | 2025-12-29 |  | 2026-02-06 | 2026-02-07 | 2026-02-11 | 2026-02-18 | 2026-02-25 | 2026-03-18 | 2026-03-09 | 2026-03-11 | 2026-03-18 | 2026-03-11 | 2026-03-25 | 2026-05-20
25-356 | Synthomer | 2026-06-11 | 4 | 1 | 0 | 1 | 1 | 2025-11-09 | 2025-11-30 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-22 | 2026-01-20 |  | 2026-02-28 | 2026-03-01 | 2026-03-05 | 2026-03-12 | 2026-03-19 | 2026-04-09 | 2026-03-31 | 2026-04-02 | 2026-04-09 | 2026-04-02 | 2026-04-16 | 2026-06-11
25-357 | Sylvamo | 2026-05-20 | 4 | 1 | 0 | 1 | 1 | 2025-10-18 | 2025-11-08 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2025-12-31 | 2025-12-29 |  | 2026-02-06 | 2026-02-07 | 2026-02-11 | 2026-02-18 | 2026-02-25 | 2026-03-18 | 2026-03-09 | 2026-03-11 | 2026-03-18 | 2026-03-11 | 2026-03-25 | 2026-05-20
25-358 | Sylvamo | 2026-05-20 | 4 | 1 | 0 | 1 | 1 | 2025-10-18 | 2025-11-08 | 2025-11-22 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2025-12-31 | 2025-12-29 |  | 2026-02-06 | 2026-02-07 | 2026-02-11 | 2026-02-18 | 2026-02-25 | 2026-03-18 | 2026-03-09 | 2026-03-11 | 2026-03-18 | 2026-03-11 | 2026-03-25 | 2026-05-20
26-002 | SNF | 2026-06-30 | 4 | 1 | 0 | 1 | 1 | 2025-11-28 | 2025-12-19 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-10 | 2026-02-08 |  | 2026-03-19 | 2026-03-20 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-28 | 2026-04-19 | 2026-04-21 | 2026-04-28 | 2026-04-21 | 2026-05-05 | 2026-06-30
26-003 | SNF | 2026-06-30 | 4 | 1 | 0 | 1 | 1 | 2025-11-28 | 2025-12-19 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-10 | 2026-02-08 |  | 2026-03-19 | 2026-03-20 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-28 | 2026-04-19 | 2026-04-21 | 2026-04-28 | 2026-04-21 | 2026-05-05 | 2026-06-30
26-004 | SNF | 2026-06-30 | 4 | 1 | 0 | 1 | 1 | 2025-11-28 | 2025-12-19 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-10 | 2026-02-08 |  | 2026-03-19 | 2026-03-20 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-28 | 2026-04-19 | 2026-04-21 | 2026-04-28 | 2026-04-21 | 2026-05-05 | 2026-06-30
26-014 | SNF | 2026-05-28 | 5 | 1 | 0 | 1 | 1 | 2025-10-19 | 2025-11-09 | 2025-11-23 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-01 | 2025-12-30 |  | 2026-02-07 | 2026-02-08 | 2026-02-12 | 2026-02-19 | 2026-02-26 | 2026-03-19 | 2026-03-10 | 2026-03-12 | 2026-03-19 | 2026-03-12 | 2026-03-26 | 2026-05-28
26-015 | SNF | 2026-06-24 | 3 | 1 | 0 | 1 | 1 | 2025-11-29 | 2025-12-20 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-11 | 2026-02-09 |  | 2026-03-20 | 2026-03-21 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-29 | 2026-04-20 | 2026-04-22 | 2026-04-29 | 2026-04-22 | 2026-05-06 | 2026-06-24
26-016 | SNF | 2026-06-04 | 5 | 1 | 0 | 1 | 1 | 2025-10-26 | 2025-11-16 | 2025-11-30 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-08 | 2026-01-06 |  | 2026-02-14 | 2026-02-15 | 2026-02-19 | 2026-02-26 | 2026-03-05 | 2026-03-26 | 2026-03-17 | 2026-03-19 | 2026-03-26 | 2026-03-19 | 2026-04-02 | 2026-06-04
26-017 | SNF | 2026-06-25 | 5 | 1 | 0 | 1 | 1 | 2025-11-16 | 2025-12-07 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-01-29 | 2026-01-27 |  | 2026-03-07 | 2026-03-08 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-16 | 2026-04-07 | 2026-04-09 | 2026-04-16 | 2026-04-09 | 2026-04-23 | 2026-06-25
26-018 | SNF | 2026-06-25 | 5 | 1 | 0 | 1 | 1 | 2025-11-16 | 2025-12-07 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-18 | 2026-01-25 | 2026-01-29 | 2026-01-27 |  | 2026-03-07 | 2026-03-08 | 2026-03-12 | 2026-03-19 | 2026-03-26 | 2026-04-16 | 2026-04-07 | 2026-04-09 | 2026-04-16 | 2026-04-09 | 2026-04-23 | 2026-06-25
26-005 | US Sugar | 2026-06-03 | 5 | 1 | 0 | 1 | 1 | 2025-10-25 | 2025-11-15 | 2025-11-29 | 2025-12-06 | 2025-12-13 | 2025-12-20 | 2025-12-27 | 2026-01-03 | 2026-01-07 | 2026-01-05 |  | 2026-02-13 | 2026-02-14 | 2026-02-18 | 2026-02-25 | 2026-03-04 | 2026-03-25 | 2026-03-16 | 2026-03-18 | 2026-03-25 | 2026-03-18 | 2026-04-01 | 2026-06-03
26-020 | US Sugar | 2026-07-15 | 5 | 1 | 0 | 1 | 1 | 2025-12-06 | 2025-12-27 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-18 | 2026-02-16 |  | 2026-03-27 | 2026-03-28 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-05-06 | 2026-04-27 | 2026-04-29 | 2026-05-06 | 2026-04-29 | 2026-05-13 | 2026-07-15
26-021 | US Sugar | 2026-07-15 | 5 | 1 | 0 | 1 | 1 | 2025-12-06 | 2025-12-27 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-18 | 2026-02-16 |  | 2026-03-27 | 2026-03-28 | 2026-04-01 | 2026-04-08 | 2026-04-15 | 2026-05-06 | 2026-04-27 | 2026-04-29 | 2026-05-06 | 2026-04-29 | 2026-05-13 | 2026-07-15
25-120 | Andritz | 2026-07-08 | 5 | 1 | 0 | 1 | 1 | 2025-11-29 | 2025-12-20 | 2026-01-03 | 2026-01-10 | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-11 | 2026-02-09 |  | 2026-03-20 | 2026-03-21 | 2026-03-25 | 2026-04-01 | 2026-04-08 | 2026-04-29 | 2026-04-20 | 2026-04-22 | 2026-04-29 | 2026-04-22 | 2026-05-06 | 2026-07-08
26-022 | Andritz | 2026-06-04 | 4 | 1 | 0 | 1 | 1 | 2025-11-02 | 2025-11-23 | 2025-12-07 | 2025-12-14 | 2025-12-21 | 2025-12-28 | 2026-01-04 | 2026-01-11 | 2026-01-15 | 2026-01-13 |  | 2026-02-21 | 2026-02-22 | 2026-02-26 | 2026-03-05 | 2026-03-12 | 2026-04-02 | 2026-03-24 | 2026-03-26 | 2026-04-02 | 2026-03-26 | 2026-04-09 | 2026-06-04
Formulas:
App. Prints Submitted = [Customer Response]-21
Customer Response = [Resubmit]-J2
Customer Response = [Resubmit]-N2
Resubmit = [Customer Response]-O2
Long lead time = [Release Target]-Q2
Prelim BOM = [Long lead time]-R2
Final Calcs = [Cert Dwgs]-T2
A.I. = [Final Calcs]+U2
Cert Dwgs = [Update BOM]-V2
Update BOM = [Stock Check]-W2
Stock Check = [Order Balance]-X2
Order Balance = [Burn File]
Final BOM = [Build Plan]-Z2
Build Plan = [Burn File]-AA2
Build Plan = [Release Target]-AA2
Burn File = [Release Target]-AB2
QC Checklist = [Cert Dwgs]+AC2
QC Checklist = [Release Target]-AC2
Release Target = [Ship Date]-(SUM([Fabrication]:[Shipping Prep])*7)-7
Ship Date = [Ship Date]

## OGSM 2019 (hidden)
OGSM 2019 (EFFICIENCY MEASURE)
JOB | CUSTOMER | PO RECEIVING | KICK-OFF MEETING |  | INITIAL DWG SUBMISSION |  | BILL OF MATERIAL |  | BUILT PLAN |  | CERTIFIED DWG | SHOP RELEASE |  | CYCLE TIME | DWG DELAY | RELEASE DELAY | REMARK |  | TIME PERIOD | DWG DUE | DWG ON TIME | EFFICIENCY
|  |  | EXPECTED | ACTUAL | EXPECTED | ACTUAL | EXPECTED | ACTUAL | EXPECTED | ACTUAL |  | EXPECTED | ACTUAL
#REF! | #REF! | #REF! | #REF! | 2019-02-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | NP ON VACATION
#REF! | #REF! | #REF! | #REF! | 2019-02-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | NP ON VACATION
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | N/A | N/A | #VALUE! | N/A | N/A | #REF! | #VALUE!
#REF! | #REF! | #REF! | #REF! | 2019-03-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-03-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-04-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | APPROVAL ON LEG
#REF! | #REF! | #REF! | #REF! | 2019-03-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-04-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Customer changes
#REF! | #REF! | #REF! | #REF! | 2019-03-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Customer changes
#REF! | #REF! | #REF! | #REF! | 2019-03-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-03-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-03-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-03-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | AI dwg CHECK
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #VALUE! | N/A | #VALUE! | #REF! | #VALUE! | TOE plate JN 071-18
#REF! | #REF! | #REF! | #REF! | 2019-05-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-04-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-04-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-04-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-04-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #VALUE! | #REF! | #VALUE! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-05-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | CRN APPROVAL
#REF! | #REF! | #REF! | #REF! | 2019-05-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | CRN APPROVAL
#REF! | #REF! | #REF! | #REF! | 2019-05-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | NO SCALED DWG
#REF! | #REF! | #REF! | #REF! | 2019-06-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-06-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-07-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Hurricane Dorian
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | AI dwg CHECK
#REF! | #REF! | #REF! | #REF! | 2019-08-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-08-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | YATES JOB WAS PRIORITY
#REF! | #REF! | #REF! | #REF! | 2019-09-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-09-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-10-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2019-11-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | [13 empty] | 0
#REF! | #REF! | #REF! | #REF! | 2019-12-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-03-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-04-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-05-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-06-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | N/A | N/A | N/A | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #VALUE! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-09-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-09-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-09-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-09-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-09-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-09-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-10-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-10-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-10-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-11-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-10-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | JAN' 2021 | #REF! | 6 | #REF!
#REF! | #REF! | #REF! | #REF! | 2020-12-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | FAB'2021 | #REF! | 2 | #REF!
#REF! | #REF! | #REF! | #REF! | N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | FAB'2021
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | MAR'21 | #REF! | 1 | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | FAB'2021
#REF! | #REF! | #REF! | #REF! | 2021-03-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | MAR'21 | 1 | 1
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-03-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-04-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-05-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-06-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-07-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-08-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-09-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-10-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-11-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2021-12-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-01-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-02-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24-046 | SYMS Engineering | 2024-08-15 | 2024-09-04 | 2022-03-23 | 2024-09-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-09-01 | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-03-31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-01 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-02 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-03 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-05 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-06 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-07 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-08 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-09 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | 2022-04-17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25-010 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-18 | 2025-03-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-09-14 | #REF! | #REF! | #REF! | #REF!
25-011 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-19 | 2025-03-04 | #REF! | #REF! | #REF! | #REF! |  | #REF! | 2025-09-21 | #REF! | #REF! | #REF! | #REF!
25-012 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-20 | 2025-03-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-09-21 | #REF! | #REF! | #REF! | #REF!
25-013 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-21 | 2025-03-04 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2025-06-22 | #REF! | #REF! | #REF! | #REF!
25-014 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-22 | 2025-03-04 | 2025-05-28 | 2025-09-02 | 2025-07-28 | 2025-09-03 |  | 2025-08-28 | 2025-06-07 | 2026-01-17 | 354 | -85 | -224
25-015 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-23 | 2025-03-04 | 2025-04-25 | 2025-09-09 | 2025-06-27 | 2025-09-10 |  | 2025-09-04 | 2025-06-07 | 0 | -45685 | -52 | 45815
25-016 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-24 | 2025-03-04 | 2025-04-25 | 2025-09-09 | 2025-07-01 | 2025-09-10 | 2025-01-07 | 2025-09-04 | 2025-06-07 | 2026-01-08 | 345 | -52 | -215
25-017 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-25 | 2025-03-04 | 2025-03-25 | 2025-06-09 | 2025-07-02 | 2025-06-10 |  | 2025-06-04 | 2025-05-01 | 2025-10-27 | 272 | -21 | -179
25-018 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-26 | 2025-03-04 | 2025-04-02 | 2025-06-02 | 2025-07-02 | 2025-06-03 | 2025-09-03 | 2025-05-28 | 2025-09-14 | 2025-09-03 | 218 | -29 | 11
25-019 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-27 | 2025-03-04 | 2025-04-02 | 2025-06-02 | 2025-07-17 | 2025-06-03 | 2025-08-27 | 2025-05-28 | 2025-09-21 | 2025-08-27 | 211 | -29 | 25
25-020 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-28 | 2025-03-04 | 2025-04-02 | 2025-06-02 | 2025-07-22 | 2025-06-03 |  | 2025-05-28 | 2025-09-14 | 2025-12-04 | 310 | -29 | -81
25-021 | Kimberly Clark | 2025-01-28 | 2025-03-03 | 2022-04-29 | 2025-03-04 | 2025-03-10 | 2025-04-25 | 2025-07-23 | 2025-04-28 | 2025-09-30 | 2025-04-22 | 2025-09-21 | 2025-09-30 | 245 | -6 | -9
25-023 | Andritz | 2025-01-30 | 2025-02-12 | 2022-04-30 | 2025-02-13 | 2025-05-21 | 2025-09-10 | 2025-09-19 | 2025-09-11 |  | 2025-09-05 | 2025-04-03 | 2025-10-24 | 267 | -97 | -204
25-024 | Andritz | 2025-01-30 | 2025-02-12 | 2022-05-01 | 2025-02-13 | 2025-05-13 | 2025-09-10 | 2025-09-17 | 2025-09-11 |  | 2025-09-05 | 2025-04-03 | 2025-12-04 | 308 | -89 | -245
25-025 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-02 | 2025-03-05 | 2025-03-25 | 2025-08-29 | 2025-08-19 | 2025-09-01 |  | 2025-08-26 | 2025-06-15 | 2025-09-04 | 211 | -20 | -81
25-026 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-03 | 2025-03-05 | 2025-05-13 | 2025-09-05 | 2025-09-11 | 2025-09-08 |  | 2025-09-02 | 2025-06-06 | 2025-09-18 | 225 | -69 | -104
25-027 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-04 | 2025-03-05 | 2025-02-12 | 2025-03-13 | 2025-03-18 | 2025-03-14 |  | 2025-03-10 | 2025-06-06 | 2025-03-19 | 42 | 21 | 79
25-028 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-05 | 2025-03-05 | 2025-02-12 | 2025-03-13 | 2025-03-18 | 2025-03-14 |  | 2025-03-10 | 2025-06-06 | 2025-03-19 | 42 | 21 | 79
25-029 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-06 | 2025-03-05 | 2025-02-26 | 2025-06-02 | 2025-05-28 | 2025-06-03 |  | 2025-05-28 | 2025-06-06 | 2025-06-13 | 128 | 7 | -7
25-030 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-07 | 2025-03-05 | 2025-02-26 | 2025-05-23 | 2025-05-16 | 2025-05-26 |  | 2025-05-20 | 2025-06-06 | 2025-06-13 | 128 | 7 | -7
25-031 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-08 | 2025-03-05 | 2025-02-26 | 2025-05-23 | 2025-05-22 | 2025-05-26 |  | 2025-05-20 | 2025-06-14 | 2025-08-06 | 182 | 7 | -53
25-032 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-09 | 2025-03-05 | 2025-03-03 | 2025-05-23 | 2025-05-22 | 2025-05-26 |  | 2025-05-20 | 2025-06-14 | 2025-08-06 | 182 | 2 | -53
25-033 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-10 | 2025-03-05 | 2025-03-03 | 2025-05-23 | 2025-05-22 | 2025-05-26 |  | 2025-05-20 | 2025-06-14 | 2025-08-08 | 184 | 2 | -55
25-034 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-11 | 2025-03-05 | 2025-03-05 | 2025-05-23 | 2025-05-23 | 2025-05-26 |  | 2025-05-20 | 2025-06-14 | 2025-08-08 | 184 | 0 | -55
25-035 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-12 | 2025-03-05 | 2025-02-27 | 2025-06-02 | 2025-06-02 | 2025-06-03 |  | 2025-05-28 | 2025-06-14 | 2025-08-13 | 189 | 6 | -60
25-036 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-13 | 2025-03-05 | 2025-02-27 | 2025-06-02 | 2025-06-02 | 2025-06-03 |  | 2025-05-28 | 2025-06-14 | 2025-08-15 | 191 | 6 | -62
25-037 | Irving Tissue | 2025-02-05 | 2025-03-04 | 2022-05-14 | 2025-03-05 | 2025-03-05 | 2025-06-02 | 2025-06-04 | 2025-06-03 |  | 2025-05-28 | 2025-06-14 | 2025-08-20 | 196 | 0 | -67
25-039 | Zachry | 2025-02-26 | 2025-03-18 | 2022-05-15 | 2025-03-19 | 2025-02-26 | 2025-06-02 | 2025-06-06 | 2025-06-03 |  | 2025-05-28 | 2025-05-25 | 2025-07-02 | 126 | 21 | -38
25-040 | NAK Kiln | 2025-03-05 | 2025-03-18 | 2022-05-16 | 2025-03-19 | 2025-03-05 | 2025-06-02 | 2025-06-05 | 2025-06-03 | 2025-06-16 | 2025-05-28 | 2025-03-21 | 2025-07-02 | 119 | 14 | -103
25-042 | Andritz | 2025-03-19 | 2025-04-08 | 2022-05-17 | 2025-04-09 | 2025-02-26 | 2025-06-02 | 2025-06-06 | 2025-06-03 |  | 2025-05-28 | 2025-06-12 | 2025-07-02 | 105 | 42 | -20
25-044 | Noah Industrial | 2025-04-01 | 2025-04-28 | 2022-05-18 | 2025-04-29 | 2025-02-28 | 2025-06-02 | 2025-05-29 | 2025-06-03 |  | 2025-05-28 | 2025-06-22 | 2025-06-18 | 78 | 60 | 4
25-045 | ProPipe | 2025-04-05 | 2025-04-11 | 2022-05-19 | 2025-04-12 |  | #VALUE! | #VALUE! | #VALUE! |  |  | 2025-05-20 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
25-052 | Kraton | 2025-05-19 | 2025-06-06 | 2022-05-20 | 2025-06-09 | 2025-02-18 | 2025-03-18 | 2025-09-16 | 2025-03-19 |  | 2025-03-13 | 2025-08-15 | 2025-09-17 | 121 | 111 | -33
25-053 | Andritz | 2025-06-02 | 2026-01-02 | 2022-05-21 | 2026-01-05 |  | #VALUE! | 2025-05-29 | #VALUE! | 2025-06-20 |  | 2026-02-12 | 2025-07-01 | 29 | #VALUE! | 226
25-054 | Chromascape | 2025-06-03 | 2025-06-30 | 2022-05-22 | 2025-07-01 | 2025-05-14 | 2025-06-04 | 2025-06-17 | 2025-06-05 |  | 2025-05-30 | 2025-08-03 | 2025-06-25 | 22 | 48 | 39
25-055 | Airgas | 2025-06-12 | 2025-10-01 | 2022-05-23 | 2025-10-02 | 0 | 1900-01-03 | NA | 1900-01-04 |  | 0 | 2026-01-03 | 0 | -45820 | 45932 | 46025
25-056 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-24 | 2025-07-04 | 2025-06-11 | 2025-08-01 | 2025-09-12 | 2025-08-04 |  | 2025-07-29 | 2025-08-21 | 2025-09-23 | 102 | 23 | -33
25-057 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-25 | 2025-07-04 | 0 | 1900-01-03 | 2025-08-25 | 1900-01-04 |  | 0 | 2025-08-21 | 2025-08-28 | 76 | 45842 | -7
25-058 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-26 | 2025-07-04 | 2025-06-27 | 2025-07-22 | 2025-07-30 | 2025-07-23 |  | 2025-07-17 | 2025-08-21 | 2025-09-23 | 102 | 7 | -33
25-059 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-27 | 2025-07-04 | 2025-11-25 | 2025-12-22 | 2026-01-07 | 2025-12-23 |  | 2025-12-17 | 2025-08-21 | 2025-09-23 | 102 | -144 | -33
25-060 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-28 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 |  | 2025-08-04 | 2025-08-21 | 2025-08-20 | 68 | -5 | 1
25-061 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-29 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 |  | 2025-08-04 | 2025-08-21 | 2025-08-20 | 68 | -5 | 1
25-062 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-30 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 |  | 2025-08-04 | 2025-08-21 | 2025-09-03 | 82 | -5 | -13
25-063 | Reco | 2025-06-13 | 2025-07-03 | 2022-05-31 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 |  | 2025-08-04 | 2025-08-21 | 2025-09-03 | 82 | -5 | -13
25-064 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-01 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-09-26 | 105 | -5 | -36
25-065 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-02 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-09-26 | 105 | -5 | -36
25-066 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-03 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-11-10 | 150 | -5 | -81
25-067 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-04 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-11-10 | 150 | -5 | -81
25-068 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-05 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-12-09 | 179 | -5 | -110
25-069 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-06 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2025-12-09 | 179 | -5 | -110
25-070 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-07 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2026-01-12 | 213 | -5 | -144
25-071 | Reco | 2025-06-13 | 2025-07-03 | 2022-06-08 | 2025-07-04 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 | 2025-08-01 | 2025-08-04 | 2025-08-21 | 2026-01-12 | 213 | -5 | -144
25-072 | Burke Industrial | 2025-06-16 | 2025-07-04 | 2022-06-09 | 2025-07-07 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 |  | 2025-08-04 | 2025-07-31 | 2026-02-09 | 238 | -2 | -193
25-073 | Burke Industrial | 2025-06-16 | 2025-07-04 | 2022-06-10 | 2025-07-07 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 |  | 2025-08-04 | 2025-07-31 | 2026-02-09 | 238 | -2 | -193
25-074 | Kemira | 2025-06-16 | 2025-07-04 | 2022-06-11 | 2025-07-07 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 |  | 2025-08-04 | 2025-08-10 | 2026-02-18 | 247 | -2 | -192
25-075 | Kemira | 2025-06-16 | 2025-07-04 | 2022-06-12 | 2025-07-07 | 2025-07-09 | 2025-08-07 | 2025-08-06 | 2025-08-08 |  | 2025-08-04 | 2025-09-08 | 2026-02-18 | 247 | -2 | -163
25-076 | Irving tissue | 2025-06-17 | 2025-07-14 | 2022-06-13 | 2025-07-15 | 2025-07-03 | 2025-07-17 | 2025-07-21 | 2025-07-18 |  | 2025-07-14 | 2025-09-05 | 2025-07-30 | 43 | 12 | 37
25-077 | Epic Systems | 2025-06-25 | 2025-07-15 | 2022-06-14 | 2025-07-16 | 2025-07-03 | 2025-07-17 | 2025-07-21 | 2025-07-18 |  | 2025-07-14 | 2025-09-11 | 2025-07-30 | 35 | 13 | 43
25-078 | Epic Systems | 2025-06-25 | 2025-07-15 | 2022-06-15 | 2025-07-16 | 2025-07-16 | 2025-07-25 | 2025-08-01 | 2025-07-28 |  | 2025-07-22 | 2025-09-11 | 2025-09-11 | 78 | 0 | 0
25-079 | Epic Systems | 2025-06-25 | 2025-07-15 | 2022-06-16 | 2025-07-16 | 2025-07-16 | 2025-08-22 | 2025-08-29 | 2025-08-25 |  | 2025-08-19 | 2025-09-11 | 2025-10-30 | 127 | 0 | -49
25-080 | Domtar | 2025-06-27 | 2025-07-17 | 2022-06-17 | 2025-07-18 | 2025-07-28 | 2025-08-22 | 2025-08-21 | 2025-08-25 |  | 2025-08-19 | 2025-08-24 | 2025-08-28 | 62 | -10 | -4
25-083 | Synthomer | 2025-07-15 | 2025-08-04 | 2022-06-18 | 2025-08-05 | 2025-07-23 | 2025-08-28 | 2025-06-04 | 2025-08-29 | 2025-10-23 | 2025-08-25 | 2026-02-26 | 2025-10-31 | 108 | 13 | 118
25-084 | Atlas Minerals | 2025-07-18 | 2025-08-07 | 2022-06-19 | 2025-08-08 | 2025-07-21 | 2025-08-28 | 2025-09-03 | 2025-08-29 | 2025-10-23 | 2025-08-25 | 2025-11-28 | 2025-11-05 | 110 | 18 | 23
25-085 | Noah Industrial | 2025-07-22 | 2025-08-11 | 2022-06-20 | 2025-08-12 | 2025-07-21 | 2025-08-28 | 2025-09-03 | 2025-08-29 |  | 2025-08-25 | 2025-09-07 | 2025-11-05 | 106 | 22 | -59
25-086 | Tellus | 2025-07-30 | 2025-07-29 | 2022-06-21 | 2025-07-30 |  | #VALUE! | 2025-09-10 | #VALUE! |  |  | 2025-09-06 | 2025-10-30 | 92 | #VALUE! | -54
25-087 | Solvay | 2025-08-07 | 2025-08-27 | 2022-06-22 | 2025-08-28 | 0 | 1900-01-03 | NA | 1900-01-04 |  | 0 | 2025-10-02 | 0 | -45876 | 45897 | 45932
25-088 | CIL Isotopes | 2025-08-13 | 2025-09-02 | 2022-06-23 | 2025-09-03 | 2025-08-15 | 2025-11-07 | 2025-11-11 | 2025-11-10 |  | 2025-11-04 | 2025-10-03 | 2025-11-24 | 103 | 19 | -52
25-089 | Valmet | 2025-08-22 | 2025-09-19 | 2022-06-24 | 2025-09-22 12:00 | 2025-08-08 | 2025-11-07 | 2025-11-05 | 2025-11-10 | 2025-11-24 | 2025-11-04 | 2025-12-15 | 2025-11-24 | 94 | 45.5 | 21
25-090 | GAF | 2025-08-18 | 2025-08-22 | 2022-06-25 | 2025-08-25 | 2025-08-12 | 2025-08-22 | #VALUE! | 2025-08-25 |  | 2025-08-19 | 2025-09-29 | #VALUE! | #VALUE! | 13 | #VALUE!
25-091 | US Sugar | 2025-09-04 | 2025-09-10 | 2022-06-26 | 2025-09-11 |  | #VALUE! | 2025-08-27 | #VALUE! |  |  | 2025-10-19 | 2025-08-26 | -9 | #VALUE! | 54
25-092 | Symrise | 2025-09-10 | 2025-10-07 | 2022-06-27 | 2025-10-08 | 2025-08-28 | 2025-09-18 | 2025-09-22 | 2025-09-19 | 2025-09-22 | 2025-09-15 | 2025-11-16 | 2025-09-24 | 14 | 41 | 53
25-093 | Symrise | 2025-09-10 | 2025-10-07 | 2022-06-28 | 2025-10-08 | 2025-09-03 | 2025-09-18 | 2025-09-22 | 2025-09-19 | 2025-09-22 | 2025-09-15 | 2025-11-16 | 2025-10-23 | 43 | 35 | 24
25-094 | Kimberly Clark | 2025-09-15 | 2025-10-03 | 2022-06-29 | 2025-10-06 | 2025-09-22 | 2025-12-09 | 2025-12-09 | 2025-12-10 |  | 2025-12-04 | 2025-11-13 | 2025-12-16 | 92 | 14 | -33
25-095 | Andritz | 2025-09-19 | 2025-10-16 | 2022-06-30 | 2025-10-17 | 2025-08-22 | #VALUE! | #VALUE! | #VALUE! |  |  | 2026-02-26 | #VALUE! | #VALUE! | 56 | #VALUE!
25-096 | Milliken | 2025-09-22 | 2025-10-10 | 2022-07-01 | 2025-10-13 | 0 | 1900-01-03 | 2025-09-23 | 1900-01-04 |  | 0 | 2025-11-09 | 2025-09-23 | 1 | 45943 | 47
25-097 | Milliken | 2025-09-22 | 2025-10-10 | 2022-07-02 | 2025-10-13 | 2025-10-01 | 2025-10-30 | 2025-11-18 | 2025-10-31 |  | 2025-10-27 | 2025-11-09 | 2026-01-13 | 113 | 12 | -65
25-098 | Coastal Technologies | 2025-09-24 | 2025-10-21 | 2022-07-03 | 2025-10-22 | 2025-10-01 | 2025-10-30 | 2025-11-18 | 2025-10-31 |  | 2025-10-27 | 2026-03-01 | 2026-01-13 | 111 | 21 | 47
25-099 | Burke Industrial | 2025-10-02 | 2025-10-29 | 2022-07-04 | 2025-10-30 | 2025-10-06 | 2025-11-21 | 2025-11-21 | 2025-11-24 | 2025-12-01 | 2025-11-18 | 2025-11-22 | 2025-12-09 | 68 | 24 | -17
25-101 | Harper Love | 2025-10-24 | 2025-11-20 | 2022-07-05 | 2025-11-21 | 2025-10-16 | 1900-01-03 | NA | 1900-01-04 | 0 | 0 | 2025-12-25 | 0 | -45954 | 36 | 46016
25-102 | Epic Systems | 2025-11-07 | 2025-12-11 | 2022-07-06 | 2025-12-12 | 2025-10-15 | #VALUE! |  | #VALUE! |  |  | 2026-03-15 |  | #VALUE! | 58 | #VALUE!
25-103 | Epic Systems | 2025-11-07 | 2025-12-11 | 2022-07-07 | 2025-12-12 | 2025-10-15 | 2025-10-28 |  | 2025-10-29 |  | 2025-10-23 | 2026-03-15 |  | #VALUE! | 58 | #VALUE!
25-104 | Epic Systems | 2025-11-07 | 2025-12-11 | 2022-07-08 | 2025-12-12 | 2025-10-22 | 2025-11-04 |  | 2025-11-05 |  | 2025-10-30 | 2026-03-15 |  | #VALUE! | 51 | #VALUE!
25-105 | Epic Systems | 2025-11-07 | 2025-12-11 | 2022-07-09 | 2025-12-12 | 2025-10-29 | 2025-11-10 |  | 2025-11-11 |  | 2025-11-05 | 2026-03-15 |  | #VALUE! | 44 | #VALUE!
25-106 | Epic Systems | 2025-11-07 | 2025-12-11 | 2022-07-10 | 2025-12-12 | 2025-11-20 | #VALUE! |  | #VALUE! |  |  | 2026-03-15 |  | #VALUE! | 22 | #VALUE!
25-107 | Epic Systems | 2026-02-02 | 2026-02-27 | 2022-07-11 | 2026-03-02 | 2025-12-12 | #VALUE! |  | #VALUE! |  |  | 2026-02-26 |  | #VALUE! | 80 | #VALUE!
25-108 | Epic Systems | 2025-10-30 | 2025-11-26 | 2022-07-12 | 2025-11-27 | 2025-12-12 | #VALUE! |  | #VALUE! |  |  | 2026-02-26 |  | #VALUE! | -15 | #VALUE!
25-109 | Epic Systems | 2025-10-30 | 2025-11-26 | 2022-07-13 | 2025-11-27 | 2025-12-12 | 2026-02-24 | 0 | 2026-02-25 | 0 | 2026-02-19 | 2026-03-15 | 0 | -45960 | -15 | 46096
25-110 | Epic Systems | 2025-10-30 | 2025-11-26 | 2022-07-14 | 2025-11-27 | 2025-12-12 | #VALUE! | 0 | #VALUE! | 0 |  | 2026-02-16 | 0 | -45960 | -15 | 46069
25-111 | Epic Systems | 2025-10-30 | 2025-11-26 | 2022-07-15 | 2025-11-27 | 2025-12-12 | #VALUE! |  | #VALUE! |  |  | 2026-02-16 |  | #VALUE! | -15 | #VALUE!
25-112 | Epic Systems | 2025-10-30 | 2025-11-26 | 2022-07-16 | 2025-11-27 | 2025-11-26 | #VALUE! |  | #VALUE! |  |  | 2026-02-16 |  | #VALUE! | 1 | #VALUE!
25-113 | Epic Systems | 2025-11-14 | 2025-12-11 | 2022-07-17 | 2025-12-12 | 2025-11-26 | #VALUE! |  | #VALUE! |  |  | 2026-02-26 |  | #VALUE! | 16 | #VALUE!
25-115 | Epic Systems | 2025-10-30 | 2025-11-26 | 2022-07-18 | 2025-11-27 | 2025-11-26 | 2026-02-24 |  | 2026-02-25 |  | 2026-02-19 | 2026-03-15 |  | #VALUE! | 1 | #VALUE!
25-116 | Polynt | 2025-11-04 | 2025-12-01 | 2022-07-19 | 2025-12-02 | 2025-11-26 | #VALUE! | 2026-02-02 | #VALUE! | 0 |  | 2026-03-08 | 0 | -45965 | 6 | 46089
25-117 | Merrick | 2025-11-07 | 2026-01-08 | 2022-07-20 | 2026-01-09 | 2025-11-26 | 1900-01-03 | 0 | 1900-01-04 | 0 | 0 | 2026-02-26 | 0 | -45968 | 44 | 46079
25-118 | Merrick | 2025-11-07 | 2026-01-08 | 2022-07-21 | 2026-01-09 | 2025-11-26 | 1900-01-03 |  | 1900-01-04 | 0 | 0 | 2026-03-05 | 0 | -45968 | 44 | 46086
25-119 | Vertiv | 2025-11-14 | 2025-11-27 | 2022-07-22 | 2025-11-28 | 2025-12-12 | 1900-01-03 |  | 1900-01-04 |  | 0 | 2025-12-27 |  | #VALUE! | -14 | #VALUE!
25-120 | Andritz | 2025-11-21 | 2025-11-20 | 2022-07-23 | 2025-11-21 |  | #VALUE! |  | #VALUE! |  |  | 2025-12-29 |  | #VALUE! | #VALUE! | #VALUE!
25-121 | Kimberly Clark | 2025-12-04 | 2025-12-31 | 2022-07-24 | 2026-01-01 | 2025-12-19 | #VALUE! |  | #VALUE! |  |  | 2026-03-13 |  | #VALUE! | 13 | #VALUE!
25-122 | Kimberly Clark | 2025-12-04 | 2025-12-31 | 2022-07-25 | 2026-01-01 | 2026-01-14 | #VALUE! |  | #VALUE! |  |  | 2026-03-13 |  | #VALUE! | -13 | #VALUE!
25-123 | Kimberly Clark | 2025-12-04 | 2025-12-31 | 2022-07-26 | 2026-01-01 | 2026-01-14 | #VALUE! |  | #VALUE! |  |  | 2026-02-15 |  | #VALUE! | -13 | #VALUE!
25-124 | Vertiv | 2025-12-15 | 2025-12-12 | 2022-07-27 | 2025-12-15 |  | #VALUE! | 0 | #VALUE! |  |  | 2026-01-22 | 0 | -46006 | #VALUE! | 46044
25-356 | Synthomer | 2025-12-29 | 2026-01-23 | 2022-07-28 | 2026-01-26 | 0 | #VALUE! |  | #VALUE! |  |  | 2026-02-26 |  | #VALUE! | 46048 | #VALUE!
25-357 | Sylvamo | 2025-12-30 | 2026-01-26 | 2022-07-29 | 2026-01-27 | 2026-01-08 | #VALUE! |  | #VALUE! |  |  | 2026-03-07 |  | #VALUE! | 19 | #VALUE!
25-358 | Sylvamo | 2025-12-30 | 2026-01-26 | 2022-07-30 | 2026-01-27 | 2026-01-08 | #VALUE! |  | #VALUE! |  |  | 2026-03-07 |  | #VALUE! | 19 | #VALUE!
Formulas:
KICK-OFF MEETING = WORKDAY([INITIAL DWG SUBMISSION],-1,)
BILL OF MATERIAL = WORKDAY([CERTIFIED DWG],3,)
BUILT PLAN = WORKDAY([CERTIFIED DWG],4,)
ACTUAL = IF(VLOOKUP([JOB],'Actual Dates'!A4:AF778,8,),'Actual Dates'!H5,"")
ACTUAL = IF(VLOOKUP([JOB],'Actual Dates'!A4:AF773,25,),'Actual Dates'!AA5,"")
CERTIFIED DWG = IF(VLOOKUP([JOB],'Actual Dates'!A4:AF801,21,),'Actual Dates'!U5,"")

## DRAWING EFFICIENCY (hidden)
| TIME PERIOD | DWG DUE | DWG ON TIME | EFFICIENCY | TARGET
2021 | JANUARY | #REF! | 6 | #REF! | 95%
| FEBRUARY | #REF! | 2 | #REF! | 95%
| MARCH | 2 | 2 | 100% | 95%
| APRIL | 2 | 2 |  | 95%
| MAY | 2 | 2 |  | 95%
| JUNE |  |  |  | 95%
| JULY |  |  |  | 95%
| AUGUST |  |  |  | 95%
| SEPTEMBER |  |  |  | 95%
| OCTOBER |  |  |  | 95%
| NOVEMBER |  |  |  | 95%
| DECEMBER |  |  |  | 95%
2022 | JANUARY |  |  |  | 95%
| FEBRUARY |  |  |  | 95%
| MARCH |  |  |  | 95%
| APRIL |  |  |  | 95%
| MAY |  |  |  | 95%
| JUNE |  |  |  | 95%
| JULY |  |  |  | 95%
| AUGUST |  |  |  | 95%
| SEPTEMBER |  |  |  | 95%
| OCTOBER |  |  |  | 95%
| NOVEMBER |  |  |  | 95%
| DECEMBER |  |  |  | 95%